Concession Agreement

By & Between

[•]

(As The Agency)

And

[•]

(As The Concessionaire)

In Respect Of

[•]

Dated: as of _________________

Table of Contents

1.	Definitions & Interpretation	5

2.	Concession	41

3.	Conditions	42

4.	Project Site	50

5.	Independent Engineer	61

6.	Independent Auditor	65

7.	Concessionaire’s Representations, Warranties and Certain Obligations & Undertakings	69

8.	Agency Representations, Warranties And Certain Obligations &Undertakings	88

9.	Indemnities & Limitation of Liability	95

10.	Equity And Funding Matters	100

11.	Development Performance Security & O&M Performance Security	101

12.	Financing Matters	106

13.	Development Works	107

14.	Completion	112

15.	Relief Extensions & Relief Compensations	116

16.	Change of Scope	125

17.        Revenue Matters	129

18.	Defects & Deficiencies, Notice of Remedy, Suspension	130

19.	Operation and Maintenance	133

20.	Insurances	142

21.	Force Majeure	147

22.	Events of Default	153

23.	Termination	159

24.	Divestment of Rights and Interest	165

25.	Defects Liability During Exit Implementation Period	169

26.	Disclaimer	170

27.	Assignment and Charges	172

29.	Dispute Resolution	173

30.	Miscellaneous	175

List of Schedules	179

Signature Page	179

Concession Agreement

This ‘Concession Agreement’ (this Agreement) is entered into on this [Date] of [Month], [Year] at [Location], Pakistan:

By and Between

[•] having its offices at [•] for and on behalf of the [•] (the Agency);

And

[•], a company incorporated under the Applicable Laws of Pakistan, having its registered office located at [•] (the Concessionaire, which expression shall, where the context so permits, be deemed to mean and include its successors-in-interest and permitted assigns),

(the Agency and the Concessionaire are hereinafter collectively referred to as the Parties and each individually as a Party).

Recitals

- On RFP Publication Date, a Request for Proposals (together with the related advertisements) (the RFP) was issued by the Agency to prospective bidders for the grant of the Concession for the implementation of the Project through public private partnership, under the Project Modality. Upon conclusion of the bidding process pursuant to the RFP, the Sponsor was selected by the Agency for such purposes. The letter of award was issued to the Sponsor by the Agency on the LOA Date.

- In accordance with the requirements of the RFP and the terms of the Bid, the Sponsor incorporated the Concessionaire as a special purpose vehicle to implement the Project, and the Agency has agreed to grant to the Concessionaire the right and obligation to implement the Project on the terms and conditions contained in this Agreement.

- The Concessionaire acknowledges and confirms that it has, based on the RFP, undertaken a thorough due diligence (including the technical, financial, and legal due diligence) of the Project and its requirements, and on the basis of its independent assessment is entering into this Agreement for the purpose of accepting the Concession for the implementation of the Project under the Project Modality in accordance with the terms and conditions of this Agreement.

- The Parties are now entering into this Agreement to set out the terms and conditions applicable to, inter alia, the Concession and the implementation of the Project, and the relationship of the Agency and the Concessionaire and their respective rights and obligations.

Now, therefore, this agreement witnesseth and it is hereby agreed to by and between the Parties as follows:

# Definitions & Interpretation

## Definitions

In this Agreement (including the Recitals), unless the context shall otherwise require:

Abandonment or Abandoned means the voluntary cessation of the development or Operation and Maintenance of the Concession Assets by the Concessionaire and/or the withdrawal of all, or substantially all, personnel by Concessionaire from the Project Site for reasons other than a Permitted Event;

Acceptable Pakistani Bank shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Accounting Year shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Additional Cost means the additional capital expenditure and/or the additional operating cost and/or, any adverse financial impact on the Concessionaire and/or additional taxes and/or all of the above as the case may be, which the Concessionaire has or would be required to incur and which has/have arisen as a consequence of Change of Scope; provided, that the Additional Costs shall be paid and treated in such manner as is stipulated in Section [x];

Affected Party shall have the meaning ascribed thereto in Section 21.1 (Force Majeure Event);

Agency shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Agency Agreements means:

- this Agreement;

- the Project Site Land Instrument;

- the Specific Agency Agreements; and

- any other agreement entered into in respect of the Project between the:

- Agency; and

- Concessionaire and/or the Sponsor in respect of the Project and designated as a “Agency Agreement” with the written consent of the Agency;

Agency Conditions Precedent shall have the meaning ascribed thereto in Section 3.1.3;

Agency CP Failure Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payments);

Agency Default Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payments);

Agency Event of Default shall have the meaning ascribed thereto in Section 22.2.1;

Agency Indemnified Persons shall have the meaning ascribed thereto in Section 9.1.1;

Agency Overriding Power Event shall have the meaning ascribed thereto in Section 8.9.1;

Agency Remedy Amount shall have the meaning ascribed thereto in Section 18.2.3;

Agency Remedy Invoice shall have the meaning ascribed thereto in Section 18.2.3;

Agency Representative means the representative of the  Agency  appointed by the  Agency for purposes of this Agreement in accordance with Section 8.8 (Agency Representative);

Agreement means this ‘Concession Agreement’ including the Recitals, Main Body and all Schedules attached hereto;

Applicable Laws means all applicable federal, provincial and local laws, promulgated or brought into force and effect in Pakistan, as the case may be, including regulations and rules made thereunder, and judgments, decrees, injunctions, writs and orders of any court of record, as may be in force and effect during the subsistence of this Agreement;

Applicable Standards means the standards, specifications, requirements and criterion set out in relation to and applicable to:

- the Project Works;

- the Project and its implementation;

- the Concession Assets; and

- the performance by the Concessionaire and the Sponsor (as applicable) of their respective obligations under the Agency Agreements;

in each case above, as contained and set out in (as applicable):

- this Agreement (including all Schedules attached hereto);

- the Agency Agreements;

- the Applicable Laws;

- the Concessionaire Permits;

- the Environmental Standards;

- the Specific Requirements; and

- any other standards, requirements and criterion, mutually agreed between the Parties from time to time,

provided, however, that in the event of any discrepancy in the standards, requirements and criterion set out in the abovementioned, the standards, requirements and criterion in accordance with nationally and internationally accepted standards as per Good Industry Practice (as applicable), shall apply (unless otherwise mutually agreed between the Parties);

Approved Pre-Commencement Costs shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Arbitration Act means the Arbitration Act, 1940 and shall include modifications to or any re-enactment thereof as in force from time to time;

Associate or Affiliate means, in relation to either Party and/or the Sponsor, a Person who controls, is controlled by, or is under the common control with such Party and/or the Sponsor (as used in this definition, the expression “control” means, with respect to a Person which is a company or corporation, the ownership, directly or indirectly, of more than 50% (fifty per cent) of the voting shares of such person and the power to direct the management and policies of such Person, whether by operation of law or by contract or otherwise), and with respect to a Person which is not a company or corporation, the power to direct the management and policies of such Person, whether by operation of law or by contract or otherwise);

Award shall have the meaning ascribed thereto in Section 28.3.4;

Base Case Financial Model means the financial model attached herewith as Schedule U (Financial Model);

Base Price shall have the meaning ascribed thereto in Schedule Q (Price Escalations);

Bid means the technical and financial bid of the Sponsor with respect to the Project submitted to the Agency on [•];

Bid Submission Date means the date on which the Bid is submitted;

Board of Arbitrators shall have the meaning ascribed thereto in Section 28.3.1;

Board Resolution means a resolution passed by the board of directors of the Concessionaire authorizing the Concessionaire to, inter alia, enter into this Agreement;

Cash Collateral Account shall have the meaning ascribed thereto in Section 11.1.4;

Change in Complete Control shall have the meaning ascribed thereto in Schedule P (Equity Matters);

Change in Control shall have the meaning ascribed thereto in Schedule P (Equity Matters) (•);

Change in Insurance Market shall have the meaning ascribed thereto in Section 20.10.1;

Change in Law means the occurrence of any of the following events on or after the Bid Submission Date:

- the enactment of any new federal, provincial or local government law, as applicable in the Project Jurisdiction;

- the repeal, morrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrdification or re-enactment of any existing federal, provincial or local government law, as applicable in the Project Jurisdiction;

- the imposition by a Government Authority of any additional Concessionaire Permit;

- a change in the interpretation or application of any Applicable Law (as applicable in the Project Jurisdiction) by a court of record as compared to such interpretation or application by a court of record prior to the date of this Agreement; and

provided, that any Excluded Change In Law shall not constitute a ‘Change in Law’;

Change in Law Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payment);

Change in Shareholding shall have the meaning ascribed thereto in Schedule P (Equity Matters);

Change of Scope shall have the meaning ascribed thereto in Section 16.1 (Change of Scope);

Change of Scope Advance Percentage shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Change of Scope Notice shall have the meaning ascribed thereto in Section 16.2.2;

Change of Scope Limit shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Commencement Certificate means a certificate to be jointly issued in writing by the Independent Engineer and the Independent Auditor to the Concessionaire and copied to the Agency in accordance with Section 3.3 (Commencement Certificate & Commencement Date);

Commencement Date means the date set out in the Commencement Certificate being the date on which each of the Conditions Precedent stand satisfied, waived and/or deferred;

Commencement Date Delay Notice shall have the meaning ascribed thereto in Section 3.5.3;

Commercial Operations Date means the date on which the Operations Period shall commence, such period commencing on the day immediately succeeding the Substantial Completion Date;

Completion Tests means the tests required to be conducted for Substantial Completion, as listed in Schedule G (Completion Tests Matters);

Completion Tests Date Notice shall have the meaning ascribed thereto in Section 14.1.1;

Concession means the right granted by the Agency to the Concessionaire to develop, build, operate and maintain the Concession Assets and carry out all other works that may be required to carry out such development, operation and maintenance in accordance with the terms of this Agreement, during the Concession Period;

Concession Assets means and includes all tangible and intangible assets located on the Project Site and all rights, title, benefits, facilities and easements, whether directly and/or indirectly related thereto, relating to and forming part of the Project (only to the extent of the Project Site);

Concession Period means, in respect of the Concession and the Concession Assets, the period commencing on the Commencement Date and ending on the Trigger Date;

Concessionaire shall have the meaning ascribed thereto in the Preamble;

Concessionaire Authorized Representative shall have the meaning ascribed thereto in Section 7.4.1;

Concessionaire Conditions Precedent shall have the meaning ascribed thereto in Section 3.1.2;

Concessionaire CP Failure Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payments);

Concessionaire Default Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payment);

Concessionaire Engaged Persons means each of the Concessionaire’s representatives (including the Concessionaire Authorized Representative and the Concessionaire Project Expert), agents, executives, contractors, employees, subcontractors, vendors, suppliers, parties with whom it has entered into the Project Agreements, that are engaged, hired, appointed, contracted (directly or indirectly) by the Concessionaire for the performance of Project Works or any part thereof;

Concessionaire Event of Default shall have the meaning ascribed thereto in Section 22.1.1 (Concessionaire Event of Default);

Concessionaire Indemnified Persons shall have the meaning ascribed thereto in Section 9.1.2;

Concessionaire Preliminary Notice shall have the meaning ascribed thereto in Section 23.2.1;

Concessionaire Project Expert shall have the meaning ascribed thereto in Section 7.4.1(b);

Concessionaire Permits means all such approvals, consents, authorizations, notifications, concessions, acknowledgements, licenses, permits, decisions or similar items that relate to the Project and its implementation including all such consents and authorisations issued by a Government Authority and which the Concessionaire is or its Contractors are required to obtain from any Government Authority and thereafter to maintain to fulfill its obligations under the Agency Agreements; provided, however, that in no event shall the Concessionaire Permits include any concessions or exemptions from the Applicable Laws unless they are expressly granted pursuant to the terms of the  Agency Agreements;

Conditions Precedent shall have the meaning ascribed thereto in Section 3.1 (Conditions Precedent);

Consent(s) means any permit, license, approval, concession, right, award, registration, certification, waiver, exemption, or other authorization, including any amendments thereto, that is required from any Government Authority;

Contractor(s) means the Development Contractor and the O&M Contractor and any of the Concessionaire’s other direct contractors and any of their direct sub-contractors integrally involved in the Project for the performance of Project Works (or any part thereof);

Compensation Amount shall have the meaning ascribed thereto in Section 4.10.3;

Completion Check List shall have the meaning ascribed thereto in Section 14.3.2;

Completion Check List Items shall have the meaning ascribed thereto in Section 14.4.1;

Corporate Documents means the constitutional documents and the corporate authorizations set out in Schedule K (Corporate Documents);

Corrupt Act means:

- offering, giving or agreeing to give to the Agency, a Government Authority or to any Person employed by or on behalf of the Agency and/or a Government Authority any gift or consideration of any kind as an inducement or reward:

- for doing or not doing (or for having done or not having done) any act in relation to the obtaining or performance of this Agreement or any other contract relating to this Agreement with the Agency and/or a Government Authority; or

- for showing or not showing favor or disfavor to any Person in relation to this Agreement or any other contract relating to this Agreement with the Agency and/or a Government Authority;

- entering into this Agreement or any other contract relating to this Agreement with the Agency and/or a Government Authority in connection with which commission / discount has been paid / received (as the case may be) or has been agreed to be paid or received by the Concessionaire or on its behalf, or to its knowledge, unless before the relevant contract is entered into particulars of any such commission and the terms and conditions of any such contract for the payment of such commission / discount have been disclosed in writing to the Agency;

- committing any offence:

- under any law, in respect of fraudulent acts in relation to this Agreement, from time to time dealing with bribery, corruption or extortion;

- under any law, in respect of fraudulent acts in relation to this Agreement, creating offences in respect of fraudulent acts; or

- in respect of fraudulent acts in relation to this Agreement;

- in respect of fraudulent acts in relation to this Agreement, defrauding or attempting to defraud or conspiring to defraud the Agency or any other public body;

Corrupt Act Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payments);

Cure Period means:

- in respect of a Concessionaire Event of Default during any period when any Financing Due is not outstanding, the period commencing on the date of receipt by the Concessionaire of the Agency Preliminary Notice and expiring on the date falling forty-five (45) days thereafter;

- in respect of a Agency Event of Default, the period commencing on the date of receipt by the Agency of the Concessionaire Preliminary Notice and expiring on the date falling sixty (60) days thereafter;

Daily Development Period Damages shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Decommissioned Project Area shall have the meaning ascribed thereto in Section 7.12.1;

Defects Liability Period shall have the meaning ascribed thereto in Section 25.1.1;

Defects & Deficiencies means:

(a)	in respect of Project Works, any Project Works (or any part thereof) that fail to conform to the Applicable Standards in any manner (including (without limitation) in services, performance, materials, development execution, operations and maintenance and/or workmanship);

(b)	in respect of the Concession Assets, any Concession Asset (or any part thereof) that fail to conform to the Applicable Standards;

Delayed Payment Rate shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Development Inspection Report shall have the meaning ascribed thereto in Section 13.5.2;

Development Progress Report shall have the meaning ascribed thereto in Section 13.4.1;

Development Performance Security shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Development Performance Security Expiry Certificate shall have meaning ascribed thereto in section 11.1.9.

Development Performance Security Expiry Date shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Development Period means the period commencing on the Commencement Date and ending on the Project Development Completion Date;

Development Period Damages shall have the meaning ascribed thereto in Section 14.5.1;

Development Period Damages Cap shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Development Period Damages Payment Date shall have the meaning ascribed thereto in Section 14.5.2;

Development Period Insurances means the Insurances procured and/or obtained by the Concessionaire pursuant to the provisions of and in accordance with Section 20.1 (Development Period Insurances) and Part I (Development Period Insurances) of Schedule I (Insurances);

Development Programme shall bear the meaning ascribed thereto in Section 13.2.2;

Development Progress Reporting Timeline shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Development Requirements means the relevant standards, requirements and criterion that are set out in relation to and are applicable to the Development Works, as set out in:

- the Main Body;

- the Scope of the Project;

- the Specific Requirements;

- the Schedule G (Completion Tests Matters);

- the Development Programme;

- any other standards, requirements and criterion, mutually agreed between the Parties from time to time,

provided, however, in the event of any discrepancy in the standards, requirements and criterion set out in the abovementioned, the standards, requirements and criterion in accordance with nationally and internationally accepted standards as per Good Industry Practice (as applicable), shall apply (unless otherwise mutually agreed between the Parties);

Development Tests shall bear the meaning ascribed thereto in Section 13.3.1;

Development Time for Completion means the time permitted herein for performance and completion of  Development Works and all other obligations to be performed by the Concessionaire for the issuance of the Project Development Completion Certificate, as set out in and contemplated by the Applicable Standards and the Development Programme, including the:

(i)	completion of development works on or prior to the date set out in the Project Development Completion Schedule;

(ii)	performance and completion of each Project Development Milestone on or prior to its Project Development Milestone Date;

(v)	achievement of Substantial Completion on or prior to the Scheduled Substantial Completion Date;

(vi)	achievement of Project Development Completion on or prior to the Scheduled Project Development Completion Date;

Development Works means all obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire until the Project Development Completion Date pursuant to the Applicable Standards including, inter alia, the obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire in respect of: (a) the procurement and development of the Concession Assets (including all activities and obligations incidental thereto); (b) the Site Development Works; and (c) the activities consisting of, and for achievement of, in each case, each Project Development Milestone;

Dispute shall have the meaning ascribed thereto in Section 28.1.1;

Dispute Resolution Procedure means the procedure for resolution of Disputes as set out in Article 30 (Dispute Resolution);

Divestment Requirements shall have the meaning ascribed thereto in Section 24.1.1;

Easementary Rights means all easements, reservations, rights-of-way, utilities and other similar purposes, or zoning or other restrictions relating to the Project Site and to the use of real property relating to the Project Site, which are necessary or appropriate for the conduct of activities of the Concessionaire related to the Concession Assets;

Effective Date means the date on which this Agreement is signed by each of the Parties;

EIA Approval means the approval obtained by the Concessionaire from the Relevant Environmental Protection Agency in relation to the Project;

Emergency Decommissioning shall have the meaning ascribed thereto in Section 7.12.1;

Emergency means a condition or situation that is likely to endanger the security of the individuals on or about the Project Site or which poses an immediate threat of material damage to any of the Concession Assets or the Project Site;

Encumbrance means any encumbrance on an asset, including but not restricted to mortgage, charge, pledge, lien, hypothecation and/or any security interest, assignment, privilege or priority of any kind having the effect of security or other such obligations and shall include without limitation any designation of loss payees or beneficiaries or any similar arrangement under any insurance policy pertaining to the Concession Assets and/or any part or portion thereof and physical encumbrances and encroachments thereon;

Environmental Standards means collectively, the applicable environmental guidelines and occupational health and safety standards established by the “Pakistan Environmental Protection Agency” and the Relevant Environmental Protection Agency;

Development Contract(s) means the agreement entered or to be entered into between the Concessionaire and the Development Contractor(s) in accordance with this Agreement, for, inter alia, the development, procurement, completion, testing of the Concession Assets and the commissioning of the same, as such agreement may be amended by the parties thereto from time to time;

Development Contractor(s) means the contractors engaged by the Concessionaire under the Development Contracts, meeting the eligibility criteria under the RFP and details in respect of which are provided in the RFP (if applicable);

Equity shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Escrow Account means the account established by the Concessionaire with the Escrow Agent;

Escrow Agent means the bank selected by the parties to the Escrow Agreement to manage the Revenues, compensation and expenditures of the Concessionaire;

Escrow Agreement means the agreement entered into by and between, inter alios, the Agency, the Escrow Agent and the Concessionaire, prior to the Scheduled Commencement Date, in relation to, inter alia, the obligations of the Concessionaire to deposit in and utilize from the Escrow Account, all Revenues;

Excluded Change In Law shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Exit Implementation Period means:

(a)	in case of Termination of this Agreement, the period commencing on the Termination Date and expiring on the Transfer Date;

(b)	in case of expiry of this Agreement on the Final Expiry Date, the period commencing thirty (30) days prior to the Final Expiry Date and expiring on the Final Expiry Date;

Extension Request Deadline shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Final Expiry Date shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Financial Model means the Base Case Financial Model, as revised by the Independent Auditor in accordance with the terms of this Agreement;

First IA List shall have the meaning ascribed thereto in Section 6.1.1;

First IE List shall have the meaning ascribed thereto in Section 5.1.1;

Force Majeure Costs shall have the meaning ascribed thereto in Schedule B (Specific Definitons)

Force Majeure Event means the occurrence of any or all of the Non-Political Events and/or the Political Events;

Force Majeure Notice shall have the meaning ascribed thereto in Section 21.2.1;

Force Majeure Period means, as determined by the Independent Engineer, the period commencing from the date of occurrence of a Force Majeure Event and ending on: (a) the date on which the Affected Party resumes or should have resumed (as determined by the Independent Engineer) such of its obligations the performance of which it was excused in terms of Section 21.8 (Excuse from Performance of Obligations); or (b) the Termination Date; as applicable;

Good Industry Practice means those practices, methods, techniques, standards, skills, diligence and prudence which are generally and reasonably expected from a reasonably skilled and experienced operator engaged in the same type of undertaking as envisaged in respect of the Concessionaire under this Agreement and acting generally in accordance with the provisions of the Applicable Laws, and would mean good development practices in the  development and project management and which would be expected to result in the performance of its obligations by the Concessionaire and in the operation and maintenance of the Project in accordance with the Applicable Standards. “Good Industry Practices” are not limited to optimum practices, methods, techniques, standards, skills, diligence, prudence or acts to the exclusion of all others, but rather are a spectrum of possible practices, methods, techniques, standards, skills, diligence, prudence or acts which could have been expected to accomplish the desired result at reasonable cost consistent with reliability and safety;

Government Authority(ies) means the Government of Pakistan, the Agency, any governmental department, commission, board, body, bureau, agency, authority, instrumentality, court or other judicial or administrative body having jurisdiction over the Concessionaire, the Project, Project Site, the Concession Assets or any part thereof, or the performance of all or any of the services or obligations of the Concessionaire under or pursuant to this Agreement;

Handover List shall have the meaning ascribed thereto in Section 25.1.1;

Indemnified Party shall have the meaning ascribed thereto in Section 9.3.1;

Indemnifying Party shall have the meaning ascribed thereto in Section 9.3.1;

Indemnity Survival Period shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Independent Auditor means the auditor appointed in respect of the Project in accordance with Article 6 (Independent Auditor) and in terms of the Independent Auditor Contract;

Independent Auditor Appointment Term shall have the meaning ascribed thereto in Section 6.2.1;

Independent Auditor Contract means the contract to be entered into between the Agency, the Concessionaire, the Independent Auditor and any other Person agreed by the Parties in accordance with Article 6 (Independent Auditor);

Independent Auditor Payments shall have the meaning ascribed thereto in Section 6.5.1;

Independent Auditor Payment Account means the account to be established by the Concessionaire and Notified to the Agency, in accordance with the terms of this Agreement and the Independent Auditor Contract;

Independent Auditor Payment Account Bank means a banking company mutually agreed between the Parties for the purposes of establishing and maintaining the account pursuant to the terms of the Independent Auditor Contract, the Agency Agreements and the Project Agreements;

Independent Auditor Payment Account Standing Instructions shall bear the meaning ascribed thereto in Section 6.6.2;

Independent Engineer means the engineer appointed in respect of the Project in accordance Article 5 (Independent Engineer) and in terms of the Independent Engineer Contract;

Independent Engineer Appointment Term shall have the meaning ascribed thereto in Section 5.2.1;

Independent Engineer Contract means the contract to be entered into between the  Agency, the Concessionaire, the Independent Engineer and any other Person agreed by the Parties, in accordance with Article 5 (Independent Engineer);

Independent Engineer Payments shall bear the meaning ascribed thereto in Section 5.5.1;

Independent Engineer Payment Account means the account to be established by the Concessionaire and Notified to the Agency, in accordance with the terms of this Agreement and the Independent Engineer Contract;

Independent Engineer Payment Account Bank means a banking company mutually agreed between the Parties for the purposes of establishing and maintaining the account pursuant to the terms of the Independent Engineer Contract, the Agency Agreements and the Project Agreements;

Independent Engineer Payment Account Standing Instructions shall bear the meaning ascribed thereto in Section 5.6.2;

Indicative Independent Auditor Terms of Reference means the duties, functions and the scope of work to be performed by the Independent Auditor, as indicatively attached herewith as Schedule N – Part I (Indicative Independent Auditor Terms of Reference); provided, however, upon execution of the Independent Auditor Contract, the scope of work of the Independent Auditor set out therein shall be deemed to replace Schedule N – Part I (Indicative Independent Auditor Terms of Reference);

Indicative Independent Engineer Terms of Reference means the duties, functions and the scope of work to be performed by the Independent Engineer, as indicatively attached herewith as Schedule N – Part II (Indicative Independent Engineer Terms of Reference); provided, however, upon execution of the Independent Engineer Contract, the scope of work of the Independent Engineer set out therein shall be deemed to replace Schedule N – Part II (Indicative Independent Engineer Terms of Reference);

Insurances means all insurances, reinsurance, agreements of insurance and reinsurance and/or arrangement for insurance and/or reinsurance in relation to the Project, the Concession Assets, the  Development Works and/or any part or portion thereof procured or to be procured by the Concessionaire, including but not restricted to the Development Period Insurances and the Operations Period Insurances;

Sponsor Invested Equity means the the aggregate of funds invested by the shareholders of the Sponsor Shares into the Concessionaire for funding the Project Cost;

Lapse of Consent means any Concessionaire Permit:

(a) 	ceasing to remain in full force and effect and not being renewed or replaced within the time period prescribed by the Applicable Laws for the renewal or replacement of such Concessionaire Permit or, where a time period is not prescribed by the Applicable Laws, within sixty (60) days of such Concessionaire Permit ceasing to be in full force and effect; or

(b) 	not being issued upon application having been properly and timely made and diligently pursued within the time period prescribed by the Applicable Laws or where a time period is not prescribed by the Applicable Laws, within sixty (60) days of proper application being made for such Concessionaire Permit; or

(c) 	being made subject, upon renewal, or otherwise, to any terms or conditions that materially and adversely affect the Concessionaire’s (or a Contractor’s) ability to perform its obligations under Agency Agreements and/or the Project Agreements,

in each of the above instances despite such party’s compliance with the applicable procedural and substantive requirements as applied in a “non-discriminatory” (as explained in Section 8.3.2) manner;

Legal Requirement means all Applicable Laws, Consents and Environmental Standards;

LOA Date shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Losses means any loss, damage, liability, payment and obligation (excluding any indirect or consequential loss, damage, liability, payment or obligation), and all expenses (including, without limitation, reasonable legal fees);

Main Body means this Agreement excluding the Schedules;

Material Adverse Effect means, in the opinion of the Independent Engineer (in respect of technical matters) and/or in the opinion of the Independent Auditor (in respect of financial matters), there has occurred or could reasonably be expected to occur an effect, event, matter or circumstance or a change in the circumstances which materially and adversely impairs:

- the business, operations, property, assets, present or future condition (financial or otherwise) or prospects of the Concessionaire, Sponsor or Contractor in respect of the Project;

- the ability or probability (financial or otherwise) of the Concessionaire, Sponsor or Contractor to perform and observe its respective obligations under the Project Agreements;

- the legality, validity or enforceability of, or the rights, obligations or remedies of, the Agency under this Agreement; and/or

- the Concessionaire’s ability to implement, finance, construct, operate and maintain the Project in accordance with the terms of the Project Agreements;

Material Adverse Impediment shall have the meaning ascribed to it in Section 4.13.1;

Material Breach means breach by either Party or Sponsor of any of its /their obligations under the Agency Agreements which has/is likely to have a Material Adverse Effect on the Project and which such breaching Party shall have failed to cure (within the applicable Cure Period) and if such Cure Period is not applicable then the date falling forty-five (45) days following the date of receipt of a notice issued by the non-breaching Party to the breaching Party to cure such breach;

Material Breach of O&M Requirements shall have the meaning ascribed to it in Section 19.3.1;

Material Impediment Removal Period shall have the meaning ascribed to it in Section 4.13.2;

Maximum Extension Period shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Minimum Indemnification Amount shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

New IA List shall have the meaning ascribed thereto in Section 6.2.3;

New IE List shall have the meaning ascribed thereto in Section 5.2.3;

New O&M Performance Security shall have the meaning ascribed to it in Section 11.2.7;

Non-Political Event shall bear the meaning ascribed thereto in Section 21.1.1(b);

Non-Political Event Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payments);

Notice, Notify, Notification and its grammatical variations means as notified in writing;

Notice of Remedy shall have the meaning ascribed thereto in Section 18.2.1(c);

O&M Costs shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

O&M Contract means the contract entered into or that may be entered into by the Concessionaire in accordance with this Agreement for the provision of the Operation and Maintenance in accordance with O&M Requirements and the O&M Manual;

O&M Contractor means the Person of good repute with whom the Concessionaire has entered into or may enter into the O&M Contract;

O&M Documents means all such reports, records, surveys, plans, analyses, calculations, manuals, operating procedures, guides and manuals, updated ‘as built’ drawings and documentation of any nature prepared, updated and submitted by the Concessionaire in connection with the Operations and Maintenance to the Agency, the Independent Engineer and/or the Independent Auditor pursuant to the Applicable Standards and pursuant to any requests made in accordance with the Applicable Standards by the Agency, the Independent Engineer and/or the Independent Auditor from time to time;

O&M Inspection Report shall have the meaning ascribed thereto in Section 19.11.2;

O&M Manual shall have the meaning ascribed thereto in Section 19.5.2;

O&M Status Report shall have the meaning ascribed thereto in Section 19.10.1;

O&M Performance Security shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

O&M Programme shall have the meaning ascribed thereto in Section 19.6.1;

O&M Requirements means the relevant standards, requirements and criterion that are set out in relation to and are applicable to the Operation and Maintenance, as set out in:

- the Main Body;

- the Scope of the Project;

- the Schedule H (O&M Requirements);

- the O&M Manual;

- the Safety Requirements;

- the Applicable Standards being the requirements applicable in respect of matters relating to the Concession Assets;

- in respect of each Operational Year following Substantial Completion Date, the O&M Programme prepared for such Operational Year in accordance with Section 19.6 (O&M Programme); and

- any other standards, requirements and criterion, mutually agreed between the Parties from time to time,

provided, however, in the event of any discrepancy in the standards, requirements and criterion set out in the abovementioned, the standards, requirements and criterion in accordance with nationally and internationally accepted standards as per Good Industry Practice (as applicable), shall apply (unless otherwise agreed between the Parties);

O&M Status Reporting Timeline shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

O&M Tests shall have the meaning ascribed thereto in Section 19.12.1;

O&M Time For Completion means the time permitted herein for performance and completion of Operations and Maintenance and all other obligations to be performed by the Concessionaire during the Operations Period, as set out in and contemplated by the Applicable Standards and each O&M Programme, including, performance and completion of each Project O&M Milestone on or prior to its Project O&M Milestone Date;

Order of Priority shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Operation and Maintenance or Operate and Maintain means all obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire during the Operations Period pursuant to the Applicable Standards including: (a) the preparation, completion and delivery of all O&M Documents; (b) the operation and maintenance of the Concession Assets during the Operations Period; (c) functions of operations, maintenance, safety measurements etc., and performance of other services and obligations incidental thereto; and (d) achievement of Project O&M Milestones;

Operational Year means a period of one (1) year commencing on each consecutive anniversary of the Commercial Operations Date and ending as of the end of the day preceding the next anniversary of the Commercial Operations Date, except for the first (1st) Operational Year which shall start on the Commercial Operations Date;

Operations Period means the period commencing on the Commercial Operations Date and ending on the Trigger Date;

Operations Period Insurances means the Insurances procured and/or obtained by the Concessionaire pursuant to the provisions of and in accordance with Section 20.2 (Operations Period Insurances) and Part I (Operations Period Insurances) of Schedule I (Insurances);

Party or Parties shall have the meaning ascribed thereto in the Preamble;

Permitted Events means:

- Force Majeure Events;

- Agency Events of Default;

- Emergency Decommissioning, to the extent the same does not result from reasons attributable to the Concessionaire;

- Material Adverse Impediment, to the extent the same does not result from reasons attributable to the Concessionaire;

- a Change in Law causing a delay in the performance of the Concessionaire’s obligations under this Agreement;

- the occurrence of the circumstances set out in Section 4.9 (Geological and Archeological Finds) causing a delay in the performance of the Concessionaire’s obligations under this Agreement; and

- the occurrence of the Agency Overriding Power Event, to the extent the same does not result from reasons attributable to the Concessionaire;

[Persistent Breach of O&M Requirements means:

- any reoccurring and persistent breach of the O&M Requirements that remains un-remedied despite the issuance of Notice of Remedy by the Independent Engineer;

- repeated occurrences of a breach that has been remedied pursuant to a Notice of Remedy, notwithstanding that the earlier occurrences of breach may have been remedied pursuant to the Notice of Remedy or otherwise,

in each case, sub-clause (a) and (b) above, that results in a Material Adverse Effect; provided, however, the Concessionaire shall not be deemed to be in Material Breach of the O&M Requirements in the afore-stated circumstances in the event such breach is caused by the Permitted Events;]

Person means any individual, firm, company, corporation, society, partnership (whether or not having a separate legal personality), joint venture, trust, unincorporated organization, government state, association or Government Authority or any other legal entity and shall include successors and assigns;

Political Event shall have the meaning ascribed thereto in Section 21.1.1(a);

Political Event Termination Amount shall have the meaning ascribed thereto in Schedule T (Termination Payments);

Pre-Estimated Project Cost means the estimated cost of the Project, as specified in the Base Case Financial Model;

Pre-Commencement Activities shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Preliminary Works means such works as are mutually agreed between the Parties to be performed by the Concessionaire prior to the Commencement Date;

Preservation Costs shall have the meaning ascribed thereto in Section 18.3.4;

Project means each of the following activities, as performed (in each case) in accordance with this Agreement:

- the ownership and possession of the Concession Assets;

- the development,  procurement, permitting, testing and commissioning of, in each case, the Concession Assets;

- the procurement and contracting for goods, equipment and services for the Concession Assets;

- the insuring and Operation and Maintenance of the Concession Assets;

- payments by the Parties of amounts due and payable under this Agreement;

- the recruitment, employment and training of staff for the Concession Assets;

- the transfer of the Concession Assets to the Agency on the Transfer Date; and

- all activities incidental or related to any of the above;

Project Agreements means:

- this Agreement;

- the O&M Contract;

- the Development Contract; and

- any other material contract entered into or to be entered into by the Concessionaire at any time after the Effective Date in connection with the Project and designated as a “Project Agreement” with the consent of the Agency;

Project Development Completion shall have the meaning ascribed thereto in Section 14.6.1;

Project Development Completion Certificate shall have the meaning ascribed thereto in Section 14.5.4.1;

Project Development Completion Date shall have the meaning ascribed thereto in Section 14.6.1;

Project Development Completion Schedule means the schedule attached herewith as Schedule E (Project Development Completion Schedule) setting out:

- the Scheduled Project Development Completion Date;

- the Scheduled Substantial Completion Date; and

- the Project Development Milestones;

Project Development Milestones means the progressive milestones relating to the performance of Development Works and other obligations to be performed by the Concessionaire until the Project Development Completion Date and the dates for achievement of each such milestone, as set out in:

- this Agreement; and

- the Development Programme;

Project Development Milestone Date means the date permitted herein for achievement of each Project Development Milestone, as set out and contemplated (in respect of each Project Development Milestone) in:

(a)	the Applicable Standards;

(b)	the Development Programme;

Project Facilities means the facilities to be constructed, built, installed, erected and/or provided by the Concessionaire on the Project Site, as detailed in Schedule D (Project Facilities);

Project Jurisdiction means where the Project is located and whose laws apply to the local aspects of the Project as defined in Schedule B (Specific Definitions);

Project Manager / Project Director shall have the meaning ascribed thereto in Section 8.13.1;

Project Management / Implementation Unit means the project management / implementation unit established by the  Agency in accordance with the Applicable Laws for the purpose of overseeing the day to day implementation of the Project in accordance with the terms of this Agreement and Applicable Laws, particularly during the Development Period, and shall be headed by the Project Manager;

Project Milestone means:

(a)	in respect of Development Works, the Project Development  Milestones; and

(b)	in respect of the Operations and Maintenance, the Project O&M Milestones;

Project Milestone Date means:

(a)	in respect of a Project Development Milestone, the respective Project Development Milestone Date for such Project Development Milestone;

(b)	in respect of a Project O&M Milestone, the respective Project O&M Milestone Date for such Project O&M Milestone;

Project O&M Milestones means the progressive milestones relating to the performance and completion of Operation and Maintenance that are to be achieved by the Concessionaire pursuant to the Applicable Standards during an Operational Year of the Operation Period, as set out in:

(a)	the Applicable Standards; and

(b)	the O&M Programme for such Operational Year;

Project O&M Milestone Date means the date permitted herein for achievement of each Project O&M Milestone, as set out and contemplated (in respect of each Project O&M Milestone) in:

(a)	the Applicable Standards; and

(b)	the O&M Programme

Project Requirements shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Project Site means the site on which the Project is to be implemented comprising of the immovable property on which the Project Facilities (including the Concession Assets) are to be located in terms of this Agreement and as demarcated in the map attached hereto in Schedule F (Project Site);

Project Site Conditions shall have the meaning ascribed to it in Section 4.4.1;

Project Site Land Instrument shall have the meaning ascribed thereto in Schedule DD;

Project Site Land Instrument Right shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Project Site Land Instrument Right Expiry Date shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Project Works means all obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire pursuant to the Applicable Standards and shall include:

- the Development Works and all obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire until the Project Development Completion Date;

- the Operations and Maintenance and all obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire during the Operations Period;

PKR or Pakistani Rupees means the lawful currency of the Islamic Republic of Pakistan;

Project Modality shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Proposed Development Programme shall have the meaning ascribed thereto in Section 13.2.1;

Proposed Completion Tests Date shall have the meaning ascribed thereto in Section 14.1.1;

Proposed O&M Programme shall have the meaning ascribed to it in Section 19.6.1;

Protected Assets shall have the meaning ascribed thereto in Section 8.10.1(b);

Relevant Environmental Protection Agency shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Relief Costs shall have the meaning ascribed to it in Schedule J (Specific Matters Relating To Relief Events);

Relief Cost Threshold shall have the meaning ascribed thereto in Schedule B (Specific Definitions)

Relief Event(s) shall have the meaning ascribed thereto in Section 15.1.1;

Relief Order means a written order jointly issued by the Independent Auditor and the Independent Engineer to the Parties pursuant to Article 15 (Relief Extensions & Relief Compensations) authorizing an extension of Time for Completion and/or payment of Relief Costs in accordance with Article 15 (Relief Extensions & Relief Compensations);

Relief Order Proposal shall have the meaning ascribed thereto in Section 15.3.1;

Relief Order Request shall have the meaning ascribed thereto in Section 15.1.1;

Remedy Events shall have the meaning ascribed thereto in Section 18.2.1;

Remedy Time Period shall have the meaning ascribed thereto in Section 18.2.1(c);

Repetition Dates shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Revenue shall have the meaning ascribed thereto in Schedule B (Specific Definitions);;

RFP shall have the meaning ascribed to in Recital A above;

RFP Publication Date shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Safety Requirements means the arrangements and procedures for conducting safety related measures in respect of the Concession Assets, as set out in the O&M Manual;

Scheduled Commencement Date shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Scheduled Project Development Completion Date shall have the meaning ascribed thereto in Section 14.4.2A;

Scheduled Substantial Completion Date shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Scope of the Project means the scope of the Project, as set out in Schedule A (Scope of the Project);

Site Development Works means all obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire at the Project Site during the Development Period pursuant to the Applicable Standards including, inter alia, the obligations, works, services and duties undertaken and/or performed and/or to be undertaken and/or performed by the Concessionaire in respect of: (a) the procurement, commissioning and completion of the Concession Assets (including all activities and obligations incidental thereto); (b) alteration, up-gradation, repair, restoration, maintenance, extension, demolition or dismantling of buildings or structures, forming or to form, part of the Project Site, whether permanent or not, on which the Concession Assets shall be situated; and (c) performing all obligations and activities for performance and completion of each Project Development Milestone; provided, however, “Site Development Works” does not include any of the following work:

(a)	the drilling for, or extraction of, oil or natural gas;

(b)	the extraction (whether by underground or surface working) of minerals, including tunneling or boring, or constructing underground works, for that purpose;

(c)	clearance of the Project Site, to the extent such clearance is to be expressly performed by the Agency in accordance with the terms of this Agreement;

Specific Agency Agreements shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Specific Concessionaire Conditions Precedent shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Specific Persons shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Specific Relief Costs shall have the meaning ascribed to it in Schedule J (Specific Matters Relating To Relief Events);

Specific Requirements shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Specific Concessionaire Undertakings shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Specific Term Sheet Parameters shall have the meaning ascribed thereto in Section 27.3.1;

Specific Requirements means:

- in respect of  Development Works, the  Development  Requirements; and

- in respect of Operations and Maintenance, the O&M Requirements;

Sponsor(s) means[•];

Sponsor Base Equity Amount shall have the meaning ascribed thereto in Schedule B (Specific Definitions)

Sponsor Shares shall have the meaning ascribed thereto in Schedule Y (Equity Matters);

State Approved Accounting Firms means:

- A. F. Ferguson & Co. (a member firm of PricewaterhouseCoopers network);

- EY Ford Rhodes;

- KPMG Taseer Hadi & Co.;

- M. Yousuf Adil Saleem & Co. (a member firm of Deloitte Touche Tohmatsu);

and / or any other successor-chartered accountancy firm categorized as one of the State Approved Accounting Firms;

Substantial Completion shall have the meaning ascribed thereto in Section 14.3.3;

Substantial Completion Certificate means the certificate issued by the Independent Engineer at the request of the Concessionaire in accordance with Section 14.3 (Substantial Completion Certificate);

Substantial Completion Criteria shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Substantial Completion Date shall have the meaning ascribed thereto in Section 14.3.2;

Suspension shall have the meaning ascribed thereto in Section 18.3.1;

Termination means the termination of this Agreement and the Concession hereunder upon the issuance of a Termination Notice in accordance with the terms hereof and to the extent stated herein;

Termination Date means the date of issuance of the Termination Notice;

Termination Dividend Amount shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Termination Equity shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Termination Equity IRR shall have the meaning ascribed thereto in Schedule B (Specific Definitions);

Termination Notice means a notice to be issued in writing, by a Party notifying the other Party of the Termination in accordance with the applicable provisions of this Agreement including, where applicable, following the expiry of the relevant Cure Period or such other cure period specified in the Agreement;

Termination Payment means:

- in respect of Termination due to a Concessionaire Event of Default, the Concessionaire Default Termination Amount;

- in respect of Termination due to a Corrupt Act, the Corrupt Act Termination Amount;

- in respect of Termination due to a Agency Event of Default, the Agency Default Termination Amount;

- in respect of Termination due to a Political Event, the Political Event Termination Amount;

- in respect of Termination due to a Non-Political Event, the Non-Political Event Termination Amount;

- in respect of Termination due to a Change in Law, the Change in Law Termination Amount;

Termination Payment Date means the date on which the Agency has made payment of the relevant Termination Payment to the Concessionaire such date not exceeding ninety (90) days following the Termination Date;

Time for Completion means (as applicable):

(a)	in respect of Development Works, the  Development Time for Completion; and

(b)	in respect of Operations & Maintenance, the O&M Time for Completion;

Total Project Cost means the actual capital cost of the Project upon completion of the Project, as certified by the Independent Auditor; provided, that the same shall not include (unless otherwise agreed with the Agency) the Additional Cost;

Transfer Bond shall have the meaning ascribed thereto in Section 24.7.1;

Transfer Date means:

(a)	in case of early Termination of this Agreement prior to the Final Expiry Date, the Termination Payment Date subject to: (i) the  Agency making payment of the relevant Termination Payment to the Concessionaire; and (ii) the Concessionaire completing the Divestment Requirements on or prior to such date;

(b)	in case of achievement of Final Expiry Date pursuant to this Agreement, the Final Expiry Date;

Trigger Date means and includes, the Final Expiry Date and/or the Termination Date, as the case may be;

Uninsurable means that: (a) the insurance or Takaful cover is no longer available in the international or local insurance markets; or (b) the premium/contribution payable for such insurance is such that the risk is no longer generally insured against by prudent concessionaires of projects similar to the Project;

Unpaid Termination Equity Amount shall have the meaning ascribed thereto in Section 23.5.2(b);

Utilities Affected Assets shall have the meaning ascribed thereto in Section 4.11.2;

Utility Proceeds shall have the meaning ascribed to it Section 4.11.3;

Utility Relocation Delay shall have the meaning ascribed thereto in Section 4.10.3;

Vacant Possession means delivery to the Concessionaire by the Agency of possession of the Project Site in accordance with this Agreement, in accordance with Applicable Laws, and in accordance with the Project Site Land Instrument  free from all Encumbrances, encroachments, existing trees, existing structures and utilities etc.; and the grant of all Easementary Rights and all other rights appurtenant thereto, such that the Concessionaire enjoys complete uninterrupted and quiet possession and control of the Project Site from the grant of the license/lease  and throughout the Concession Period;

Vesting Certificate shall have the meaning ascribed thereto in Section 24.4.1; and

## Construction

    - In this Agreement, unless the context otherwise requires:

- references to any legislation or any provision thereof shall include amendment or re-enactment or consolidation of such legislation or any provision thereof so far as such amendment or re-enactment or consolidation applies or is capable of applying to any transaction entered into hereunder;

- references to laws of Pakistan or Pakistan law or regulation having the force of law shall include the laws, acts, ordinances, rules, regulations, bye laws or notifications which have the force of law in the territory of Pakistan and as from time to time may be amended, modified, supplemented, extended or re-enacted;

- the table of contents, headings or sub-headings in this Agreement are for convenience of reference only and shall not be used in, and shall not affect, the construction or interpretation of this Agreement;

- the words “include” and “including” are to be construed without limitation and shall be deemed to be followed by “without limitation” or “but not limited to” whether or not they are followed by such phrases;

- references to “construction” or “building” include, unless the context otherwise requires, investigation, design, developing, engineering, procurement, delivery, transportation, installation, processing, fabrication, testing, commissioning and other activities incidental to the construction, and “construct” or “build” shall be construed accordingly;

- references to “development” include, unless the context otherwise requires, construction, renovation, refurbishing, augmentation, up-gradation and other activities incidental thereto, and “develop” shall be construed accordingly;

- any reference to any period of time means a reference to that according to Pakistan Standard Time;

- any reference to day means a reference to a calendar day as per the Gregorian Calendar;

- references to a “business day” shall be construed as a reference to a day (other than a Sunday) on which banks in Pakistan are generally open for business;

- any reference to month means a reference to a calendar month as per the Gregorian calendar;

- references to any date, period or Project Milestone means and include such date, period or Project Milestone as may be extended pursuant to Relief Order;

- any reference to any period commencing “from” a specified day or date and “till” or “until” a specified day or date shall include both such days or dates; provided, that if the last day of any period computed under this Agreement is not a business day, then the period shall run until the end of the next business day;

- the words importing singular shall include plural and vice versa;

- references to any gender shall include the other and the neutral gender;

- “indebtedness” shall be construed so as to include any obligation (whether incurred as principal or surety) for the payment or repayment of money, whether present or future, actual or contingent;

- references to the “winding-up”, “dissolution”, “insolvency”, or “reorganization” of a company or corporation shall be construed so as to include any equivalent or analogous proceedings under the law of the jurisdiction in which such company or corporation is incorporated or any jurisdiction in which such company or corporation carries on business including the seeking of liquidation, winding-up, reorganization, dissolution, arrangement, protection or relief of debtors;

- save and except as otherwise provided in this Agreement, any reference, at any time, to any agreement, deed, instrument, License or document of any description shall be construed as reference to that agreement, deed, instrument, License or other document as amended, varied, supplemented, modified or suspended at the time of such reference; provided, that this sub-section shall not operate so as to increase liabilities or obligations of the Agency hereunder or pursuant hereto in any manner whatsoever;

- any agreement, consent, approval, authorization, notice, communication, information or report required under or pursuant to this Agreement from or by any Party, the Independent Engineer or the Independent Auditor shall be valid and effective only if it is in writing under the hand of a duly authorized representative of such Party, the Independent Engineer or the Independent Auditor, as the case may be, in this behalf and not otherwise;

- the Schedules and Recitals to this Agreement form an integral part of this Agreement and shall be in full force and effect as though they were expressly set out in the body of this Agreement;

- references to Recitals, Articles, Sections, or Schedules in this Agreement shall, except where the context otherwise requires, mean references to Recitals, Articles, Sections, and Schedules of or to this Agreement, and references to an "Article" or "Section" shall, subject to any contrary indication, be construed as a reference to a provision within the Main Body of this Agreement, and references to a "Clause" or "Paragraph" shall be construed as a reference to a provision within the Schedules to this Agreement; and

- time shall be of the essence in the performance of the Parties’ respective obligations. If any time period specified herein is extended, such extended time shall also be of the essence.

    - The rule of construction, if any, that a contract should be interpreted against the parties responsible for the drafting and preparation thereof, shall not apply.

    - Any word or expression used in this Agreement shall, unless otherwise defined or construed in this Agreement, bear its ordinary English meaning and, for these purposes, the General Clauses Act 1897 shall not apply.

## Costs for Documents

    - Unless expressly provided otherwise in this Agreement, any documentation required to be provided or furnished by the Concessionaire to the Agency, the Independent Engineer and/or the Independent Auditor or any other relevant person so appointed or nominated by the Agency, the Financiers or any other person legally so required shall be provided free of cost and in three (3) copies, and if the Agency, the Independent Engineer and/or the Independent Auditor is required to return any such documentation with their comments and/or approval, they shall be entitled to retain two (2) copies thereof.

## Measurements and Arithmetic Conventions

    - All measurements and calculations in respect of financial matters shall be in the metric system and calculations done to two (2) decimal places, with the third digit of five (5) or above being rounded up and below five (5) being rounded down, however all calculations in respect of technical matters shall be in SI/foot pound and second system in accordance with the provision of this Agreement.

## Priority of Agreements, Articles, Sections and Schedules

    - This Agreement, and all other agreements and documents forming part of this Agreement are to be taken as mutually explanatory and, unless otherwise expressly provided elsewhere in this Agreement, the priority of this Agreement and the other Agency Agreement and other documents and agreements forming part thereof or referred to therein shall, in the event of any conflict between them, be in the following order (unless otherwise agreed between the Parties):

- this Agreement;

- the Agency Agreements (other than this Agreement).

    - Subject to the provisions of Section 1.5.1, in the event of any ambiguity and/or discrepancies with regard to this Agreement, the following shall apply:

- between two or more Articles and/or Section of this Agreement, the provisions of a specific Article relevant to the issue under consideration shall prevail over those in other Article and/or Section;

- between the Article and/or Section of this Agreement and the Schedules, the Article and/or Section shall prevail unless the issue in question/matter is specifically provided for in the Schedule and only referred to in the Article and / or Section, as the case may be;

- between any two Schedules, the Schedule relevant to the issue shall prevail;

- between the written description on the  drawings and the  Development Requirements, the latter shall prevail;

- between the written description on the O&M Documents and the O&M Requirements, the latter shall prevail;

- between the dimension scaled from the drawings and its specific written dimension, the latter shall prevail;

- between the dimension scaled from the O&M Documents and its specific written dimension, the latter shall prevail; and

- between any value written in numerals and that in words, the latter shall prevail.

# Concession

## Grant of Concession

    - In consideration of the Concessionaire’s obligations contained in this Agreement and in reliance on the Concessionaire’s representations, warranties and covenants contained herein, the  Agency, subject to the terms of this Agreement, hereby authorizes the Concessionaire, for the duration of the Concession Period, to implement the Project in accordance with the Project Modality, and to exercise and enjoy the rights, powers, benefits, privileges, authorizations and entitlements as set forth in this Agreement.

    - The Concessionaire agrees and undertakes to implement the Project in accordance with the terms of this Agreement and the Agency Agreements.

## Concession Period

    - The Concession is hereby granted and shall be effective for the Concession Period.

## Extension of Concession Period

    - The Concessionaire may request an extension of the Concession Period at any time on or prior to the Extension Request Deadline; provided that at the time of the request the Concessionaire is materially in compliance with its obligations under this Agreement and is not otherwise facing a default thereunder. The Agency shall have the right to accept or reject this request for extension at its sole and absolute discretion. To the extent the Agency accepts the extension of the Concession Period, such extension shall not exceed the Maximum Extension Period and shall be strictly predicated upon the financial terms, risk allocation, and structural framework established within this Agreement. Upon such acceptance, the Parties shall enter into such instruments, agreements and arrangements (including any amendments to the Agency Agreements in accordance with Section 29.3 (Amendments)).

# Conditions

## Conditions Precedent

    - Save and except as expressly provided herein, the respective obligations of the Parties shall be subject to the satisfaction (waiver and/or deferral in accordance with Section 3.2 (Waiver and/or Deferral of Conditions and Extension of Scheduled Commencement Date)) in full of the conditions precedent specified in Section 3.1.2 and Section 3.1.3 (the Conditions Precedent) on or prior to the Scheduled Commencement Date.

    - The Concessionaire shall satisfy the following Conditions Precedent to the satisfaction of the Agency, the Independent Engineer and the Independent Auditor prior to the Scheduled Commencement Date (the Concessionaire Conditions Precedent):

- the Concessionaire has provided the Development Performance Security to the Agency that remains effective and valid until the Development Performance Security Expiry Date;

- the Concessionaire has provided to the Agency, the Independent Auditor and the Independent Engineer certified true copies of the executed Development Contract;

- the Concessionaire has provided copies of its Corporate Documents to the Agency (with copies delivered to the Independent Engineer and the Independent Auditor), duly certified as true copies by the company secretary or director of the Concessionaire;

- the Concessionaire has provided to the Agency copies (with copies delivered to the Independent Engineer and Independent Auditor) of its Board Resolution that duly authorizes:

- the Concessionaire to enter into this Agreement and to undertake the obligations and liabilities, as set out in this Agreement, and the transactions as contemplated by this Agreement;

- a specified Person or Persons to:

(aa)	execute this Agreement on behalf of the Concessionaire; and

(bb)	undertake all other acts specifically relating to this Agreement, as contemplated by this Agreement;

- the Agency has received the following legal opinions:

- a legal opinion from the legal counsel of the Concessionaire confirming that the Concessionaire has been duly organized and is validly existing under the Applicable Laws and has the requisite power and authority to enter into the Agency Agreements to which the Concessionaire is a party and to undertake the transactions as contemplated by the Agency Agreements and to assume the obligations as contained herein and the enforceability of the same against the Concessionaire;

- a legal opinion from the legal counsel of the Sponsor confirming that such Sponsor is validly existing under the Applicable Laws and that such Sponsor has the requisite authority and power to enter into the Agency Agreement(s) and the Project Agreement(s) to which such Sponsor is a party and to assume the obligations as contained therein and the enforceability of the same against the Sponsor;

- the Concessionaire has entered into the Project Site Land Instrument with the Agency for the Project Site Land Instrument Right in respect of the Project Site to the Concessionaire in accordance with Article 4 (Project Site);

- the Concessionaire has provided to the Agency documents evidencing that:

- the Concessionaire entered into a valid and effective Independent Engineer Contract for the appointment of the Independent Engineer with the counterparties to such contract, within [one (1) month] of the Effective Date; and

- the Concessionaire entered into a valid and effective Independent Auditor Contract for the appointment of the Independent Auditor with the counterparties to such contract, within [one (1) month] of the Effective Date;

- the Concessionaire has entered into the Escrow Agreement and has established the Escrow Account;

- the representations and warranties of the Concessionaire contained in Article 7 (Concessionaire’s Representations, Warranties and Certain Obligations & Undertakings) of this Agreement were true and correct in all material respects on the Effective Date and remain true and correct in all material respects as at the date of the issuance of the certificate referenced herein, and the Agency shall have received a certificate to that effect in form and substance reasonably acceptable to the Agency, dated as of the date of its submission to the Agency and signed by the company secretary of the Concessionaire;

- the Specific Concessionaire Conditions Precedent; and

- the Concessionaire has submitted copies of documents evidencing satisfaction of each of the Concessionaire Conditions Precedent to the Independent Engineer and the Independent Auditor.

    - The Agency shall satisfy the following Conditions Precedent to the satisfaction of the Concessionaire, the Independent Auditor and the Independent Engineer prior to the Scheduled Commencement Date (the Agency Conditions Precedent):

- the Agency has granted the Project Site Land Instrument Right with respect to the Project Site to the Concessionaire in accordance with Article 4 (Project Site) and the Project Site Land Instrument;

- the Agency has handed over Vacant Possession of the Project Site to the Concessionaire in accordance with Article 4 (Project Site) and the Project Site Land Instrument;

- the Agency has entered into the Independent Engineer Contract for the appointment of the Independent Engineer with the other counterparties to such contract, within [one (1) month] of the Effective Date;

- the Agency has entered into the Independent Auditor Contract for the appointment of the Independent Auditor with the other counterparties to such contract, within [one (1) month] of the Effective Date;

- the Agency has entered into the Escrow Agreement;

- the Specific Agency Conditions Precedent; and

- the Agency has submitted copies of documents evidencing satisfaction of each of the Agency Conditions Precedent to the Independent Engineer and the Independent Auditor.

    - On a monthly basis from the Effective Date, the Concessionaire shall advise the Independent Engineer and the Independent Auditor (with a copy to the Agency) as to the status of the satisfaction of the Concessionaire Conditions Precedent, provided that:

- no review or approval by the Independent Engineer and/or the Independent Auditor of any Concessionaire Conditions Precedent shall relieve the Concessionaire from any liability that it would otherwise have had in respect of such Concessionaire Conditions Precedent or failure to comply with the Applicable Laws or this Agreement with respect thereto; and

- neither the Agency, the Independent Engineer, the Independent Auditor, nor any of their respective representatives or advisors shall be liable to the Concessionaire or any other Person by reason of their review or approval of any Concessionaire Conditions Precedent.

## Waiver and/or Deferral of Conditions and Extension of Scheduled Commencement Date

    - The:

- Agency may (at its discretion) waive and/or defer any of the Concessionaire Conditions Precedent set forth in Section 3.1.2. For the avoidance of doubt, the Agency may, at its sole discretion, grant any waiver and/or deferral hereunder with such conditions as it may deem fit;

- Concessionaire may (at its discretion) waive and/or defer any of the Agency Conditions Precedent set forth in Section 3.1.3 . For the avoidance of doubt, the Concessionaire may, at its sole discretion, grant any waiver and/or deferral hereunder with such conditions as it may deem fit.

    - Notwithstanding anything contained herein, the Scheduled Commencement Date may be extended from time to time with the mutual consent of the Parties.

    - Any deferral and/or waiver of a Conditions Precedent in terms of this Section 3.2 (Waiver and/or Deferral of Conditions and Extension of Scheduled Commencement Date) shall be notified in writing to the Independent Engineer and the Independent Auditor by the Party granting such deferral and/or waiver of such condition in accordance with this Agreement.

## Commencement Certificate & Commencement Date

    - Each Party shall promptly inform the other Party in writing (together with copies delivered to the Independent Engineer and the Independent Auditor) when the Conditions Precedent for which it is responsible have been satisfied.

    - The Parties agree that:

- within thirty (30) days of the Agency’s receipt from the Concessionaire, through the Independent Engineer and the Independent Auditor, evidence of satisfaction of a Concessionaire Conditions Precedent, the Agency shall notify the Independent Engineer and the Independent Auditor in writing (with a copy to the Concessionaire) whether it has any objections on the satisfaction of such Concessionaire Conditions Precedent. In the event the Agencydoes not raise any objection in writing on the satisfaction of a Concessionaire Conditions Precedent within the thirty (30) day period set out herein, such Concessionaire Conditions Precedent shall be deemed to be not objected to by the Agency. In the event the Agency raises any objections on the satisfaction of a Concessionaire Conditions Precedent and notifies the same to the Independent Engineer and the Independent Auditor (with a copy to the Concessionaire) within the thirty (30) day period set out herein, the Concessionaire shall address such objections and re-submit to the Independent Engineer and the Independent Auditor (with a copy to the Agency) evidence of satisfaction of such Concessionaire Conditions Precedent and the process in this Section 3.3.2(a) shall be repeated until such time that the Agency has not objected to or is deemed to have not objected to the satisfaction of such Concessionaire Conditions Precedent. The provisions of this Section 3.3.2(a) shall apply to each Concessionaire Conditions Precedent for which evidence of satisfaction is submitted by the Concessionaire to the Independent Engineer and the Independent Auditor (with a copy to the Agency) from time to time;

- within thirty (30) days of the Concessionaire’s receipt from the Agency, through the Independent Engineer and the Independent Auditor, evidence of satisfaction of an Agency Conditions Precedent, the Concessionaire shall notify the Independent Engineer and the Independent Auditor in writing (with a copy to the Agency) whether it has any objections on the satisfaction of such Agency Conditions Precedent. In the event the Concessionaire does not raise any objection in writing on the satisfaction of an Agency Conditions Precedent within the thirty (30) day period set out herein, such Agency Conditions Precedent shall be deemed to be not objected to by the Concessionaire. In the event the Concessionaire raises any objections on the satisfaction of a Agency Conditions Precedent and notifies the same to the Independent Engineer and the Independent Auditor (with a copy to the Agency) within the thirty (30) day period set out herein, the Agency shall address such objections and re-submit to the Independent Engineer and the Independent Auditor (with a copy to the Concessionaire) evidence of satisfaction of such Agency Conditions Precedent and the process in this Section 3.3.2(b) shall be repeated until such time that the Concessionaire has not objected to or is deemed to have not objected to the satisfaction of such Agency Conditions Precedent. The provisions of this Section 3.3.2(b) shall apply to each Agency Conditions Precedent for which evidence of satisfaction is submitted by the Agency to the Independent Engin eer and the Independent Auditor (with a copy to the Concessionaire) from time to time.

    - The Parties hereby jointly undertake to procure that the Independent Engineer and the Independent Auditor jointly issue the Commencement Certificate within three (3) days of the date on which the Independent Engineer and the Independent Auditor are satisfied that each of the:

- Concessionaire Conditions Precedent stand satisfied (and/or waived or deferred by the Agency in accordance with Section 3.2.1(a));

- Concessionaire Conditions Precedent are not objected to or deemed not to have been objected to by the Agency (acting through the Agency Representative) in accordance with Section 3.3.2(a) and if any Concessionaire Conditions Precedent is objected to by the Agency in accordance with Section 3.3.2(a), the Concessionaire has addressed such objections and re-submitted evidence of satisfaction of such Concessionaire Conditions Precedent to the Independent Engineer and the Independent Auditor (with a copy to the Agency) in accordance with Section 3.3.2(a);

- Agency Conditions Precedent stand satisfied (and/or waived or deferred by the Concessionaire in accordance with Section 3.2.1(b)); and

- Agency Conditions Precedent are not objected to or deemed not to have been objected to by the Concessionaire in accordance with Section 3.3.2(b) and if any Agency Conditions Precedent is objected to by the Concessionaire in accordance with Section 3.3.2(b), the Agency has addressed such objections and re-submitted evidence of satisfaction of such Agency Conditions Precedent to the Independent Engineer and the Independent Auditor (with a copy to the Concessionaire) in accordance with Section 3.3.2(b).

    - The Independent Engineer and the Independent Auditor, jointly, shall set out in the Commencement Certificate the date on which the Commencement Date is achieved.

## Termination Prior to Commencement Date

    - In the event:

- the Conditions Precedent are not satisfied, waived and/or deferred on or prior to the date falling ninety (90) days following the Scheduled Commencement Date, (including the extended time, if any) due to reasons attributable to the Concessionaire; and/or

- of occurrence of a Concessionaire Event of Default prior to the Commencement Date;

then the Agency shall have the right (to be exercised in its sole and absolute discretion) to Terminate this Agreement by issuance of a written Termination Notice to the Concessionaire. In such case, the Agency shall be entitled to encash the  Development Performance Security to its full value. Furthermore, the Agency shall make payment to the Concessionaire of the Concessionaire CP Failure Termination Amount.  Except for the encashment of the  Development Performance Security and the payment of the Approved Pre-Commencement Costs in terms of this Section 3.4.1, each Party hereto shall have no claims against the other for costs, damages, compensation or otherwise for such Termination of this Agreement.

    - In the event:

- the Conditions Precedent are not satisfied, waived and/or deferred on or prior to the date falling ninety (90) days following the Scheduled Commencement Date, (including the extended time, if any) due to reasons attributable to the Agency and/or a Force Majeure Event; and/or

- of occurrence of an Agency Event of Default prior to the Commencement Date,

the Concessionaire shall have the right (to be exercised in its sole and absolute discretion) to Terminate this Agreement by issuance of a written Termination Notice to the Agency. In such case, the Agency shall (within fifteen (15) days of its receipt of the Termination Notice) return the Development Performance Security, as applicable, to the Concessionaire without any encashment, demands or claims. Furthermore, the Agency shall make payment to the Concessionaire of the Agency CP Failure Termination Amount. Except for the payment of the Approved Pre-Commencement Costs, each Party hereto shall have no claims against the other for costs, damages, compensation or otherwise for such Termination of this Agreement.

    - It is clarified that the provisions of this Section 3.4 (Termination Prior to Commencement Date) shall only apply to any Termination of this Agreement occurring prior to the Commencement Date.

    - This Agreement and any other Agency Agreements (if executed) to which the Concessionaire and/or the Sponsor are a party, shall have no further effect. The Parties shall have no further rights and shall be released from all their obligations under this Agreement, except in respect of any rights or obligations arising before the Termination occurred and except as set out in Section 29.4 (Survival), Section 3.4.1 and Section 3.4.2.

## Delay in Achieving the Commencement Date

    - If the achievement of the Commencement Date has been delayed due to:

- any delay or failure on the part of the Agency in the performance of its obligations under this Agreement, which is not otherwise attributable to the Sponsors, the Concessionaire or any of its Contractors; or

- the occurrence of a Force Majeure Event, the Independent Engineer and Independent Auditor shall confer with the Parties with a view to equitably adjusting the Scheduled Commencement Date and the Project Development Completion Schedule, taking into account:

- the effect which the Concessionaire demonstrates is solely attributable to the Agency’s delay or failure and which would not have occurred but for such delay or failure;

- the effect which the Concessionaire demonstrates is solely attributable to the occurrence of a Force Majeure Event and which would not have occurred but for such delay or failure; and

- the ability of the Parties to reschedule their obligations to avoid or minimise the overall resulting delays and ensure that any such adjustment to the Scheduled Commencement Date and the Project Development Completion Schedule is limited to that necessary and is a consequence of the delay or failure.

    - The remedies set out in this Section 3.5 shall be the Concessionaire’s sole and exclusive remedies with respect to any delay in achieving the Commencement Date by the Scheduled Commencement Date due to any matter referred to in Section 3.5.1, provided that if the Concessionaire fails to achieve the Commencement Date by the Scheduled Commencement Date (as adjusted under Section 3.5.1), then, unless the Scheduled Commencement Date is extended in accordance with Section 3.5.3, either Party may exercise its right to terminate this Agreement pursuant to Section 3.4.

    - If, for reasons other than those specified under Section 3.5.1, the Concessionaire is unable to achieve the Commencement Date by the Scheduled Commencement Date then, the Scheduled Commencement Date shall be extended for a period not exceeding one hundred and eighty (180) days. No later than twenty (20) days prior to the Scheduled Commencement Date, the Concessionaire shall provide written notice to the Independent Engineer and Independent Auditor of its expected inability to achieve the Commencement Date by the Scheduled Commencement Date (the Commencement Date Delay Notice).

# Project Site

## Land Instrument Right

    - Pursuant to the Project Site Land Instrument, the Agency agrees to grant the Project Site Land Instrument Right in respect of the Project Site for the Concession Period to the Concessionaire for the purposes set out herein (the Project Site Land Instrument Right) and in accordance with the Project Site Land Instrument. The Project Site Land Instrument shall be duly executed by the Parties and, to the extent required by Applicable Laws, registered by the Concessionaire with the relevant Government Authority and all costs, fees, expenses, duties, charges and taxes (including charges relating to the registration of the Project Site Land Instrument) relating to the same shall be borne by the Concessionaire.

    - The Concessionaire shall be responsible for payment of all charges in accordance with the Project Site Land Instrument that relate to the Project Site Land Instrument Right of the Project Site to the Concessionaire by the Agency.

    - The Project Site Land Instrument Right shall commence on the physical handing over of the Vacant Possession of the Project Site to the Concessionaire by the Agency and upon commencement, shall expire on the Project Site Land Instrument Right Expiry Date. Any extension of the Concession Period shall also extend the Project Site Land Instrument Right and the Concessionaire and the Agency shall enter into such addenda, extensions or modifications of the Project Site Land Instrument as are necessary to give effect to such extension.

    - The Agency shall grant such permission or exemptions as may be required under the Applicable Laws relating to and regulating land, as applicable in the Project Jurisdiction, so as to ensure that the Concessionaire can enjoy Vacant Possession and hold the area of land comprising the Project Site, except where failure to enjoy Vacant Possession has resulted from a breach by the Concessionaire of the Applicable Standards.

## Title of Project Site & Delivery of Vacant Possession

    - The Agency represents and warrants to the Concessionaire that (a) it has the full legal right, power, and authority to grant the Project Site Land Instrument Right in respect of the Project Site to the Concessionaire; (b) the Project Site is, and upon the handover of Vacant Possession shall be, free and clear of all Encumbrances, and is not subject to any third-party claims or competing interests; and (c) it has the requisite authority to authorize the Concessionaire to undertake the Development Works on the Project Site in accordance with the terms of this Agreement.

    - Subject to Section 15.1 (Relief Events), the Agency shall at its own cost and expense deliver, to the Concessionaire, Vacant Possession of the Project Site (including all Easementary Rights) in accordance with the Project Site Land Instrument. Upon the delivery of Vacant Possession by the Agency, the Concessionaire’s right to enter and use the Project Site shall be irrevocable.

    - The Parties agree and acknowledge that this Section 4.2.3 shall come into effect as of the Effective Date. In the event the Concessionaire is adversely affected and/or delayed in the performance of its obligations and/or there is any adverse financial impact on the Concessionaire, in each case, resulting from any delay and/or failure of the Agency to deliver Vacant Possession of the Project Site to the Concessionaire in accordance with the Project Site Land Instrument, such delay and/or failure of the Agency shall entitle the Concessionaire to issuance of a Relief Order Request and in such case, the provisions of Article 15 (Relief Extensions & Relief Compensations) shall apply.

## Use of Project Site

    - The Concessionaire hereby unconditionally and irrevocably confirms, acknowledges and agrees that the Agency shall enter into the  Project Site Land Instrument with the Concessionaire that shall grant the Project Site Land Instrument Right to the Concessionaire for the sole purpose of implementation of the Project and for enjoying the rights and benefits of the Concession granted hereunder and that the Concessionaire shall use the Project Site only for the purposes of implementing the Project thereupon and for purposes incidental or necessary thereto subject to the terms and conditions of the Applicable Standards. The Concessionaire shall, in carrying out its obligations under this Agreement, utilize all existing roads and land areas at the Project Site.

    - The Concessionaire hereby undertakes that it shall not without prior written consent of the Agency use the Project Site for any purpose other than:

- for the purposes of the Project and purposes incidental thereto; and

- as may otherwise be approved by the Agency in writing.

## Concessionaire’s Responsibility

    - Subject to Section 4.13 (Removal of Material Adverse Impediment), the physical and the ambient conditions (including climatic, hydrological, hydro-geological, ecological, environmental, geotechnical, geological, paleontological and archaeological conditions) of the Project Site (the Project Site Conditions) shall be the sole responsibility of the Concessionaire. Accordingly, without limiting any other obligations of the Concessionaire that are included in this Agreement, the Concessionaire shall be deemed as at the Effective Date to have:

- carried out an investigation of all Project Site Conditions and of any extraneous material in or under the Project Site including its surface, sub-soil and ground water to enable the Concession Assets to be designed and constructed and for its obligations to be performed with due regard for the Project Site Conditions and the seismic activity (if any) in the region of the Project Site;

- for the purpose of such investigation in section 4.4.1(a), inspected and examined the Project Site and surroundings;

- satisfied itself as to the nature of the Project Site Conditions, the surface, sub-soil and ground water of the Project Site, the form and nature of the Project Site, the load-bearing and other relevant properties of the Project Site, the risk of damage to property affecting the Project Site, the nature of the materials (whether natural or otherwise) to be excavated and the nature of the design, its obligations and material necessary for the implementation of the Project;

- satisfied itself as to the adequacy of its right of passage over, access to and through the Project Site and any accommodation it may require for the purposes of fulfilling any of its obligations included in this Agreement, such as any additional land or buildings located outside the Project Site;

- satisfied itself as to the possibility of interference by Persons with rights-of-way across, access to or use of the Project Site with particular regard to the owners and users of any land adjacent to the Project Site; and

- satisfied itself as to the precautions, times and methods of working necessary to prevent or minimize nuisance or interference being caused to any third parties.

    - For the avoidance of doubt, the Concessionaire accepts full responsibility for all matters in Section 4.4.1 and the Concessionaire shall, subject to Section 4.15 (Removal of Material Adverse Impediment):

- not be entitled to make any claim against the Agency whether in contract, tort or otherwise on any ground relating to the matters in Section 4.4.1; and

- indemnify the Agency against all direct Losses sustained by the Agency and/or any third party in consequence of cleaning-up and otherwise dealing with any potentially hazardous materials being any natural or artificial substance, whether in solid, gaseous or liquid form capable of causing harm to any human or any other living organism supported by the environment (including air, water, land, surface land and sub-surface land) or capable of damaging the environment or public health or posing a threat to public safety including any pollutants and any hazardous, toxic, radioactive, noxious, corrosive or dangerous substances and all substances for which in each case liability or responsibility is imposed under Applicable Laws) at the Project Site.

## No Sale or Creation of Encumbrance

    - The Concessionaire shall not part with, dispose of, sell, sublease or create any Encumbrance of any nature whatsoever on the whole or any part of the Project Site and shall not place or create nor permit any Contractor or other person claiming through or under the Concessionaire to place or create any Encumbrance over all or any part of the Project Site or the Concession Assets, or on any rights of the Concessionaire therein or under this Agreement, save and except as otherwise expressly set forth in this Agreement.

## Protection of Site from Encroachments

    - Following the delivery and handing over to the Concessionaire of the Vacant Possession of the Project Site by the Agency and until the Transfer Date, the Concessionaire shall be fully responsible for and shall protect the Project Site from, in each case, any and all occupations, thefts, encroachments and Encumbrances. The Concessionaire further undertakes, covenants and confirms to indemnify  any Government Authority and the Agency from any costs, claims, expenses or charges incurred resulting from any breach of its obligations under this Section 4.6 (Protection of Site from Encroachments).

    - [Following the delivery and handing over of Vacant Possession of the Project Site to the Concessionaire and until the Transfer Date, the Agency shall be fully responsible for and shall protect all Agency-retained areas and adjacent areas from any and all occupations, thefts, encroachments, and Encumbrances to the extent that such events affect or impede the Concessionaire’s use of the Project Site.]

    - Following the delivery and handing over to the Concessionaire of the Vacant Possession of the Project Site by the Agency and until the Transfer Date, the Agency undertakes not to give possession of the Project Site to any other Person without the Concessionaire's prior written approval during the Concession Period.

## Special/Temporary Right of Way

    - The Concessionaire shall, at its own cost and risk, obtain any special or temporary right of way that is not included in the Scope of the Project and description of Project Site and the Concession Assets, and is required by the Concessionaire in connection with access to the Project Site and shall also obtain (at its cost and expense) such other facilities, the provision of which is not the responsibility of the Agency under the Agency Agreements, as may be required by the Concessionaire for the purposes of the Project and its implementation in accordance with the Applicable Standards; provided, that the Agency shall reasonably facilitate the Concessionaire in obtaining the aforesaid special or temporary right of way.

## Project Site Access

    - Following the Project Site Land Instrument Right of the Project Site and delivery of the Vacant Possession of the Project Site to the Concessionaire by the Agency, the Project Site Land Instrument Right granted to the Concessionaire shall always be subject to the right of access of the Agency, any relevant Government Authority, the Independent Auditor and the Independent Engineer and their representatives, officers, employees and agents for inspection, viewing and exercise of their rights and performance of their obligations under this Agreement; provided, that the exercise of such right of access shall not interfere with the Concessionaire’s performance of its rights and obligations under this Agreement.

## Geological and Archaeological Finds

    - It is expressly agreed between the Parties that mining, geological or archaeological rights do not form part of the Project Site Land Instrument Right to be granted to the Concessionaire in terms of the  Project Site Land Instrument and the Concessionaire hereby acknowledges and agrees that it shall not have any mining rights or interest in the underlying minerals, fossils, antiquities, structures or other remnants or things either of particular geological or archaeological interest and that all such rights, interest and property on or under the Project Site shall vest in and belong to the Agency or the relevant concerned Government Authority.

    - The Concessionaire shall procure all no-objection certificates and consents from the Culture Department of the relevant Project Jurisdiction that may be required by the Concessionaire under the Applicable Laws, in respect of any potential geological and archeological finds on the Project Site, prior to commencement of the Project Works. Furthermore, the Concessionaire shall take all reasonable precautions to prevent its employees, workmen, agents, representatives and/or any other persons appointed by the Concessionaire from having access to the Project Site, including the Contractors, from removing or damaging such interest or property (as set out in Section 4.9.1) and shall inform the Agency forthwith of the discovery thereof and comply with such instructions as the Agency and/or the concerned Government Authority may issue in relation to the protection and/or removal of such property. In the event any expenses are incurred by the Concessionaire in fulfilling its obligations as set out in this Section 4.9.2 as a result of the geological and/or archaeological finds being on the Project Site, then the same shall entitle the Concessionaire to issuance of a Relief Order Request and in such case, the provisions of Article 15 (Relief Extensions & Relief Compensations) shall apply. Further, in the event the Concessionaire is delayed in performance of its obligations under this Agreement due to the occurrence of the circumstances set out in this Section 4.9 (Geological and Archaeological Finds), the Concessionaire shall be granted extensions in the timeline in which it has to perform its obligations under this Agreement (provided that such extensions are duly certified by the Independent Engineer) and in such case, the provisions of Article 15 (Relief Extensions & Relief Compensations) shall apply. Notwithstanding anything contained herein, the Agency shall procure the issuance of the instructions required from the concerned Government Authority and referred to in this Section 4.9.2.

## Existing Utilities and Roads

    - Notwithstanding anything to the contrary contained herein, the Concessionaire shall ensure that the respective entities owning the existing roads, right of way or utilities on, under or above the Project Site are enabled by the Concessionaire to keep such utilities in continuous satisfactory use, if necessary, by providing suitable temporary or permanent diversions with the authority of the controlling body of that road, right of way or utility, and the Agency shall, upon written request from the Concessionaire (as certified by the Independent Engineer), initiate and undertake, at the Agency’s cost, legal proceedings for acquisition of any right of way necessary for such diversion. The Concessionaire shall be responsible for identifying the existing utilities and roads through the  Pre-Commencement Activities  submitted by the Concessionaire to the Independent Engineer and during the relocation of existing utilities, supervising the same in relation to the agreed alignment (for excavation, laying, backfilling, erection of utility poles, etc.) by seeking assistance from the design consultant with respect to the survey points without damaging the existing utilities and roads. In the event of any breach by the Concessionaire of its obligations under this Section 4.10.1, the Concessionaire shall be responsible for rectification of the same at its own cost, risk and expense.

    - [Notwithstanding the Concessionaire’s obligations to identify utilities through the Pre-Commencement Activities, the Agency’s obligations and warranties in respect of the Project Site shall extend to all existing utilities (including hidden or underground utilities) that were not apparent or discoverable through a review of the records provided by the Agency or through a diligent physical inspection of the Project Site. In the event the Concessionaire encounters such non-apparent utilities, it shall be deemed a Relief Event, and the Agency shall be responsible for all costs and delays associated with the relocation or diversion of the same in accordance with the provisions of Article 15 (Relief Extensions & Relief Compensations).]

    - [In the event the Concessionaire suffers a delay in the performance of its obligations under this Agreement due to the relocation of existing utilities (the Utility Relocation Delay), the Concessionaire shall be entitled, at its sole election, to either: an extension of Time for Completion corresponding to the period of such delay; or a cash compensation amount equivalent to the actual costs and/or losses incurred as a direct result of such delay (the Compensation Amount). The occurrence of such Utility Relocation Delay and the corresponding extension of time or Compensation Amount must be duly verified and certified by the Independent Engineer. In the event the Concessionaire elects to receive the Compensation Amount, the Agency shall make full payment of the IE-certified Compensation Amount to the Concessionaire within sixty (60) days of the issuance of the Independent Engineer's certification.]

## New Utilities and Roads

    - The Concessionaire shall allow utility companies (subject to the consent of theAgency and subject to such conditions as the Agency may specify and subject to mutual agreement between the Agency, Concessionaire and the utility companies), access to, and use of the Project Site for laying telephone lines, water pipes, electric cables or other public utilities; provided, that nothing contained in this Section 4.11.1 shall waive and/or relieve or be deemed to waive and/or relieve the obligations of the Concessionaire contained in the Agency Agreements and any damage caused to the Concession Assets by such access to, and use of the Project Site for laying telephone lines, water pipes, electric cables or other public utilities shall be restored forthwith.

    - The affected part of the Concession Assets (or any part thereof) (the Utilities Affected Assets) shall be restored in accordance with the Applicable Standards and Good Industry Practice by the Concessionaire and the costs relating to the same shall be borne by the Concessionaire and/or the utility companies in accordance with the terms mutually agreed between the Concessionaire and the utility companies; provided, however, any such terms (including any amendments of the same) shall be subject to the prior approval of the Agency (which approval shall not be unreasonably delayed, conditioned or withheld). Notwithstanding anything to the contrary set out herein, the Agency shall neither be responsible for restoration of any Utilities Affected Assets nor for any costs relating to the same.

    - The Agency exclusively reserves the right to charge fees from the utility company or any other entity for allowing the passage of the telephone lines, water pipes, electric cables or other public utilities over or under the Project Site and such fee, in case being paid to the Concessionaire, shall be paid to the Agency through such mechanism as the Agency has notified to the Concessionaire (the Utility Proceeds).

## Agency Indemnities in Respect of Project Site

    - The Agency shall indemnify and shall hold the Concessionaire harmless from any costs, claims, expenses or charges incurred (in respect of the time period falling prior to delivery of Vacant Possession of Project Site to the Concessionaire) in relocating, rehabilitating or resettling persons in connection with making available the Project Site to the Concessionaire for implementation of the Project and for delivery of Vacant Possession of the Project Site to the Concessionaire.

    - The Agency hereby indemnifies and holds harmless the Concessionaire against all Losses arising in connection with or relating to any defect in title in the Concessionaire’s Project Site Land Instrument Right in the Project Site, which prevents, impedes or delays the Concessionaire from constructing or Operating and Maintaining the Concession Assets in accordance with this Agreement; provided, that such Losses are not the consequence of any breach or non-compliance by the Concessionaire of this Agreement, the  Project Site Land Instrument and the Applicable Standards; provided, further that such action is not a consequence of the Concessionaire’s failure to maintain the Project Site in its possession free from encroachments and encumbrances by third parties and/or is not as a consequence or failure by the Concessionaire to meet its obligations under this Agreement.

    - [The Agency shall defend any claim, suit, action or proceeding brought by any third party asserting any title, competing interest, or right in respect of the Project Site. Furthermore, the Agency hereby indemnifies and holds harmless the Concessionaire against all Losses arising in connection with or relating to any such third-party claim, suit, action or proceeding.]

## Removal of Material Adverse Impediment

    - Following delivery of the Vacant Possession of the Project Site to the Concessionaire by the Agency, the Concessionaire shall be responsible for removal of all impediments, debris (including any structures not in anyone’s possession) on the Project Site, whether physical or legal, to the development and Operation and Maintenance of the Concession Assets; provided, however, that the Concessionaire shall Notify the Agency, within ten (10) days of any impediment (the Material Adverse Impediment) on the Project Site, whether physical or legal, to the development and/or Operation and Maintenance of the Concession Assets which:

- causes a Material Adverse Effect;

- is not attributable to the Concessionaire;

- in the opinion of the Independent Engineer, could not have been identified or foreseen through any investigations of the Project Site Conditions carried out, or deemed to be carried out, by the Concessionaire, in terms of Section 4.4; and

- does not result from any non-compliance by the Sponsor and/or the Concessionaire under any Agency Agreements.

    - Any Notice issued by the Concessionaire pursuant to Section 4.15.1 shall be duly verified and certified by the Independent Engineer prior to submission to the Agency and the Independent Engineer shall, prior to delivery of such Notice to the Agency, duly certify in the Notice, inter alia, the occurrence and subsistence of the Material Adverse Impediment and the time period required for removal of the same (the Material Impediment Removal Period). Upon receipt by the Agency of the Notice duly verified and certified by the Independent Engineer, the Agency shall act so as to remove such Material Adverse Impediment within the Material Impediment Removal Period. In the event the Concessionaire suffers delays in the performance of its obligations and/or incurs costs, in each case, as a direct result of the Material Adverse Impediment, the same shall entitle the Concessionaire to issuance of a Relief Order Request and in such case, the provisions of Article 15 (Relief Extensions & Relief Compensations) shall apply.

## Title to Project Site,  Development Works and Concession Assets

## The Agency shall retain all rights and title to the Project Site throughout the Concession Period. Subject to the terms of this Agreement, the Concessionaire has, and shall have, no title to, ownership interest in or lien over, the Project Site nor shall it create any Encumbrance with respect thereto.

## The Concessionaire shall retain all leasehold rights in respect of the Project Site and legal and beneficial rights and ownership of the Concession Assets (including the  Development Works) as and when the same are performed and/or completed until the Transfer Date.

## On the Transfer Date and subject to:

- receipt by the shareholders of Sponsor Shares of the Termination Payment in accordance with Section 23.5 (Termination Payments);

- resolution of Disputes (if any); and

- settlement of outstanding payments and accounts of the Concessionaire with regards to any due and payable payments under the Agreement, as verified by the Independent Engineer and Independent Auditor;

## the Concessionaire shall transfer the ownership rights to the Concession Assets to the Agency and at the Agency’s option (to be exercised in its sole and absolute discretion) transfer all the Sponsor Shares to the Agency in accordance with the terms of this Agreement. In the event the Agency:

- elects to acquire Sponsor Shares on the Transfer Date and if the Concessionaire is publicly listed on the Transfer Date, the Concessionaire and Agency shall mutually agree on a mechanism to acquire Sponsor Shares held by any shareholders other than the Sponsor; or

- elects not to exercise its discretion of transferring Sponsor Shares from the Concessionaire to the Agency, then the Concessionaire hereby undertakes to cancel the Agency’s shares (if applicable) in compliance with the Applicable Laws.

# Independent Engineer

## Selection

    - Within five (5) days from the Effective Date, the Concessionaire shall provide the Agency with a list of three (3) reputable firms of engineers for appointment of the Independent Engineer (the First IE List). In the event the proposed Independent Engineer is a consortium of engineers then: (a) a lead consortium member shall serve as the lead Independent Engineer and shall be fully responsible for the overall management, coordination and implementation of the services under the Independent Engineer Contract; and (b)[ the consortium members shall be jointly and severally liable for the services under the Independent Engineer Contract.]

    - Within ten (10) days of receipt by the Agency of the First IE List, the Agency shall (subject to one (1) of the firms in the First IE List being acceptable to the Agency) select a reputed firm of engineers from the First IE List and the Agency and the Concessionaire shall appoint such firm as the Independent Engineer in terms of the Independent Engineer Contract within ten (10) days of receipt of such slection notice from the Agency. The Independent Engineer Contract shall be executed within one (1) month from the Effective Date.

    - In the event the firms of engineers identified by the Concessionaire in the First IE List are not acceptable to the Agency, the Concessionaire and the Agency shall appoint (in terms of the Independent Engineer Contract to be executed within one (1) month from the Effective Date) such firm as the Independent Engineer as is mutually acceptable to the Agency and the Concessionaire within one (1) month of the Effective Date and such appointment shall be made in terms of the Independent Engineer Contract (the Independent Engineer Appointment Date).

    - Failure by the Concessionaire to execute the Independent Engineer Contract by the Independent Engineer Appointment Date shall constitute a Material Breach of this Agreement.

    - The Independent Engineer shall provide the services set out in the Independent Engineer Contract and as requested by the Parties with mutual consent from time to time. Unless mutually agreed otherwise between the Parties, the Independent Engineer Contract shall be in accordance with the Indicative Independent Engineer Terms of Reference.

    - [Any Dispute between the Parties arising from the selection of the Independent Engineer or if the Parties fail to reach agreement as to the Independent Engineer under Section 5.1 and 5.2,  then the Dispute shall be resolved following the procedures for the settlement of disputes stipulated in Section 28 (Dispute Resolution).]

## Term of Appointment of the Independent Engineer

    - The appointment of the Independent Engineer shall be for an initial term of three (3) years from the date of the effectiveness of the Independent Engineer Contract (the Independent Engineer Appointment Term); provided, however, that:

- the Independent Engineer Appointment Term shall be extended prior to expiry of the same with the mutual consent of the Parties so as to ensure that at all times during the Concession Period an Independent Engineer is retained/appointed, for the purposes set out in this Agreement; or

- the Parties shall be entitled to appoint a new Independent Engineer prior to the expiry of the Independent Engineer Appointment Term (such appointment to be effective upon expiry of the Independent Engineer Appointment Term) so as to ensure that at all times during the Concession Period an Independent Engineer is retained/appointed for the purposes set out in this Agreement. In the event of the appointment of a new Independent Engineer upon expiry of the Independent Engineer Appointment Term, the provisions of Section 5.2.3 shall apply.

    - The appointment of the Independent Engineer may be terminated:

- by either Party if, the Independent Engineer is adjudged insolvent and/or bankrupt and/or the winding up proceedings are filed against the Independent Engineer and/or the Independent Engineer files winding up proceedings in a court of law and/ or any action for malpractice and/or misadministration is filed against the Independent Engineer in a court of law;

- by the Parties with the mutual consent of the Parties.

    - Upon the occurrence of any of the events listed in Section 5.2.2, the Parties shall have the right to terminate the Independent Engineer Contract in accordance with the terms of the same  and/or in the event of expiry of the Independent Engineer Appointment Term, the Parties shall appoint a new Independent Engineer in accordance with this Section 5.2.3. In the afore-stated circumstances, the Parties shall replace the appointed Independent Engineer with another consulting engineering firm or body corporate selected by the Agency from the First IE List provided by the Concessionaire pursuant to Section 5.1.1 ; provided, however, that the termination and/or replacement of the Independent Engineer shall not have effect until such time as the replacement Independent Engineer has been appointed. In the event the Agency objects to the appointment of any firm of engineers named in the First IE List, then the Concessionaire shall provide the Agency with a new list of three (3) reputable firms of engineers for appointment of the replacement Independent Engineer (the New IE List). Within ten (10) days of receipt by the Agency of the New IE List, the Agency shall either:

- select a reputable firm of engineers from the New IE List and shall cause the Concessionaire to appoint such firm as the Independent Engineer; or

- reject the appointment of any of the firms provided in the New IE List, in which case, the Parties shall appoint such firm of engineers as the new Independent Engineer as is mutually agreed by the Parties.

The provisions of this Article 5 (Independent Engineer) shall apply to any new Independent Engineer (including appointment and replacement of the same) appointed in accordance with the terms herein.

    - The term of appointment of the replacement Independent Engineer shall be the unexpired period of the Independent Engineer Appointment Term or such other term as may be mutually agreed between the Parties.

    - The Concessionaire shall ensure that all provisions of this Agreement pertaining to the Independent Engineer and its responsibilities in respect of the matters set out herein are duly incorporated in the Independent Engineer Contract.

## Independent Engineer Authorized Signatories

The Parties shall require the Independent Engineer to designate and notify the Agency and the Concessionaire of the authorized representatives of the Independent Engineer that shall be authorized by the Independent Engineer to sign for and on behalf of the Independent Engineer, and any communication or document required to be signed by the Independent Engineer shall be valid and effective only if signed by such authorized signatories on behalf of the Independent Engineer; provided, that the Independent Engineer may, by notice in writing to the Parties, substitute any of the authorized signatories.

## Decision of Independent Engineer & Dispute Resolution

    - Subject to Section 5.4.2, any advice, instruction, decision, direction and/or award of the Independent Engineer shall be binding on the Parties unless mutually agreed otherwise by the Parties.

    - In the event any Dispute arises between the Agency and the Concessionaire with regard to any advice, instruction, decision, direction and/or award of the Independent Engineer, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

## Independent Engineer Remuneration

    - The Concessionaire shall be solely responsible for the payment of the fees and expenses payable to the Independent Engineer pursuant to the Independent Engineer Contract (the Independent Engineer Payments), notwithstanding that the Independent Engineer shall be appointed by and shall fulfill its obligations in accordance with the terms of the Independent Engineer Contract.

    - The Concessionaire undertakes to effect the Independent Engineer Payments in a diligent and timely manner and in accordance with the Independent Engineer Contract.

## Independent Engineer Payment Account

    - The Concessionaire shall establish and maintain the Independent Engineer Payment Account from the Commencement Date and until the Trigger Date.

    - The Concessionaire shall issue irrevocable standing instructions to the Independent Engineer Payment Account Bank (in form and substance agreed between the Parties) (the Independent Engineer Payment Account Standing Instructions) in accordance with the Independent Engineer Contract.

    - The Independent Engineer Payment Account Standing Instructions issued by the Concessionaire shall not be unilaterally suspended, amended and/or revoked by either Party and shall remain effective, in each case, until the Trigger Date (or such other date as is mutually agreed between the Parties), and no withdrawal from the Independent Engineer Payment Account may be made by the Concessionaire, except as provided in this Agreement and the Independent Engineer Payment Account Standing Instructions. The Independent Engineer Payment Account Standing Instructions may be suspended, amended and/or revoked with the mutual consent of the Parties.

# Independent Auditor

## Selection

    - Within five (5) days from the Effective Date, the Concessionaire shall provide the Agency with a list of four (4) reputable firms of chartered accountants for appointment of the Independent Auditor (the First IA List). In the event the proposed Independent Auditor is a consortium of chartered accountants then: (a) a lead consortium member shall serve as the lead Independent Auditor and shall be fully responsible for the overall management, coordination and implementation of the services under the Independent Auditor Contract; and (b)[ the consortium members shall be jointly and severally liable for the services under the Independent Auditor Contract.]

    - Within ten (10) days of receipt by the Agency of the First IA List, the Agency shall (subject to one of the firms in the First IA List being acceptable to the Agency) select a reputed firm of auditors from the First IA List and the Agency and the Concessionaire shall appoint such firm as the Independent Auditor in terms of the Independent Auditor Contract within ten (10) days of receipt of such slection notice from the Agency. The Independent Auditor Contract shall be executed within one (1) month from the Effective Date.

    - In the event the firms of auditors identified by the Concessionaire in the First IA List are not acceptable to the Agency, the Concessionaire and the Agency shall appoint (in terms of the Independent Auditor Contract to be executed within one (1) month from the Effective Date) such firm as the Independent Auditor as is mutually acceptable to the Agency and the Concessionaire within one (1) month of the Effective Date and such appointment shall be made in terms of the Independent Auditor Contract (the Independent Auditor Appointment Date).

    - Failure by the Concessionaire to execute the Independent Auditor Contract by the Independent Auditor Appointment Date shall constitute a Material Breach of this Agreement.

    - The Independent Auditor shall provide the services set out in the Independent Auditor Contract and as requested by the Parties with mutual consent from time to time. Unless mutually agreed otherwise between the Parties, the Independent Auditor Contract shall be in accordance with the Indicative Independent Auditor Terms of Reference.

    - [Any Dispute between the Parties arising from the selection of the Independent Auditor or if the Parties fail to reach agreement as to the Independent Auditor under Sections 6.1 and 6.2, then the Dispute shall be resolved following the procedures for the settlement of disputes stipulated in Section 28 (Dispute Resolution).]

## Term of Appointment of the Independent Auditor

    - The appointment of the Independent Auditor shall be for an initial term of two (2) years from the date of the effectiveness of the Independent Auditor Contract (the Independent Auditor Appointment Term); provided, however, that:

- the Independent Auditor Appointment Term shall be extended prior to expiry of the same with the mutual consent of the Parties so as to ensure that at all times during the Concession Period an Independent Auditor is retained/appointed for the purposes set out in this Agreement; or

- the Parties shall be entitled to appoint a new Independent Auditor prior to the expiry of the Independent Auditor Appointment Term (such appointment to be effective upon expiry of the Independent Auditor Appointment Term) so as to ensure that at all times during the Concession Period an Independent Auditor is retained/appointed for the purposes set out in this Agreement. In the event of the appointment of a new Independent Auditor upon expiry of the Independent Auditor Appointment Term, the provisions of Section 6.2.3 shall apply.

    - The appointment of the Independent Auditor may be terminated:

- by either Party if the Independent Auditor is adjudged insolvent and/or bankrupt and/or winding up proceedings are filed against the Independent Auditor and/or the Independent Auditor files winding up proceedings in a court of law and/or any action for malpractice and/or misadministration is filed against the Independent Auditor in a court of law;

- by the Parties with the mutual consent of the Parties.

    - Upon the occurrence of any of the events listed in Section 6.2.2, the Parties shall have the right to terminate the Independent Auditor Contract in accordance with the terms of the same and/or in the event of expiry of the Independent Auditor Appointment Term, the Parties shall appoint a new Independent Auditor in accordance with this Section 6.2.3. In the afore-stated circumstances, the Parties shall replace the appointed Independent Auditor with another firm of chartered accountants selected by the Agency from the First IA List provided by the Concessionaire pursuant to Section 6.1.1; provided, however, that the termination and/or replacement of the Independent Auditor shall not have effect until such time as the replacement Independent Auditor has been appointed. In the event the Agency objects to the appointment of any firm of chartered accountants named in the First IA List, then the Concessionaire shall provide the Agency with a new list of three (3) reputable firms of chartered accountants for appointment of the replacement Independent Auditor (the New IA List). Within ten (10) days of receipt by the Agency of the New IA List, the Agency shall either:

- select a reputable firm of chartered accountants from the New IA List and shall cause the Concessionaire to appoint such firm as the Independent Auditor; or

- reject the appointment of any of the firms provided in the New IA List, in which case, [the Parties shall appoint one of the State Approved Accounting Firms with mutual consent of the Parties as the new Independent Auditor.]

The provisions of this Article 6 (Independent Auditor) shall apply to any new Independent Auditor (including appointment and replacement of the same) appointed in accordance with the terms herein.

    - The term of appointment of the replacement Independent Auditor shall be the unexpired period of the Independent Auditor Appointment Term or such other term as may be mutually agreed between the Parties.

    - The Concessionaire shall ensure that all provisions of this Agreement pertaining to the Independent Auditor and its responsibilities in respect of the matters set out herein are duly incorporated in the Independent Auditor Contract.

## Independent Auditor Authorized Signatories

    - The Parties shall require the Independent Auditor to designate and notify the Agency and the Concessionaire of the authorized representatives of the Independent Auditor that shall be authorized by the Independent Auditor to sign for and on behalf of the Independent Auditor, and any communication or document required to be signed by the Independent Auditor shall be valid and effective only if signed by such authorized signatories on behalf of the Independent Auditor; provided, that the Independent Auditor may, by notice in writing to the Parties, substitute any of the authorized signatories.

## Decision of Independent Auditor & Dispute Resolution

    - Subject to Section 6.4.2, any advice, instruction, decision, direction and/or award of the Independent Auditor shall be binding on the Parties unless mutually agreed otherwise by the Parties.

    - In the event any Dispute arises between the Agency and the Concessionaire with regard to any advice, instruction, decision, direction and/or award of the Independent Auditor, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

## Independent Auditor Remuneration

    - The Concessionaire shall be solely responsible for the payment of the fees and expenses payable to the Independent Auditor pursuant to the Independent Auditor Contract (the Independent Auditor Payments), notwithstanding that the Independent Auditor shall be appointed by and shall fulfill its obligations in accordance with the terms of the Independent Auditor Contract.

    - The Concessionaire undertakes to effect the Independent Auditor Payments in a diligent and timely manner and in accordance with the Independent Auditor Contract.

## Independent Auditor Payment Account

    - The Concessionaire shall establish and maintain the Independent Auditor Payment Account from the Commencement Date and until the Trigger Date.

    - The Concessionaire shall issue irrevocable standing instructions to the Independent Auditor Payment Account Bank (in form and substance agreed between the Parties) (the Independent Auditor Payment Account Standing Instructions) in accordance with the Independent Auditor Contract.

    - The Independent Auditor Payment Account Standing Instructions issued by the Concessionaire shall not be unilaterally suspended, amended and/or revoked by either Party and shall remain effective, in each case, until the Trigger Date (or such other date as is mutually agreed between the Parties), and no withdrawal from the Independent Auditor Payment Account may be made by the Concessionaire, except as provided in this Agreement and the Independent Auditor Payment Account Standing Instructions. The Independent Auditor Payment Account Standing Instructions may be suspended, amended and/or revoked with the mutual consent of the Parties.

# Concessionaire’s Representations, Warranties and Certain Obligations & Undertakings

## Concessionaire Representations & Warranties

## The Concessionaire hereby represents and warrants to the  Agency that:

## it is duly organized and validly existing under the Applicable Laws, and that it has full power and authority to execute and perform its obligations under this Agreement and to carry out the transactions contemplated hereby;

## it has taken all necessary corporate and other actions under the Applicable Laws to:

## (i) 	authorize the execution, delivery and performance of this Agreement; and

## (ii)	validly exercise its rights and perform its obligations under this Agreement;

## this Agreement and all obligations contained herein constitute its legal, valid and binding obligations, enforceable against it in accordance with the terms hereof;

## it has the financial standing and capability to undertake and implement the Project in accordance with the Applicable Standards and neither the Concessionaire nor the Sponsors have committed a breach or have defaulted in respect of their payment obligations in relation to a financial indebtedness;

## it is subject to the Applicable Laws, and hereby expressly and irrevocably waives any immunity in any jurisdiction in respect of this Agreement and/or matters arising hereunder including any obligation, liability or responsibility hereunder;

## the execution, delivery and performance of this Agreement does not and shall not conflict with, result in the breach of, constitute a default under, or accelerate performance required by any of the terms of its memorandum and articles of association or any of its constitutive and corporate charters, filings with Government Authorities, documents, or any Applicable Laws or any covenant, contract, agreement, arrangement, understanding, decree or order to which it is a party or by which it or any of its properties or assets is bound or affected;

## there are no actions, arbitrations, suits, litigations, proceedings, or investigations pending or, to its best knowledge, threatened against it under the Applicable Laws before any court or before any other judicial, quasi-judicial or other authority, the outcome of which (i) could reasonably be expected to have a Material Adverse Effect; (ii) may result in the breach of this Agreement; (iii) individually or in the aggregate may result in any material impairment of its ability to perform any of its obligations under this Agreement; and (iv) may affect the legality, validity, or enforceability of this Agreement;

## it has no knowledge of any violation or default with respect to any Legal Requirements which may result in any Material Adverse Effect on its ability to perform its obligations under this Agreement and no fact or circumstance exists which may give rise to such proceedings that would have a Material Adverse Effect on the performance of its obligations under this Agreement;

## it has complied with Applicable Laws in all material respects and has not been subject to any fines, penalties, injunctive relief or any other civil or criminal liabilities which in the aggregate have or may have a Material Adverse Effect on its ability to perform its obligations under this Agreement;

## the Sponsor owns one hundred percent (100%) of the Sponsor Shares as of the Effective Date and no Encumbrances exist on such Sponsor Shares;

## no representation or warranty made by the Concessionaire and contained herein or in any other document furnished by it to the  Agency or to any Government Authority in relation to the Concessionaire Permits contains any untrue or misleading statement of material fact or omits or shall omit to state a material fact necessary to make such representation or warranty misleading;

## no sums, in cash or kind, have been paid or shall be paid, by it or on its behalf, to any Person by way of fees, commission or otherwise for securing the Concession or entering into this Agreement or for influencing or attempting to influence any officer or employee of the  Agency in connection therewith and neither the Concessionaire nor the Sponsor (together with their Affiliates) have engaged in any Corrupt Act in respect of the foregoing;

## each of the Concessionaire and the Sponsors have complied with requirements of the Applicable Laws and the RFP (to the extent the same are applicable to the Concessionaire and the bidders) in the preparation, finalization, delivery and submission of its Bid for the award of the Project and the Concession to the Concessionaire and have undertaken all acts and deeds (to the extent the same are applicable to the Concessionaire and the bidders) necessary for award of the Concession and the Project to the Concessionaire in terms of the RFP and the Applicable Laws;

## all representations, breach of which may cause a Material Adverse Effect, provided by the Concessionaire and/or Sponsor in its Bid submitted in response to the RFP, are true and accurate in all respects;

## it is subject to civil and commercial law with respect to this Agreement and it hereby expressly and irrevocably waives any sovereign immunity (if any) in any jurisdiction;

## the Concessionaire has furnished a valid and effective   Development Performance Security to the  Agency prior to the Effective Date and the  Development Performance Security is valid and subsisting;

## all information, data, and documentation provided by the Sponsor and the Concessionaire in the Bid and the RFP submissions were, and remain, true, accurate, and complete in all material respects as of the Effective Date;

## In the event that any occurrence or circumstance comes to the attention of either Party that renders any of its aforesaid representations or warranties untrue or incorrect, such Party shall immediately Notify the other Party of the same. Such Notification shall not have the effect of remedying any breach of the representation or warranty that has been found to be untrue or incorrect nor shall it adversely affect or waive any right, remedy or obligation of either Party under this Agreement or any  Agency Agreement.

## The Concessionaire shall repeat the representations and warranties under Section 7.1.1 at the Commencement Date.

## Concessionaire’s General Undertakings

    - The Concessionaire hereby undertakes that it shall, at its own cost and expense:

## comply with and perform all duties, obligations, acts, and deeds set out in, in each case, the Applicable Standards;

## continuously and diligently undertake, perform and complete all Project Works and Concession Assets in accordance with the Applicable Standards and within the Time for Completion;

## ensure that all Project Works and Concession Assets comply with the Applicable Standards;

## investigate, study, finance, design, construct, Operate and Maintain the Concession Assets in accordance with the Applicable Standards;

## ensure and achieve each Project Milestone on or prior to its Project Milestone Date in accordance with the Applicable Standards including:

## (i)	achieve Substantial Completion on or prior to the Scheduled Substantial Completion Date;

## (ii)	achieve Project Development Completion on or prior to the Scheduled Project Development Completion Date;

## remedy any Defects & Deficiencies in the Project Works (including in the performance of the same) and/or the Concession Assets at its own cost and risk;

## obtain and maintain all Concessionaire Permits (including any renewals of the same) in conformity with the Applicable Laws and be in compliance thereof, and deliver copies of the same to the Agency, the Independent Engineer and the Independent Auditor from time to time;

## be in compliance with and perform all its obligations in accordance with, in each case, the Applicable Laws and fulfill the requirements (including the environmental requirements) under the Applicable Laws;

## procure and maintain in full force and effect, as necessary, appropriate proprietary rights, licenses/ leases, agreements and permissions for materials, methods, processes and systems used in or incorporated into the Project;

## appoint, supervise, monitor and control as necessary, the activities of the Concessionaire Engaged Persons (including those of the Contractors under their respective and relevant Project Agreements), provided that, at all times, the Concessionaire shall be fully responsible for all acts or omissions of the Concessionaire Engaged Persons, as further contemplated in Section 7.3;

## make its own arrangements for materials (including development materials), parts, components, supplies, tools, machinery etc. for performance of the Project Works;

## be responsible for strict compliance with the relevant Applicable Standards notwithstanding the appointment and/or engagement by it of the Concessionaire Engaged Persons to implement the Project (or any part thereof) and performance of Project Works (or any part thereof);

## keep and maintain the Project Site free from all encroachments and take all steps necessary to remove encroachments, if any;

## except as provided in this Agreement, make payments to the relevant Government Authority, if required, for provision of such services as are not provided in the normal course or are available only on payment;

## afford access of the Project Site to the authorized representatives of the  Agency, the Independent Engineer, Independent Auditor and any Government Authority having jurisdiction over the Project, including those concerned with safety, security or environmental protection to inspect the Project Works and the Concession Assets and, upon reasonable notice, to investigate any matter within their authority, and provide to such Persons assistance reasonably required to carry out their respective duties and functions;

## not engage in any business or activity other than the business or related to, and conducted for, the purpose of the Project and/or other than as provided in this Agreement;

## maintain its corporate existence and its rights to carry on operations of its business;

## provide all necessary assistance to the  Agency Representative, as the  Agency Representative may reasonably require for the performance of its duties and services;

## make all payments to the Agency of the amounts due and payable by the Concessionaire in accordance with the terms of this Agreement and the Agency Agreements;

## ensure that no damage is caused to any property belonging to the Agency and/or other third parties in the execution of the Project Works;

## coordinate and manage all the Project Works and be responsible for the coordination and general management of the Project Works;

## provide to the  Agency, the Independent Auditor and the Independent Engineer all such information relating to the Project Works and the execution and completion of the same as is reasonably requested by the  Agency, the Independent Auditor and the Independent Engineer from time to time;

## Notify the  Agency, the Independent Engineer and/or the Independent Auditor (as applicable) without undue delay upon becoming aware of any changes in the information provided and/or to be provided to the same by the Concessionaire pursuant to the Applicable Standards;

## provide all necessary assistance to the Independent Engineer and the Independent Auditor as the same may reasonably require for the performance of their duties and services in accordance with the Independent Engineer Contract and the Independent Auditor Contract, respectively, and for the performance of its roles and obligations contemplated under this Agreement and the  Agency Agreements;

## ensure that the Project Agreements entered into by the Concessionaire shall not be inconsistent with the terms and conditions of the  Agency Agreements;

## submit from time to time to the Agency and the Independent Engineer its development methodology and quality assurance procedures for implementation and completion of the Project in accordance with the Applicable Standards and the same shall be subject to the review and approval of the Independent Engineer;

## undertake, do and perform from time to time, all such acts, deeds and things as may be necessary or required before commencement of Project Works (or any part thereof) for the performance of the Project Works under and in accordance with the Applicable Standards;

## construct, provide and maintain a reasonably furnished site office accommodation for the Independent Engineer at the Project Site commencing from the Commencement Date and until the Transfer Date;

## ensure the safety of the Concession Assets in accordance with the Safety Requirements;

## maintain the Project Site and the Concession Assets in good condition;

## the Concessionaire has complied with all the conditions set–out in the EIA Approval in accordance with the Applicable Laws and the same stands approved by the Relevant Environmental Protection Agency and has submitted a copy of each of the same (i.e. the report and its approval) to the  Agency (with a copy delivered to the Independent Engineer and the Independent Auditor);

## provide the Project Management / Implementation Unit with vehicles in accordance with Schedule W (Project Management and Implementation Unit Vehicles);

- the Concessionaire shall supervise the works during the relocation of existing utilities, and all utility stakeholders, in relation to the agreed alignments (for excavation, laying, back-filling, erection of utility poles etc.) by seeking assistance from the design consultant with respect to the survey points without damaging the existing utilities and roads for the relocation of utilities if encountered; and

- comply with the Specific Concessionaire Undertakings.

## Concessionaire Engaged Persons

    - The Concessionaire shall, commencing from the Effective Date, have requisite organization and designate and appoint suitable officers/ representatives as it may deem appropriate to implement and supervise the Project, to deal with the Independent Engineer/Independent Auditor/the  Agency and to be responsible for all necessary exchange of information required pursuant to the Applicable Standards.

    - The Concessionaire shall ensure that the Concessionaire Engaged Persons are experienced and qualified for the purposes of Project implementation and performance of the Project Works and are at all times properly trained for their respective functions. The Concessionaire shall be responsible for maintaining harmony and good industrial relations among the Concessionaire Engaged Persons.

    - The Concessionaire shall be fully and solely responsible for:

- observance by all the Concessionaire Engaged Persons of all the provisions and requirements of the Applicable Standards;

- the acts, omissions, failure to perform, breaches or defaults of the Concessionaire Engaged Persons of the Applicable Standards as fully as if they were the acts, omissions, failures, breaches or defaults of the Concessionaire of the Applicable Standards under this Agreement and the  Agency Agreement.

    - The Concessionaire shall be responsible for strict compliance with the Applicable Standards notwithstanding the appointment and/or engagement by it of the Concessionaire Engaged Persons to implement the Project (or any part thereof) and performance of Project Works (or any part thereof) and  no engagement of any of the Concessionaire Engaged Persons shall release or discharge the Concessionaire of any of its liabilities, responsibilities or obligations under the Applicable Standards and the Concessionaire shall not be entitled to any relief or compensation (including any extension of Time For Completion and/or monetary compensations) under this Agreement or otherwise for any acts, omissions, failures, breaches or defaults of the Concessionaire Engaged Persons. Notwithstanding anything to the contrary, the Agency shall not be liable or responsible in any manner whatsoever under any Applicable Laws, in contract, tort or otherwise in respect of the Concessionaire Engaged Persons.

    - Employment of any foreign Concessionaire Engaged Persons shall be subject to grant of requisite regulatory permits and approvals including employment/residential visas and work permits, if any required, and the obligation to apply for and obtain the same shall be the sole responsibility of the Concessionaire and, notwithstanding anything to the contrary contained in this Agreement or otherwise, refusal of or inability to obtain any such permits and approvals by the Concessionaire or the relevant Contractor shall not constitute a Force Majeure Event, and shall not in any manner excuse the Concessionaire from the performance and discharge of its obligations and liabilities under the Applicable Standards. The Concessionaire shall use reasonable efforts to promote local contractors and to employ and engage, to the extent practicable local employees and contractors.

    - The Concessionaire undertakes that it shall and any of its Concessionaire Engaged Persons shall be available to attend any meetings with the  Agency, the Independent Engineer and/or the Independent Auditor at all reasonable times, as required and Notified by the  Agency, the Independent Engineer and/or the Independent Auditor (as applicable) to the Concessionaire. All costs for attending such meetings by (including those relating to preparation and attendance in such meetings by the Concessionaire Engaged Persons) shall be on the Concessionaire’s account.

## Concessionaire Authorized Representative & Concessionaire Project Expert

## Within forty (40) days following the Effective Date, the Concessionaire shall:

## appoint, with the prior Notification to the  Agency, the Independent Engineer and the Independent Auditor, in accordance with Section 5 (Independent Engineer) and Section 6 (Independent Auditor) and all Applicable Laws, its representative duly authorized to deal with the  Agency in respect of all matters under or arising out of or relating to this Agreement (the Concessionaire Authorized Representative); and

- appoint, in accordance with the criteria set out in Schedule A (Scope of Work) and Applicable Laws, with prior Notification to the Agency and the Independent Engineer, at its sole cost and expense one or more established consulting firm and/or individual(s) to: (i) supervise the  Development Works; (ii) co-ordinate with the Independent Engineer and  Agency with respect to technical matters relating to the Project; and (iii) ensure that the Development Works are performed in accordance with the Applicable Standards (the Concessionaire Project Expert). In the event the Concessionaire Project Expert is a consulting firm, any personnel assigned to this Project shall also be required to satisfy the criteria set out in Schedule A (Scope of Work).

    - The Concessionaire shall:

(a)	ensure that the Concessionaire Authorized Representative or the Concessionaire Project Expertperform their respective obligations in the same manner as the Concessionaire is required to perform its obligations under this Agreement; and

(b)	prior to any substitution of the Concessionaire Authorized Representative and/or the Concessionaire Project Expert, the Concessionaire shall submit the details of the same to the  Agency in writing (with copies to the Independent Engineer and the Independent Auditor) and shall provide any other information reasonably requested by the  Agency in respect of the same.

    - The Concessionaire shall substitute the Concessionaire Authorized Representative and the Concessionaire Project Expert with the prior approval of the  Agency. The approval by the  Agency shall not be unreasonably withheld, conditioned or delayed; provided, however, in the event the  Agency fails to grant its approval or disapproval to the Concessionaire for the appointment and/or substitution of the Concessionaire Authorized Representative and/or the Concessionaire Project Expertwithin fifteen (15) days following the receipt of such request by the Agency from the Concessionaire, the approval of the  Agency for the appointment and/or substitution of the Concessionaire Authorized Representative and/or the Concessionaire Project Expert shall be deemed accorded. The Concessionaire hereby unconditionally and irrevocably confirms, acknowledges and agrees that the liability of the Concessionaire for the performance of its obligation pursuant to this Agreement shall neither be rescinded, waived, reduced, cancelled, terminated and / or in any manner adversely impacted as a direct and/or indirect consequence of the approval or otherwise of the  Agency pursuant to this Section.

## The Development Contractor & The O&M Contractor

    - The Concessionaire hereby undertakes that it shall:

(a)	ensure that the Development Contract and the O&M Contracts are entered into on an arm’s length basis and on commercially viable terms;

(b)	ensure that the assets created and/or constructed forming part of the Concession Assets pursuant to the Development Contract and the O&M Contract vest in the Agency on the Transfer Date;

(c)	ensure that the Development Contractor or the O&M Contractor perform their respective obligations in the same manner that the Concessionaire is required to perform its obligations under this Agreement; and

(d)	deliver copies of each of the Development Contract(s) and the O&M Contract(s) to the Agency within seven (7) days of execution of each of the Development Contract(s) and the O&M Contract(s), respectively.

    - The Agency shall not be liable for losses (including any Losses) of any nature resulting from the Development Contract and the O&M Contract entered into by the Concessionaire as a result of the expiry of the Concession Period or Termination of this Agreement.

    - Any substitution and/or replacement of the Development Contractor or the O&M Contractor of the Project shall be subject to the approval of the  Agency, which approval shall be at the sole and absolute discretion of the  Agency. In consideration of providing its approval, the  Agency shall consider whether the substitute Development Contractor or the O&M Contractor is, at least, technically, financially and otherwise capable in terms of the criteria provided in the RFP. Further, in granting its approval, the  Agency shall consider the determinations of the Independent Auditor and Independent Engineer, as provided in terms of Section 7.5.4.

    - The Independent Engineer (in respect of technical matters) and the Independent Auditor (in respect of financial matters) shall have the right to approve and/or disapprove any substitution of the Development Contractor and/or the O&M Contractor, if any, in the event (in the reasonable opinion of the Independent Engineer (in respect of technical matters) and the Independent Auditor (in respect of financial matters)):

(a)	such Development Contractor is technically and financially incapable (to the extent of its scope of work) of performing the Development Works (or any part thereof); or

(b)	such O&M Contractor is technically and financially incapable (to the extent of its scope of work) to perform the Operations and Maintenance (or any part thereof);

provided, in their determination of the afore-stated, the Independent Engineer and the Independent Auditor shall ensure, at the very minimum, that the substitute Development Contractor and/or the O&M Contractor is/are, at least, technically, financially and otherwise capable in terms of the criteria provided in the RFP.

    - The execution of the Development Contract(s) and/or the O&M Contract(s), or any amendment thereof shall be subject to the prior approval of the Independent Engineer in respect of payment terms, payment milestones, scope of the relevant Project Works and technical matters to ensure conformity with the terms of the Concession Agreement. The Concessionaire shall deliver to the Independent Engineer copies of the proposed Development Contract(s) and O&M Contract(s) (with a copy to the  Agency), or any amendment thereof. The  Agency shall, within fifteen (15) days of its receipt of the proposed Development Contract(s) and/or the O&M Contract(s), provide its comments or observation on the same, if any, to the Independent Engineer. The Independent Engineer shall within twenty-eight (28) days of the delivery of the proposed Development Contract(s) and O&M Contract(s) and/or any amendments thereof by the Concessionaire, grant its approval or disapproval of the same, in consultation with the  Agency, and/or after removing any objection by the  Agency. In the event no approval or objections to the proposed Development Contract(s) and/or the O&M Contracts is granted by the Independent Engineer within twenty-eight (28) days of the delivery of the same by the Concessionaire, it shall be deemed not to have been objected to by the Independent Engineer.

    - The Concessionaire shall deliver certified (as being true and correct) copies of the executed Development Contract(s) and O&M Contract(s), together with all amendments thereto, to the  Agency, the Independent Engineer and the Independent Auditor within seven (7) days of execution of the same.

## Concessionaire Permits

    - The Concessionaire shall make or cause to be made, in a timely fashion, all applications (whether initial or renewal applications) for the Concessionaire Permits in the prescribed form and with the prescribed fee (in each case, in accordance with the Applicable Laws) to the appropriate Government Authority and shall diligently pursue all such applications. The information supplied in the applications shall be complete and accurate and shall satisfy the substantive and procedural requirements of the Applicable Laws applied in a “non-discriminatory” manner.

    - The Concessionaire shall make or cause to be made, at least monthly prior to the Project Development Completion Date, and at least quarterly thereafter, reports listing its schedule for submitting Concessionaire Permits application forms or renewal application forms, the status of any Concessionaire Permit applications then outstanding, notifications of the granting or denial of any Concessionaire Permit or Concessionaire Permit renewal, and notifications of any violations of any Concessionaire Permit. Each report shall be submitted to the  Agency, the Independent Engineer and the Independent Auditor and shall include copies of all applications and notifications discussed in the report which have not been provided with a previous report. The first section of each report shall also summarize any problems regarding any Concessionaire Permit or Concessionaire Permit application that may materially affect the Concessionaire’s performance under any  Agency Agreement. In the event of any Lapse of Consent, the Concessionaire shall submit a report pursuant to this Section 7.6.2 within three (3) days after becoming aware thereof.

## Preliminary Works

    - The Concessionaire shall perform the Preliminary Works in accordance with this Agreement, as mutually agreed between the Parties. The costs of all Preliminary Works shall be deemed to be included in the Pre-Estimated Project Cost and the Total Project Cost.

## Access Route & Transportation

    - The Concessionaire shall be responsible for selection and usage of all transportation means, transportation routes, roads, bridges, highways and routes within, and to and from the Project Site in respect of performance of its Project Works and the  Agency shall not be responsible for any claims attributable to the Concessionaire in respect of the same. The Concessionaire shall (as between the Parties) be responsible for the repair of access routes damaged by the Concessionaire and/or the Concessionaire Engaged Persons. The extent to which the access routes have been damaged by the Concessionaire shall be assessed by the Independent Engineer.

## Taxes and Subsidies

    - The Concessionaire shall be responsible to make all payments in respect of the rates, taxes (as applicable), charges, levies, assessments or equivalent taxes levied on it.

    - The Concessionaire may raise any objections in terms of any charges levied on it by any Government Authority; provided that such objections shall be filed and pursued at the Concessionaire’s cost and the Concessionaire shall be entitled to any benefit accruing as a result of the Concessionaire’s successful objection.

    - The Concessionaire fully understands that the  Agency or any other Government Authority shall not provide any guarantee, subsidy, grant or any financial support of any nature to the Concessionaire in respect of the Project other than as provided under the  Agency Agreements.

## Protection of the Environment

    - The Concessionaire shall comply with all Applicable Standards (including any condition which may from time to time be imposed by any Government Authority, including the ‘Relevant Environmental Protection Agency’ as regards collection, treatment and disposal or discharge of effluents or waste) pertaining to protection of the environment in its arrangements, execution of Project Works, procurement, development and operations on Project Site. The Concessionaire shall take all necessary steps to protect the environment (both on and off the Project Site) and shall not cause damage and nuisance to people and property resulting from pollution, noise and other results of its operations. The Concessionaire shall ensure that air emissions, surface discharges and effluent from the Project Site during the Concession Period shall not exceed the values prescribed by Applicable Standards.

    - The Concessionaire shall provide properly designed storage areas for its hazardous materials that are impermeable to leakage into the surrounding soil for storage of hazardous wastes. Such storage shall also be covered and protected from inundation and overflow by rainfall into the surrounding soil. Any hazardous materials generated during completion of the Project Works by the Concessionaire (including any of its Concessionaire Engaged Persons) shall be properly disposed of by the Concessionaire on completion of the Project Works. The Concessionaire shall be responsible for keeping safe and disposing any hazardous materials and any dangerous substances on the Project Site generated from time to time during performance and completion of the Project Works or brought on to the Project Site by the Concessionaire.

    - The Concessionaire undertakes to indemnify, defend and hold the  Agency harmless from any and all liabilities, claims, damages, costs, penalties, fines, expenses, fees (including reasonable attorney's fees) and charges of any nature associated with any non-compliance by the Concessionaire of its obligations contained in this Section 7.10 (Protection of Environment).

## Internal Infrastructure Linkages

    - The Concessionaire shall be responsible for internal infrastructure linkages required for the Project such as waste water and storm water drainage at the Project Site. The  Agency shall use reasonable efforts to facilitate the provision thereof with respective Government Authorities at no cost to itself and it shall be the Concessionaire’s responsibility to fulfil any monetary or other compliances, as may be required by such Government Authorities.

## Emergency Decommissioning

    - In the event, during the Operations Period, in the reasonable opinion of the Concessionaire, there exists an Emergency that warrants de-commissioning of the whole or any part of the Concession Assets (the Decommissioned Project Area), the Concessionaire shall be entitled to de-commission and close the whole or any part of Decommissioned Project Area, as the case may be, for so long as such Emergency and the consequences thereof warrant (the Emergency Decommissioning); provided, however, that such Emergency Decommissioning and the particulars thereof shall be notified by the Concessionaire to the  Agency and the Independent Engineer without any delay, and the Concessionaire shall diligently abide by the Applicable Standards (including the Safety Requirements) in dealing with such Emergency Decommissioning and act in accordance with the directions that the Independent Engineer may issue for dealing with such Emergency Decommissioning; provided, however:

- that the Independent Engineer shall, within seven (7) days from the date of the Emergency Decommissioning, certify whether such Emergency Decommissioning was warranted; and

- that the Concessionaire shall re-commission the Decommissioned Project Area, without any delay, whenever the Independent Engineer either: (i) notifies the Concessionaire to re-commission the same; or (ii) certifies that such Emergency Decommissioning was not warranted.

    - Without prejudice to the provisions of Section 7.12.1(b), the Concessionaire hereby undertakes to re-commission the Decommissioned Project Area efficiently and in a time sensitive manner and as quickly as practicable after the circumstances leading to the Emergency Decommissioning have ceased to exist or have so abated as to enable the Concessionaire to re-commission the Decommissioned Project Area and shall notify the  Agency and the Independent Engineer of the same without any delay.

    - The Emergency Decommissioning of the Decommissioned Project Area and the re-commissioning thereof shall, as soon as practicable, be brought to the notice of the affected Persons by means of public announcements/notice by the  Agency. The Independent Engineer shall determine whether the Concessionaire has successfully re-commissioned the Decommissioned Project Area and made the same available as soon as practicable upon the termination/ceasing of the circumstances that have resulted in the Emergency Decommissioning.

    - All expenses, charges, fees, overheads and costs of any nature and all delays, in each case, resulting from and relating to the Emergency Decommissioning shall be borne by and shall be on account of the Concessionaire; provided, however, in the event the Emergency Decommissioning results from an  Agency Event of Default and/or a Force Majeure Event, the Concessionaire shall be entitled to issuance of a Relief Order Request and in such case, the provisions of Article 15 (Relief Extensions & Relief Compensations)shall apply.

## Restoration of Loss or Damage to Project

    - Save and except as a result of  Permitted Events (excluding a Non Political Event), in the event that the Project Works and/or Concession Assets or any part thereof suffers any loss or damage during the Concession Period, the Concessionaire shall, at its cost and expense, rectify and remedy such loss or damage forthwith in accordance with the Applicable Standards so that the Project Works and the Concession Assets conform to the Applicable Standards.

## Accounts and Reports

    - Appointment of Auditors

The Concessionaire shall make arrangements with respect to the installation and operation of an accounting and cost control system and for the appointment, as statutory auditors, of a reputed firm of independent chartered accountants reasonably acceptable to the  Agency and the Independent Auditor.

    - Specific Records

The Concessionaire shall maintain complete and accurate records accounting for all transactions relating to any Relief Order, Relief Costs, extensions of Time for Completion, Change of Scope, minutes of board meetings and shareholder meetings and other records, which records shall be subject to inspection and audit by the  Agency, the Independent Engineer and the Independent Auditor.

    - Periodic Reports

The Concessionaire shall in accordance with this Agreement furnish to the  Agency, the Independent Engineer and the Independent Auditor, the  Development Progress Report and the O&M Status Report.

The Concessionaire shall, as soon as available but in any event within sixty (60) days of filing, furnish to the  Agency, the Independent Engineer and the Independent Auditor two (2) copies of all documents filed in compliance with the requirements of the Companies Act, 2017 as amended or superseded from time to time or any other Applicable Laws.

The Concessionaire shall, as soon as available, furnish to the  Agency, the Independent Engineer and the Independent Auditor, a report on any factors materially and adversely affecting, or that might materially and adversely affect, the Project or the Concessionaire’s business and operations.

    - Reporting of Changes

The Concessionaire shall, at least fourteen (14) days prior to it becoming effective, report to the  Agency, the Independent Engineer and the Independent Auditor any contemplated (i) material change in its memorandum and articles of association; (ii) change in its fiscal year; (iii) change in the constitution of its board of directors; and (iv) change in its chief executive officer; provided, however, that, reporting as aforesaid shall not relieve the Concessionaire from its obligations or liabilities towards any other Government Authority having jurisdiction over any such matter.

    - Lists of Financiers and Creditors

Together with the periodic reports required by Section 7.14.3, the Concessionaire shall also furnish to the  Agency, the Independent Engineer and the Independent Auditor a list of each of its creditors to which the Concessionaire has an outstanding obligation of PKR 1,000,000/- (Pakistani Rupees One Million only) or more, along with statements or schedules of repayment of local and foreign loans/debts to creditors duly certified by its statutory auditors on a six (6) monthly basis in each Accounting Year. The report shall also indicate any changes, as compared to the report submitted the previous Accounting Year that might have occurred.

    - Information Regarding Statutory Notice/Winding Up Proceedings

The Concessionaire shall, within seven (7) days of receipt thereof, provide to the  Agency, the Independent Engineer and the Independent Auditor a copy of any notice that the Concessionaire may be served under Sections 301 and 302 (as such Sections may be amended, modified or re-enacted) of the Companies Act, 2017 by any of its creditors.

The Concessionaire shall provide to the  Agency, the Independent Engineer and the Independent Auditor all information in respect of any further actions taken by its creditors following any notice under Sections 301 and 302 (as such Sections may be amended, modified or re-enacted) of the Companies Act, 2017.

    - Failure by the Concessionaire to submit Reports, Documents and Information

In addition to the rights the  Agency may have under this Agreement or under the Applicable Laws, in the event that the Concessionaire fails to submit any of the documents, reports or information as and when required under this Agreement, the  Agency shall be entitled to assess against and recover from the Concessionaire reasonable costs established from time to time by the  Agency for such non-compliance. Such reasonable costs shall be paid to the  Agency within ten (10) days of notice of such non-compliance and assessment by the  Agency; provided, that such costs shall not exceed an amount equal to PKR 15,000/- (Pakistani Rupees Fifteen Thousand only) for each day that each such document, report or information remains outstanding commencing from the date that notice thereof is delivered by the  Agency to the Concessionaire.

## Affirmations

    - The Concessionaire hereby declares that it has not obtained or induced the procurement of this Agreement and/or any Project Agreement and/or any  Agency Agreement and/or any contract, consent, approval, right, interest, privilege or other obligation or benefit related to this Agreement and/or any  Agency Agreement and/or the Project from the  Agency and/or any Government Authority through any corrupt (including Corrupt Act) or illegal business practice.

    - Without limiting the generality of the foregoing, the Concessionaire represents and warrants that it has fully disclosed in writing all commissions, brokerage and other fees, and other compensation (other than compensation paid to employees of the Concessionaire for services provided) paid or payable to any Person within or outside Pakistan in relation to the Project and has not given or agreed to give and shall not give, or agree to give to any Person within or outside Pakistan either directly or indirectly through any natural or juridical Person, including its Affiliates, employees, agents, associates, brokers, consultants, officers, directors, promoters, shareholders, sponsors or subsidiaries (and any of their employees, agents, associates, brokers, consultants, officers, directors, promoters, shareholders or sponsors), any commission, gratification, bribe, finder’s fee or kickback, whether described as consultation fee or otherwise, with the object of obtaining or inducing the procurement of any  Agency Agreement or any Project Agreement or any contract, right, interest, privilege or other obligation or benefit related to any  Agency Agreement or the Project from the  Agency or any Government Authority, except that which has been expressly declared pursuant hereto.

    - The Concessionaire accepts full responsibility and strict liability for making any intentional false declaration, not making full disclosure, misrepresenting facts or taking any action likely to defeat the purpose of the representations and warranties contained herein and the declarations required hereby. The Concessionaire agrees in the event that any of the representations and warranties made by it in Sections 7.15.1 and 7.15.2 are proved to be materially incorrect, that any contract, consent, approval, right, interest, privilege or other obligation or benefit obtained or procured as aforesaid shall, without prejudice to any other right and remedies available to the  Agency, be voidable and without legal effect at the option of the  Agency.

    - Notwithstanding any rights and remedies that are available to and may be exercised by the  Agency in this regard, the Concessionaire agrees to indemnify the  Agency for any Loss or damage incurred by it on account of its corrupt business practices and further pay compensation to the  Agency in an amount equivalent to ten (10) times the amount of any commission, gratification, bribe, finder’s fee or kickback paid or given by the Concessionaire (either directly or indirectly through any natural or juridical Person, including its Affiliates, employees, agents, associates, brokers, consultants, officers, directors, promoters, shareholders, sponsors or subsidiaries (and any of their employees, agents, associates, brokers, consultants, officers, directors, promoters, shareholders or sponsors), as aforesaid for the purpose of obtaining or inducing the procurement of any  Agency Agreement or any Project Agreement or any contract, consent, approval, right, interest, privilege or other obligation or benefit related to any  Agency Agreement or the Project from the  Agency or any Government Authority.

## No Relief from Liability

    - No review, non-objection or approval by the  Agency, the Independent Engineer, the Independent Auditor or any Government Authority of any Concession Asset or Project Works (including any agreement, document, instrument, specifications or proposed by the Concessionaire) shall relieve the Concessionaire from any liability that it would otherwise have had for its negligence in the performance and completion of the Project Works and the Concession Assets (including preparation of an agreement, document, instrument, drawing, specification or design) or failure to comply with the Applicable Laws with respect thereto, or to satisfy the Concessionaire’s obligations under the  Agency Agreements, nor shall the  Agency, the Independent Engineer, the Independent Auditor or any Government Authority be liable to the Concessionaire or any other Person by reason of its review and approval of an agreement, document, instrument, drawing, specification, or design.

    - The Concessionaire shall, at all times, be responsible and liable for all its obligations under the Applicable Standards notwithstanding anything contained in the Project Agreements or any other agreement, and no default under any Project Agreement or other agreement shall excuse the Concessionaire from its obligations or liability hereunder.

## Without Prejudice

    - The representations, warranties, undertakings, obligations, roles and responsibilities of the Concessionaire set out in this Article 7 (Concessionaire’s Representations, Warranties and Certain Obligations & Undertakings) shall not limit or prejudice in any manner the representations, warranties, undertakings, obligations, roles and responsibilities of the Concessionaire set out elsewhere in the  Agency Agreements.

## Repetition of Representations and Warranties

    - The representations and warranties set out in this Section 7.1.1 are made as of the Effective Date and shall be deemed to be repeated by the Concessionaire on each of the Repetition Dates, in each case, with reference to the facts and circumstances then existing.

# Agency Representations, Warranties And Certain Obligations &Undertakings

## Agency Representations & Warranties

    - The  Agency hereby represents and warrants to the Concessionaire that:

## it has taken all necessary actions under the Applicable Laws to:

## (i) 	authorize the execution, delivery and performance of this Agreement; and

## (ii)	validly exercise its rights and perform its obligations under this Agreement;

## this Agreement and all obligations contained herein constitute its legal, valid and binding obligations, enforceable against it in accordance with the terms hereof;

## the execution, delivery and performance of this Agreement shall not conflict with, result in the breach of, constitute a default under, or accelerate performance required by any of the Applicable Laws or any covenant, contract, agreement, arrangement, understanding, decree or order to which it is a party or by which it or any of its properties or assets are bound or affected;

## there are no actions, arbitrations, litigations, suits, proceedings, or investigations pending or, to its best knowledge, threatened against it under the Applicable Laws before any court or before any other judicial, quasi-judicial or other authority, the outcome of which (i) could reasonably be expected to have a Material Adverse Effect; (ii) individually or in the aggregate may result in any material impairment of its ability to perform any of its obligations under this Agreement; (iii) may affect the legality, validity, or enforceability of this Agreement; or (iv) may otherwise result in a breach of this Agreement.

## it has no knowledge of any violation or default with respect to any Legal Requirements which may result in any Material Adverse Effect on its ability to perform its obligations under this Agreement and no fact or circumstance exists which may give rise to such proceedings that would adversely affect the performance of its material obligations under this Agreement; and

## it has complied with Applicable Laws in all material respects and has not been subject to any fines, penalties, injunctive relief or any other civil liabilities which in the aggregate have or may have a Material Adverse Effect.

## In the event that any occurrence or circumstance comes to the attention of either Party that renders any of its aforesaid representations or warranties untrue or incorrect, such Party shall immediately Notify the other Party of the same. Such Notification shall not have the effect of remedying any breach of the representation or warranty that has been found to be untrue or incorrect nor shall it adversely affect or waive any right, remedy or obligation of either Party under this Agreement or any  Agency Agreement.

## General Undertakings

    - The  Agency hereby undertakes to the Concessionaire that it shall:

- ensure peaceful use of the Project Site by the Concessionaire without any let or hindrance from the  Agency and/or any person or Government Authority claiming through or under them;

- procure police assistance and provide reasonable assistance to the Concessionaire in procuring police assistance for removal of trespassers, removal of encroachments and security on and/or in respect of the Project;

- upon written request of the Concessionaire, provide police support at and/or near the Project Site as required by the Conc essionaire; and

- support, cooperate with and facilitate the Concessionaire in the implementation of the Project in accordance with the provisions of the  Agency Agreements.

## Support For Concessionaire Permits & Conditions for Concessionaire Permits

    - Subject to the Concessionaire’s timely submission of reports required by Section 7.6.2, upon request of the Concessionaire, the  Agency shall support and use reasonable efforts to expedite consideration of the applications for the Concessionaire Permits or reissuance(s) thereof filed pursuant to Section 7.6 (Concessionaire Permits), and the timely issuance thereof or reissuance of a Concessionaire Permit subject to a Lapse of Consent by any Government Authority.  Any request for support under this Section shall be made by the Concessionaire and shall be accompanied with copies of the application for the Concessionaire Permit, any notice that the issuance or reissuance of the Concessionaire Permit was denied or deferred, and a statement of the efforts in obtaining the issuance or reissuance of the Concessionaire Permit to date.

    - The  Agency or any Government Authority may attach such “non- discriminatory” terms and conditions (as explained in Section 8.6 (Non-Discriminatory)) to the issuance or renewal of any of the Concessionaire Permits as are in accordance with the Applicable Laws and the attachment of such terms and conditions shall not in and of itself constitute a breach of this Agreement by the  Agency or a Permitted Event. The Concessionaire and its Contractors shall abide by all such terms and conditions (subject to this Section 8.3.2 and provisions in this Agreement relating to Change in Law and Lapse of Consent). If the Concessionaire (including where it is acting through its Contractors) fails to abide by any term or condition of any Concessionaire Permit, then the  Agency or any Government Authority may exercise any power pursuant to the Applicable Laws (provided such power is exercised in a “non-discriminatory” manner) in respect of such failure and (subject to this Section 8.3.2 and provisions in this Agreement relating to Change in Law and Lapse of Consent) such exercise shall not of itself constitute a breach of this Agreement by the  Agency or a Permitted Event; provided, however, that, with respect to all such Concessionaire Permits issued by the Agency or any Government Authority that is also a department or instrumentality of the  Agency, the Agency shall not, and the  Agency shall ensure that no such Government Authority shall, terminate prior to its expiration date or revoke any such Concessionaire Permit until the later of (a) thirty (30) days after delivery to the Concessionaire (or the relevant Contractor) of written notice by the  Agency or such department or instrumentality of the Agency of such failure and (b) the period of time, if any, that must expire under the Applicable Laws or the relevant Concessionaire Permit prior to early termination or revocation of any such Concessionaire Permit; provided, further, that nothing in this Section shall limit the Agencyor any Government Authority from taking any action in relation to a breach of, or non-compliance with, a Concessionaire Permit (other than termination or revocation) which it is entitled to take under the Applicable Laws (provided such action is taken in a “non-discriminatory” manner).

## Support for Obligations

    - Upon reasonable request by the Concessionaire, the  Agency shall use its reasonable efforts and its good offices to support the Concessionaire’s performance of its obligations under and pursuant to this Agreement, including, its obligations to develop, finance, insure, acquire, complete, commission, own, operate and maintain the Concession Assets. If the Concessionaire has failed to comply with its obligations under any Agency Agreement and such failure is the principal cause of the Concessionaire’s difficulties in performing such activities, the  Agency may advise the Concessionaire of such determination, and the Agency shall not be obligated to take any action to assist the Concessionaire until such time as the Concessionaire has fully complied with its obligations under the  Agency Agreements. By agreeing to use its reasonable efforts and its good offices to support the Concessionaire’s efforts, the  Agency has not relieved, and does not relieve in any way, the Concessionaire of its obligations or potential liability under the  Agency Agreements and the other documents comprising the Project Agreements.

## Procedure

    - To the extent permitted under the Applicable Laws, all applications and any other necessary requisites, whether for the Concessionaire, its employees or Contractors, are to be routed through the Concessionaire.

## Non-Discriminatory

    - The use of the term “non-discriminatory” or “discriminatory” in any Agency Agreement is not intended to prohibit or limit in any way the  Agency or any Government Authority from making rational distinctions between parties or from using measures, establishing conditions, or enforcing requirements that are, in each case, intended or designed to advance the purposes of the program being implemented by the  Agency or any Government Authority or of a Concessionaire Permit. It is intended, however, to prohibit the use of Government Authority, over Concessionaire Permits, for example, to deprive the Concessionaire of the benefits of the  Agency Agreements or any other Project Agreement by the application of a higher standard to the Concessionaire (alone, or together with others in a small class) than to others similarly situated because of, for example, its foreign ownership, or to gain commercial or political advantage.

## Powers of the Agency to charge and implement Fees & fines

    - The Concessionaire expressly agrees and undertakes that the Agency either directly or through the Concessionaire shall have an exclusive right to demand and implement additional fees, revenues (other than Revenues) and fines on the Project in accordance with Applicable Laws..

## AGENCY Representative

    - Unless already appointed prior to the Effective Date, the  Agency shall, within seven (7) days following the Effective Date, appoint its representative duly authorized to deal on its behalf to facilitate  all matters under or arising out of or relating to the  Agency Agreements (the Agency Representative). The Agency may, by notice in writing to the Concessionaire, substitute the  Agency Representative at its discretion at any time.

    - The  Agency Representative shall oversee the day to day implementation of the Project and facilitate implementation of the Project in accordance with the  Agency Agreements.

    - The function of the  Agency Representative shall be:

- to protect the interest of the  Agency by ensuring through monitoring and inspecting that the progress of  Development Works and OOperation and Maintenance, the supervision of which shall be carried out by the Independent Engineer, in accordance with this Agreement, according to the Applicable Laws, Project Requirements, Good Industry Practice and international standards;

- to oversee that the Concessionaire complies with all applicable safety standards in accordance with Good Industry Practice;

- coordinate and organize services to be provided by other agencies including public utility agencies andemergency services during the development of the Project Facilities; and

- clarify and resolve with the Concessionaire Authorized Representative, the Independent Engineer, the Independent Auditor any difficulties and disputes arising pursuant to this Agreement and manage any complaints by or against third parties.

## AGENCY Overriding Powers

    - Notwithstanding anything contained in this Agreement, the  Agency shall have the right upon the occurrence of a national emergency, civil commotion and/or as a consequence of a Force Majeure Event, to take over the performance of any or all the obligations of the Concessionaire to the extent deemed necessary by the  Agency or as directed by the relevant Government Authority, and exercise such control over the Concession Assets and/or give such directions to the Concessionaire as may be deemed necessary by the  Agency; provided, however, that the exercise of such overriding powers by the  Agency shall be of no greater scope and of no longer duration than is reasonably required in the circumstances which causes the exercise of such overriding power by the  Agency (the  Agency Overriding Power Event). The Concessionaire hereby agrees to act in accordance with the instructions issued by the  Agency pursuant to the provisions of this Section and undertakes to provide assistance and co-operation to the  Agency for performance of its obligations hereunder. In the event the  Agency exercises its overriding powers under this Section 8.9 ( Agency Overriding Powers) whereby the Concessionaire incurs any costs and expenses and/or is delayed in performance of its obligations under this Agreement, the Concessionaire shall be entitled to issuance of a Relief Order Request and in such case, the provisions of Article 15 (Relief Extensions & Relief Compensations) shall apply.

## Sovereign Immunity

    - The Agency unconditionally and irrevocably:

- agrees that the execution, delivery and performance by it of the  Agency Agreements and all other agreements, documents and writings relating to the same constitute private and commercial acts and not public or governmental acts;

- agrees that should any proceedings be brought against it or its assets (other than any of its assets which are significant in respect of national security of Pakistan (the Protected Assets)) in any jurisdiction in relation to the  Agency Agreements or any transaction contemplated by the  Agency Agreements, no immunity, sovereign or otherwise, from such proceedings, execution, attachment or other legal process shall be claimed by or on behalf of itself or with respect to any of its assets (other than the Protected Assets); and

- waives any such right of immunity, sovereign or otherwise, which the  Agency or its assets now has or may acquire in the future (other than the Protected Assets), in respect of proceedings under the  Agency Agreements.

## Without Prejudice

    - The representations, warranties, undertakings, obligations, roles and responsibilities of the  Agency set out in this Article 8 ( Agency Representations, Warranties and Certain Obligations & Undertakings) shall not limit or prejudice in any manner the representations, warranties, undertakings, obligations, roles and responsibilities of the Agency set out elsewhere in the  Agency Agreements.

## Project Management / Implementation Unit

    - The Project Management / Implementation Unit shall oversee day to day implementation of the Project in accordance with the  Agency Agreements.

## Agency Project Manager / Project Director

## Unless already appointed prior to the Effective Date, the  Agency shall, within seven (7) days following the Effective Date, appoint its representative duly authorized to deal on its behalf to facilitate  all matters under or arising out of or relating to the Agency Agreements (the Project Manager / Project Director). The  Agency may, by notice in writing to the Concessionaire, substitute the Project Manager at its discretion at any time. The  Agency shall ensure that at all times during the Concession Period, the Project Manager remains appointed.

## Repetition of Representations and Warranties

    - The representations and warranties set out in this Section 8.1.1 are made as of the Effective Date and shall be deemed to be repeated by the Agency on each of the Repetition Dates, in each case, with reference to the facts and circumstances then existing.

# Indemnities & Limitation of Liability

## General Indemnity

    - The Concessionaire

The Concessionaire shall indemnify and defend the Agency, for itself and its officers, directors and employees (the Agency Indemnified Persons) against, and hold the Agency Indemnified Persons harmless from, at all times after the Effective Date, any and all Losses incurred, suffered, sustained or required to be paid, directly or indirectly, by, or sought to be imposed upon, the Agency Indemnified Persons for personal injury or death to persons or damage to property arising out of any negligent or intentional act or omission by the Concessionaire in connection with this Agreement. Notwithstanding anything to the contrary contained in the preceding sentence, nothing in this Section 9.1.1 shall apply to any Loss in respect of and to the extent of which the Agency receives proceeds from insurance policies relating to the Project.

    - The Agency

Except as specifically provided elsewhere in this Agreement, the Agency shall indemnify and defend the Concessionaire, for itself and as trustee for its officers, directors and employees (the Concessionaire Indemnified Persons), against and hold the Concessionaire Indemnified Persons harmless from, at all times after the Effective Date, any and all Loss incurred, suffered, sustained or required to be paid, directly or indirectly, by, or sought to be imposed upon the Concessionaire Indemnified Persons for personal injury or death to persons or damage to property arising out of any negligent or intentional act or omission by the Agency in connection with this Agreement. Provided, however, that the Agency’s indemnification obligations under this Section 9.1.2 shall not apply to the extent that such Loss is: (i) attributable to the negligence, misconduct, or breach of this Agreement by the Concessionaire or any Concessionaire Engaged Person; (ii) exacerbated by the failure of the Concessionaire or any Concessionaire Engaged Person to take reasonable steps in mitigation; or (iii) recovered by the Concessionaire through proceeds from insurance policies or indemnification from another party relating to the Project.

    - Joint Negligence

In the event injury or damage results from the joint or concurrent negligent or intentional acts or omissions of the Parties (as determined by the Independent Engineer and the Independent Auditor), each Party shall be liable under this indemnification in proportion to its relative degree of fault, as determined by the Independent Engineer and the Independent Auditor.

    - Mitigation

Where a Party (the Indemnified Person) wishes to make a claim under this Agreement against the other Party (the Indemnifying Person), the Indemnified Person shall at all times take all reasonable steps to minimize and mitigate any Loss which it is entitled to bring a claim against the Indemnifying Person; provided that the Agency shall:

  - be permitted to have regard to its statutory duties and functions when mitigating such Loss; and

  - not be required to take steps that would cause the Agency to be in breach of any of its statutory functions and duties.

## Assertion of Claims to Exceed Minimum Indemnification Amount

9.2.1	Each Party shall be solely liable and shall not be entitled to assert any claim for indemnification under this Agreement, for any Loss that would otherwise be the subject of indemnification under this Agreement, until all Losses of such Party, in the aggregate, during the then-current accounting year or Accounting Year (as the case may be), exceed the Minimum Indemnification Amount. For the purposes of this Section 9.2 (Assertion of Claims to Exceed Minimum Indemnification Amount), a Loss (or claim for indemnification) shall be deemed to arise in the accounting year or Accounting Year (as the case may be) in which the event giving rise to such Loss (or claim for indemnification) occurred, or if the event is continuing in more than one (1) accounting year or Accounting Year (as the case may be), in the accounting year or Accounting Year (as the case may be) in which such event ends.

## Notice and Contest of Claims

    - In the event that either Indemnified Party receives a claim or demand from a third party in respect of which it is entitled to the benefit of an indemnity under this Article 9 (Indemnities & Limitation of Liability) (the Indemnified Party) it shall Notify the other Indemnifying Party (the Indemnifying Party) within twenty-one (21) days of receipt of the claim or demand and shall not settle or pay the claim without the prior approval of the Indemnifying Party, which approval shall not be unreasonably withheld, conditioned or delayed. In the event that the Indemnifying Party wishes to contest or dispute the claim or demand, it may conduct the proceedings in the name of the Indemnified Party, subject to the Indemnified Party being secured against any costs involved, to its reasonable satisfaction.

## Defense of Claims

    - The Indemnifying Party shall be entitled, at its option and expense and with counsel of its selection, to assume and control the defense of such claim, action, suit or proceeding, subject to the prior approval of the Indemnified Party; provided, however, it gives prompt notice of its intention to do so to the Indemnified Party, and reimburses the Indemnified Party for the reasonable costs and expenses incurred by the Indemnified Party prior to assumption by the Indemnifying Party of such defense.

    - The Indemnified Party shall be free to pay or settle any claim on such terms as it may think fit if, within twenty-eight (28) days of the notice under Section 9.3, the Indemnifying Party fails to notify the Agency of its intention to dispute the claim or assume control of the defense in accordance with Section 9.4.1. The Agency may at any time give notice to the Concessionaire that it is taking over the conduct of any defence, dispute, compromise or appeal of any claim. Upon such notice, the Concessionaire shall promptly transfer conduct of the claim to the Agency and provide all reasonable co-operation. If the Agency gives such notice, the Concessionaire shall be released from its indemnity in respect of that claim, except where the notice was given as a consequence of the Concessionaire's own failure to deal properly with the claim.

    - Unless and until the Indemnifying Party acknowledges in writing its obligation to indemnify the Indemnified Party and assumes control of the defense of a claim, suit, action or proceeding in accordance with Section 9.4.1, the Indemnified Party shall have the right, but not the obligation, to contest, defend and litigate, with counsel of its own selection, any claim, action, suit or proceeding by any third party, alleged or asserted against such Party in respect of, resulting from, related to or arising out of any matter for which it is entitled to be indemnified hereunder, and the reasonable costs and expense thereof shall be subject to the indemnification obligations of the Indemnifying Party hereunder.

    - Upon assumption by the Indemnifying Party of the control of the defense of a claim, suit, action or proceeding, the Indemnifying Party shall reimburse the Indemnified Party for the reasonable costs and expenses of the Indemnified Party in the defense of the claim, suit, action or proceeding prior to the Indemnifying Party’s acknowledgment of the Indemnification and assumption of the defense.

    - Following acknowledgment of the indemnification and assumption of the defense by the Indemnifying Party, the Indemnified Party shall have the right to employ its own counsel, and such counsel may participate in such action, but the fees and expenses of such counsel shall be at the expense of such Indemnified Party, when and as incurred, unless:

- the employment of counsel by such Indemnified Party has been authorized in writing by the Indemnifying Party; or

- the Indemnified Party shall have reasonably concluded that there may be a conflict of interest between the Indemnifying Party and the Indemnified Party in the conduct of the defense of such action; or

- the Indemnifying Party shall not, in fact, have employed independent counsel reasonably satisfactory to the Indemnified Party, to assume the defense of such action and shall have been so notified by the Indemnified Party; or

- the Indemnified Party shall have reasonably concluded and specifically Notified the Indemnifying Party either:

- that there may be specific defenses available to it which are different from or additional to those available to the Indemnifying Party; or

- that such claim, action, suit or proceeding involves or could have a Material Adverse Effect upon it beyond the scope of this Agreement.

Provided that if Sections 9.4.6, (b), (c) or (d) shall be applicable, then the counsel for the Indemnified Party shall have the right to direct the defense of such claim, demand, action, suit or proceeding on behalf of the Indemnified Party, and the reasonable fees and disbursements of such counsel shall constitute legal or other expenses hereunder.

## No Consequential Claims

    - Notwithstanding anything to the contrary contained in this Article 9 (Indemnities & Limitation of Liability), the indemnities herein provided shall not include any claim or recovery in respect of any cost, expense, loss or damage of an indirect, incidental or consequential nature, including loss of profit, except as expressly provided in this Agreement.

## Survival on Termination

    - The provisions of this Article 9 (Indemnities & Limitation of Liability) shall survive Termination for the duration of the Indemnity Survival Period, and the provisions of this Article 9 (Indemnities & Limitation of Liability) shall apply solely in respect of claims that arose immediately on or prior to the Termination Date.

## Limitation of Liability & Indemnification for Fines and Penalties

    - Neither Party shall be liable to the other Party in contract, tort, warranty, strict liability (except as may be expressly provided in any Agency Agreement), or any other legal theory for any indirect, consequential, incidental, punitive, or exemplary damages; provided, that the Parties hereby agree that the Termination Payment and Relief Costs payable under this Agreement are not indirect, consequential, incidental, punitive or exemplary damages. Neither Party shall have any liability to the other Party except pursuant to, or for breach of any Agency Agreement; provided, however, that this provision is not intended to constitute a waiver of any rights of one Party against the other with regard to matters unrelated to any Agency Agreement or to any activity not contemplated by the same.

    - Any fines or other penalties incurred by the Concessionaire for non-compliance with the Applicable Laws or other governmental directions issued pursuant thereto and in accordance therewith or the Concessionaire Permits shall not be reimbursed by the Agency or any Government Authority but shall be the sole responsibility of the Concessionaire.

# Equity And Funding Matters

10.1. The Parties acknowledge and agree that all matters pertaining to the Concessionaire’s capitalization, equity architecture, and the funding, subscription, and utilization of Equity shall be strictly governed by the provisions set forth in Schedule P (Equity Matters) and further, that any issuance, sale, transfer, Encumbrance, or disposal of the Sponsor Shares, including without limitation, any Change in Control, Change in Complete Control, or Change in Shareholding shall only be permitted in strict compliance with the parameters and restrictions established in Schedule X (Change In Control, Change In Complete Control And Change In Shareholding).

# Development Performance Security & O&M Performance Security

## Development Performance Security

    - Prior to the Effective Date, the Concessionaire has provided and delivered to the Agency the Development Performance Security. The Development Performance Security:

- has been issued and maintained without any recourse on the Concessionaire, its assets or properties;

- has not been secured through any Concession Assets and no Encumbrance of any nature has been created on the assets and properties of the Concessionaire in respect of the same.

All costs, expenses, fees and other charges of any nature, in each case, associated with the issuance, maintenance and encashment of the Development Performance Security are solely on account of the Sponsor.

    - The Development Performance Security shall secure:

- all of the Sponsor’s obligations, liabilities, payments, indemnities, representations, guarantees, warranties and responsibilities under the Agency Agreements to which it is a party; and

- all of the Concessionaire’s obligations, liabilities, payments, liquidated damages, indemnities, representations, guarantees, warranties and responsibilities under the Agency Agreements, including the integrity and quality of the Concessionaire’s and its Contractors’ workmanship, the timely and continuous performance of the Project Works, the quality and quantity of  any equipment, materials, items and components supplied, the performance of Project Works (including the Preliminary Works) by the Concessionaire and compliance of the same with the Applicable Standards and all other works and services to be provided by the Concessionaire under the Agency Agreements.

    - The Development Performance Security came into force and became effective upon issuance and delivery of the same to the Agency.

    - The Concessionaire shall maintain the Development Performance Security in full force and effect until the Development Performance Security Expiry Date. In the event, at any time during the Concession Period:

- the issuer of the Development Performance Security is downgraded below the Minimum Credit Rating and is not replaced with a security meeting the requirements of this Agreement within thirty (30) days of such downgrade; and

- the Development Performance Security is scheduled to expire prior to the Development Performance Security Expiry Date and the Concessionaire fails to extend or replace such security at least forty-five (45) days prior to its scheduled expiry;

then the Agency shall be entitled to encash the Development Performance Security to its full outstanding value. The proceeds of any encashment under Section 11.1.5 shall be deposited into a designated bank account controlled by the Agency (the Cash Collateral Account). The funds in the Cash Collateral Account shall be held by the Agency strictly as cash collateral in lieu of the Development Performance Security, subject to the following: (a) the Agency shall be entitled to draw upon the Cash Collateral Account solely upon the occurrence of the encashment triggers set out in Section 11.1.5; and (b) upon the provision of a valid replacement Development Performance Security, as confirmed by the Independent Auditor, the Agency shall, within five (5) business days, refund the unutilized balance of the Cash Collateral Account to the Concessionaire.

    - The Agency shall have the right to encash the Development Performance Security upon the occurrence of, without limitation, the following:

  - failure to comply with any obligation under this Agreement in connection with the Development Works, not remedied within thirty (30) days of written notice;

  - for the reasons given in Section 18.2.3;

  - accrued and unpaid Development Period Damages and/or any amount due and payable by the Concessionaire to the Agency, as certified by the Independent Auditor; and

  - lapse or non-renewal of Development Period Insurances.

    - The Development Performance Security shall be encashable in accordance with the terms thereof and shall be payable on the Agency’s first written demand without any prior notice, reference or recourse to the Concessionaire, the Sponsors or any other entity.

    - The Concessionaire shall be obligated to adjust the Development Performance Security from time to time to reflect any amounts payable by the Agency pursuant to Article 16 (Change of Scope), such increase being an amount equal to two percent (2%) of the amounts payable to the Concessionaire from time to time in accordance with Article 16 (Change of Scope). In addition, the Development Performance Security shall be adjusted, as a condition precedent to issuance of the Project Development Completion Certificate, prior to the Project Development Completion Date so that it is equal in value to two percent (2%) of the Total Project Cost less the aggregate of any encashments made by the Agency prior to the date of adjustment.

    - Upon determination by the Independent Engineer that the Substantial Completion Criteria have been satisfied and that the Development Performance Security Expiry Date has occurred, the Independent Engineer shall issue a certificate evidencing the occurrence of the Development Performance Security Expiry Date (the Development Performance Security Expiry Certificate). Upon issuance of the Development Performance Security Expiry Certificate, the Development Performance Security shall be null and void and shall be returned to the Concessionaire by the Agency within ten (10) Business Days of receipt by the Agency of the Development Performance Security Expiry Certificate; provided, however, that the Agency shall be entitled to retain, from the proceeds of the Development Performance Security (or, if not previously encashed, to encash and retain that portion of the Development Performance Security), an amount corresponding to any claims that are disputed bona fide by the Agency against the Concessionaire as at the date of the Development Performance Security Expiry Certificate, which retained amount shall be held by the Agency and applied or released in accordance with the resolution of such dispute pursuant to Article 30 (Dispute Resolution).

## O&M Performance Security

    - The Concessionaire hereby undertakes to procure issuance and delivery to the Agency of the O&M Performance Security from time to time in accordance with this Section 11.2 (O&M Performance Security).

    - The Concessionaire shall deliver the O&M Performance Security to the Agency at least ninety (90) days prior to the Development Performance Security Expiry Date. Following the Development Performance Security Expiry Date, and until the Trigger Date, the Concessionaire shall replace the O&M Performance Security thirty (30) days prior to commencement of each Operational Year. Each O&M Performance Security shall become effective simultaneously upon issuance.

    - The O&M Performance Security:

- shall be issued and maintained without any recourse on the Concessionaire, its assets or properties;

- shall not be secured through any Concession Assets and no Encumbrance of any nature shall be created on the assets and properties of the Concessionaire in respect of the same.

All costs, expenses, fees and other charges of any nature, in each case, associated with the issuance, maintenance and encashment of the O&M Performance Security are solely on account of the Sponsors.

    - The O&M Performance Security shall secure:

- all of the Sponsor’s obligations, liabilities, payments, indemnities, representations, guarantees, warranties and responsibilities under the Agency Agreements to which it is a party; and

- all of the Concessionaire’s obligations, liabilities, payments, liquidated damages, indemnities, representations, guarantees, warranties and responsibilities under the Agency Agreements, including the integrity and quality of the Concessionaire’s and its Contractors’ workmanship, the timely and continuous performance of the Project Works during the Operations Period, the quality and quantity of any equipment, materials, items and components supplied, the performance of Project Works during the Operations Period by the Concessionaire and compliance of the same with the Applicable Standards and all other works and services to be provided by the Concessionaire under the Agency Agreements.

    - The O&M Performance Security shall be encashable in accordance with the terms thereof and shall be payable on the Agency’s first written demand without any prior notice, reference or recourse to the Concessionaire, the Sponsors or any other entity.

    - The O&M Performance Security provided by the Concessionaire in respect of an Operational Year shall remain in force and effect until the date that falls on the expiry of such Operational Year subject to receipt by the Agency of a fully valid and effective O&M Performance Security for the subsequent Operational Year in accordance with the terms of this Agreement on or prior to such date (the O&M Performance Security Expiry Date). In the event an O&M Performance Security is to expire prior to the O&M Performance Security Expiry Date, the Concessionaire shall extend the validity of the O&M Performance Security, at least fifteen (15) Business Days prior to its expiry, so as to keep it valid and enforceable until the O&M Performance Security Expiry Date. In the event of failure by the Concessionaire to keep valid or extend the validity of any O&M Performance Security in accordance with this Section 11.2.6, the Agency shall have the right to encash such O&M Performance Security at any time prior to its expiry to its full outstanding value.

    - Upon the delivery and commencement of an O&M Performance Security for an Operational Year (the New O&M Performance Security) to the Agency by the Concessionaire in accordance with this Section 11.2 (O&M Performance Security) on or prior to the commencement of such Operational Year, the previous O&M Performance Security issued for the previous Operational Year shall be null and void and shall be returned to the Concessionaire by the Agency simultaneously with the provision of the New O&M Performance Security.

    - Notwithstanding anything to the contrary, the Concessionaire hereby undertakes and agrees that the O&M Performance Security shall remain valid:

- in case of Termination, at least for one (1) year after the Termination Notice has been issued;

- in case of expiry of this Agreement on the Final Expiry Date, one (1) year after the Final Expiry Date.

# Financing Matters

12.1.    The Parties acknowledge and agree that all matters pertaining to debt financing for the Project, including without limitation to the achievement of Financial Close, the submission and review of the Financing Term Sheet, the execution and amendment of Financing Documents, the rights and step-in mechanisms afforded to the Financiers, and all consequential modifications to the rights and obligations of the Parties under this Agreement shall be strictly governed by and subject to the provisions, conditions, and parameters set forth in Schedule L (Financing Matters).

# Development Works

## Development Works

    - The Concessionaire shall commence the Development Works on the Commencement Date and shall perform and complete the same in accordance with the  Development Time for Completion.  The Concessionaire shall achieve each Project Development Milestone on or prior to its respective Project Development Milestone Date. All Preliminary Works forming part of Development Works (if any) shall commence in accordance with the mutual agreement between the Parties. The Concessionaire shall immediately upon commencement of the Development Works Notify the Agency, the Independent Engineer and the Independent Auditor of the same.

    - Without limiting the provisions of Section 13.1.1, the Concessionaire shall be specifically responsible for the performance and compliance of the  Development Works with the Development Requirements.

    - The Concessionaire shall perform the Development Works either itself, or through the Development Contractor(s) appointed in accordance with the terms of this Agreement; provided, however, the Concessionaire shall remain solely responsible and liable for performance (within Development Time For Completion) and compliance of the Development Requirements with the Applicable Standards irrespective of whether the Development Works are undertaken by the Concessionaire or the Development Contractor(s).

## Development Programme

    - Within two (2) days following the execution of the Independent Engineer Contract, the Concessionaire shall submit to the Independent Engineer, a proposed program, to be prepared in compliance with the Applicable Standards and Good Industry Practice, for performance of the Development Works and achievement of each Project Development Milestone (the Proposed Development Programme). The Proposed Development Programme shall not amend or vary the timelines for achievement of the Project Development Milestones set out in the Project Development Completion Schedule. The Proposed Development Programme shall include, without restriction, the following:

- the Project Development Milestones to be achieved and the respective Project Development Milestone Dates for each of the same;

- the detailed order in which the Development Works shall be performed, together with timelines for performance of the same;

- arrangements and procedures for carrying out the Development Works;

- the timelines, intervals and procedures for conducting the inspection of all elements of the Development Works and any completed Concession Assets;

- arrangements and procedures for conducting safety related measures in relation to the Development Works; and

- all major events and activities in the preparation of the  Development Progress Reports and submission of the same to the Agency, the Independent Engineer and/or the Independent Auditor (as applicable) for the review and approval (as applicable).

    - Within fourteen (14) days of the receipt of the Proposed Development Programme by the Independent Engineer, the Independent Engineer shall finalize its comments on the same and shall ensure the incorporation of its comments and submit the same to the Agency. The Agency shall prior to granting its approval in respect of the Proposed Development Programme, within fifteen (15) days of the Independent Engineer’s request for the same, revert to the Independent Engineer in respect of any observations and comments that it may have, if any; provided, however, that the approval of the Proposed  Development Programme shall be granted by the Agency within fifteen (15) days of the Independent Engineer’s request for such approval if the Proposed  Development Programme is recommended by the Independent Engineer for approval after addressing any comments and observations of the Agency on the same. The Proposed Development Programme, as approved by the Agency on the Independent Engineer’s recommendation, shall be binding on the Parties (the Development Programme); provided, however, that the  Development Programme may be amended from time to time by the mutual agreement between the Parties and the Independent Engineer.

    - The Concessionaire shall, whenever required by the Agency, the Independent Engineer and/or the Independent Auditor, provide in writing, a general description of the arrangements and methods which the Concessionaire proposes to adopt for the execution of the Development Works. Any alteration to such arrangements and methods shall be made by the Concessionaire with prior written consent of the Independent Engineer and the Agency.

    - Any reports (including the  Development Progress Reports) submitted by the Concessionaire and covering the execution of the Development Works shall emphasize any delays in the  Development Time for Completion.

## Development Tests

    - The Concessionaire shall conduct or procure to be conducted such tests, as specified in Schedule G (Completion Tests Matters) in order to determine whether the Development Works conform to the Applicable Standards (the Development Tests). The Development Tests shall be conducted at such time and frequency and in such manner as may be specified by the Independent Engineer.

    - The Concessionaire hereby undertakes to conduct the Development Tests under the supervision of the Independent Engineer and in accordance with the Applicable Standards at its own cost and expense, provided, however, in the event during the Development Period the Agency determines that the Development Works are not in accordance with the Development Requirements then the Agency shall conduct separate tests to determine the quality of the  Development Works. In the event it is determined that the Development Works are not in accordance with the Development Requirements (as determined by the Independent Engineer) the Concessionaire shall repair the same and the cost of such tests shall be borne by the Concessionaire provided, however, in the event it is determined that the Development Works are in accordance with the  Development Requirements (as determined by the Independent Engineer), the cost of such tests shall be borne by the Agency.

    - The Concessionaire hereby undertakes to carry out, at its sole cost, the necessary remedial measures required to rectify the Defects & Deficiencies in the Development Works and/or the Concession Assets that are identified in the  Development Tests and to ensure that as a consequence of such remedial measures the Development Works and the Concession Assets conform to the Applicable Standards. The Concessionaire further undertakes that the remedial measures required to be undertaken by the Concessionaire pursuant to this Section 13.3.3 shall be repeated by the Concessionaire at its sole cost until such time as the Development Works and the Concession Assets conform to the Applicable Standards as verified by the Independent Engineer. In the afore-stated circumstances, the Independent Engineer may require the Concessionaire to conduct additional tests to determine whether the Defects & Deficiencies are rectified and in such case the costs of such additional tests shall be borne by the Concessionaire.

    - The Concessionaire shall maintain proper record of the  Development Tests and the remedial measures taken to cure the Defects & Deficiencies, if any, indicated by the Development Test results.

    - Results of all Development Tests shall be jointly recorded by the Independent Engineer, the Concessionaire and the Development Contractor.

## Development Progress Reports

    - Commencing from the Effective Date and until issuance of the Project Development Completion Certificate, the Concessionaire shall, furnish to the Agency, the Agency Representative, the Independent Auditor and the Independent Engineer a report in accordance with each Development Progress Reporting Timeline (the Development Progress Report) stating in reasonable detail the status and condition of the  Development Works and the Concession Assets including its compliance or otherwise with the Applicable Standards and shall promptly give such other relevant information as may be required by the Independent Engineer, the Independent Auditor and/or and the Agency. In particular, the Development Progress Report shall separately identify and state in reasonable detail the Defects & Deficiencies in the Development Works and/or the Concession Assets that require rectification and any delays in the Development Time for Completion. The Development Progress Report shall also expressly highlight all Defects & Deficiencies in the Development Works and/or the Concession Assets identified by the Independent Engineer in its  Development Inspection Report and shall set out all actions taken, and arrangements made by the Concessionaire for remedying the same.

    - Each Development Progress Report shall be updated by the Concessionaire based on any observations and comments made by the Independent Engineer and/or the Agency and shall be provided again to each of the Agency and the Independent Engineer until such time that it is approved by the Independent Engineer; provided that the Independent Engineer shall not accord its approval of the  Development Progress Report until it is satisfied that all reasonable comments and observations of the Agency on the  Development Progress Report are addressed.

    - The Development Progress Report shall be in the form approved by the Independent Engineer from time to time.

## Development Inspection Report

    - Commencing from the appointment of the Independent Engineer and until the issuance of the Project Development Completion Certificate, the Concessionaire shall procure that the Independent Engineer inspects the Development Works and the Concession Assets at least once a month and shall make all arrangements for the same.

    - The Independent Engineer shall make a report of such inspection (the Development Inspection Report) stating in reasonable detail the Defects & Deficiencies, if any, in the Development Works and/or the Concession Assets with particular reference to the Applicable Standards.

    - The Independent Engineer shall, within ten (10) days of commencement of a month, provide a copy of the Development Inspection Report to the Concessionaire and the Agency.

    - The Concessionaire hereby undertakes that, within fifteen (15) days from receipt of the Development Inspection Report, it shall rectify and remedy the Defects & Deficiencies, if any, stated in the Development Inspection Report, at its own cost and expense.

    - The inspection or submission of the  Development Inspection Report by the Independent Engineer shall not relieve or absolve the Concessionaire of its obligations and liabilities hereunder in any manner whatsoever.

## Delays During Development

    - [In the event the Concessionaire fails to achieve any Project Development Milestone or the Independent Engineer shall have reasonably determined that the rate of progress of Development Works is such that the Project cannot achieve Project Development Completion on or before the Scheduled Project Development Completion Date then the Independent Engineer shall issue a notice to the Concessionaire to this effect and the Concessionaire shall, within seven (7) days of such notice, inform the Independent Engineer in reasonable detail about the steps the Concessionaire proposes to undertake to expedite progress and the period within which it shall achieve the Project Development Completion by the Scheduled Project Development Completion Date and the Substantial Completion by the Scheduled Substantial Completion Date.]

# Completion

## Completion Tests

    - At least thirty (30) days prior to the expected Commercial Operations Date, the Concessionaire shall issue a notice to the Agency and the Independent Engineer (the Completion Tests Date Notice) fixing a date and time for performance of the Completion Tests (the Proposed Completion Tests Date).

    - The Proposed Completion Tests Date proposed by the Concessionaire shall be final for the conducting of the Completion Tests; provided, however, in the event the Proposed Completion Tests Date is unacceptable to the Independent Engineer and/or the Agency, the Concessionaire, the Agency and the Independent Engineer shall meet within seven (7) days of the Agency and Independent Engineer’s receipt of the Completion Tests Date Notice with an aim to mutually agree on an alternative date and time for performance of the Completion Tests, which date shall be no later than ten (10) days from the Proposed Completion Tests Date. If the Parties are unable to mutually agree on an alternative date and time for performance of the Completion Tests, the Concessionaire shall be entitled (with prior Notification to the Independent Engineer and the Agency) to carry out the Completion Tests on or after the tenth (10th) day from the Proposed Completion Tests Date.

    - Subject to the terms of this Agreement, in the event any Completion Tests are to be repeated due to reasons not attributable to the Agency, as determined by the Independent Engineer, such Completion Tests shall be repeated on account of the Concessionaire.

    - The Completion Tests shall be attended by the Agency Representative and such other representatives of the Agency as the Agency may nominate in writing, subject to Notification of the same to the Concessionaire and the Independent Engineer.

    - The conduct of the Completion Tests, the allocation of responsibility between the Independent Engineer and the Concessionaire for the performance of the same, and the materials, equipment and support to be provided in connection therewith, shall be as set out in Schedule G (Completion Tests Matters).

    - The Completion Tests shall be completed within the timeline specified in Schedule G (Completion Tests Matters).

## Scheduled Substantial Completion Date

    - The Concessionaire hereby guarantees that the Substantial Completion shall be achieved in accordance with the provisions of the Applicable Standards and that the Substantial Completion Date shall occur on or before the Scheduled Substantial Completion Date.

## Substantial Completion Certificate

    - The Completion Tests shall be conducted in accordance with the provisions of Section 14.1 (Completion Tests) and Schedule G (Completion Tests Matters).

    - The Independent Engineer shall, at the request of the Concessionaire, issue a Substantial Completion Certificate if the Completion Tests applicable to the Substantial Completion are successful though certain works or things forming part thereof are outstanding and not yet complete. In such an event, the Substantial Completion Certificate shall have appended thereto a list of outstanding items signed jointly by the Independent Engineer and the Concessionaire (the Completion Check List); provided, that the Independent Engineer shall not withhold the Substantial Completion Certificate for reason of any work remaining incomplete if the delay in completion thereof is attributable to the Agency (as determined by the Independent Engineer). The Independent Engineer shall set out the date in the Substantial Completion Certificate on which the Completion Tests applicable to the Substantial Completion are successfully passed (the Substantial Completion Date) and Substantial Completion is achieved.

    - The Parties hereto expressly agree that a Substantial Completion Certificate under this Section shall, upon request of the Concessionaire to this effect, be issued by the Independent Engineer, once the Substantial Completion Criteria have been satisfied (the Substantial Completion). Upon issuance of such Substantial Completion Certificate in terms of this Section 14.3.3, the Substantial Completion shall be achieved.

## Completion Check List & Failure to Achieve Substantial Completion

    - Notwithstanding that the Substantial Completion Certificate shall be signed by the Independent Engineer, the Completion Check List shall be jointly signed by the Independent Engineer and the Concessionaire as a confirmation of the outstanding works, actions and things required to be completed by the Concessionaire in line with the relevant Project Requirements (the Completion Check List Items).

    - The Concessionaire undertakes to complete all Completion Check List Items by the date determined by the Independent Engineer and set out in the Substantial Completion Certificate (the Scheduled Project Development Completion Date); provided, however, the Parties agree that the Scheduled Project Development Completion Date shall not be determined by the Independent Engineer to fall on any date that falls ninety (90) days following the Substantial Completion Date.

    - The Concessionaire shall be liable for payment of Development Period Damages to the Agency in the event the Concessionaire fails to achieve Substantial Completion on or prior to the Scheduled Substantial Completion Date. In the event the Concessionaire fails to achieve Substantial Completion within a period of one hundred and twenty (120) days from the Scheduled Substantial Completion Date, then such failure of the Concessionaire shall constitute a Concessionaire Event of Default, and the Agency may, at its sole discretion and without prejudice to its other rights and remedies available under the Agency Agreements, terminate this Agreement in accordance with Article 23 (Termination).

## Development Period Damages

    - In the event the Concessionaire fails to achieve Substantial Completion by the Scheduled Substantial Completion Date, then the Concessionaire shall pay to the Agency damages in case of delay in achieving Substantial Completion, amounting to the Daily Development Period Damages per day of delay in achievement of Substantial Completion (the Development Period Damages); provided that such Development Period Damages shall not exceed, in aggregate, the Development Period Damages Cap.

    - All Development Period Damages becoming due and payable by the Concessionaire in terms of this Section 14.5 (Development Period Damages) shall be invoiced by the Agency to the Concessionaire and shall become due and payable on the date falling thirty (30) days following the Concessionaire’s receipt of such invoice (the Development Period Damages Payment Date). In the event of failure by the Concessionaire to pay the Development Period Damages to the Agency by the Development Period Damages Payment Date, the Agency shall have the right to encash the Development Performance Security in an amount equal to the Development Period Damages. Notwithstanding anything contained herein, the recovery of Development Period Damages under this Section 14.5.2 shall be without prejudice to the rights of the Agency under the Agency Agreements (including the right of Termination in accordance with Section 14.3.3).

    - The Parties agree that it is entirely possible to predetermine the actual loss that may be suffered by the Agency and the amounts of Development Period Damages provided under this Section 14.5 (Development Period Damages) are not by way of a fine or penalty and constitute the actual loss suffered by the Agency.

## Project Development Completion Certificate

## Within ninety (90) days from the date of issuance of the Substantial Completion Certificate, the Independent Engineer shall issue a certificate certifying that the Project has achieved Project Development Completion (the Project Development Completion Certificate); provided, however, the Project Development Completion Certificate may be issued only upon the confirmation by the Independent Engineer that the Completion Check List Items have been completed in accordance with the Applicable Standards.

## Project Development Completion Date

## The Project shall be deemed to achieve project development completion (the Project Development Completion) on the date of issuance of the Project Development Completion Certificate (the Project Development Completion Date).

## For the avoidance of doubt, the Parties hereby agree that in the event the Substantial Completion Certificate is issued prior to the Scheduled Substantial Completion Date, the Concession Period shall remain the same.

## Scheduled Project Development Completion Date

## Subject to the terms of this Agreement, the Concessionaire hereby guarantees that the Project Development Completion Date shall be achieved in accordance with the provisions of this Agreement and that the Project Development Completion Date shall occur on or before the Scheduled Project Development Completion Date.

# Relief Extensions & Relief Compensations

## Relief Events

    - The Concessionaire shall only be entitled to initiate a request to the Independent Engineer and the Independent Auditor (the Relief Order Request) for issuance of a Relief Order relating to, as applicable, an extension of the Time For Completion and/or payment of Relief Costs by the Agency in the event of occurrence of the following events and circumstances as certified by the Independent Engineer (the Relief Events):

- a Material Adverse Impediment; provided, that the Concessionaire shall be entitled to only an extension in Time for Completion for any delays and to Relief Costs that, in each case, directly result from the Material Adverse Impediment and as are determined by the Independent Engineer and Independent Auditor in the Relief Order;

- a Political Event; provided, that the Concessionaire shall be entitled to only an extension in Time for Completion for any delays and to Relief Costs that, in each case, directly result from the Political Event and as are determined by the Independent Engineer and Independent Auditor in the Relief Order;

- an Emergency Decommissioning directly resulting from an Agency Event of Default or a Political Event; provided, that the Concessionaire shall be entitled to only an extension in Time for Completion for any delays and to Relief Costs that, in each case, directly result from Emergency Decommissioning caused by a Political Event and as are determined by the Independent Engineer and the Independent Auditor in the Relief Order;

- the occurrence of the circumstances set out in Section 4.9 (Geological and Archaeological Finds) causing a delay in the performance of the Concessionaire’s obligations under this Agreement; provided, that the Concessionaire shall be entitled to only an extension in Time For Completion for any delays and to Relief Costs that, in each case, directly result from the occurrence of the circumstances set out in Section 4.9 (Geological and Archaeological Finds) and as are determined by the Independent Engineer and the Independent Auditor in the Relief Order;

- the occurrence of the Agency Overriding Power Event; provided, that the Concessionaire shall be entitled to only an extension in Time for Completion for any delays and to Relief Costs that, in each case, directly result from the Ageny Overriding Power Event and as are determined by the Independent Engineer and the Independent Auditor in the Relief Order;

- a Non-Political Event; provided, that the Concessionaire shall be entitled to only an extension in Time for Completion for any delays that directly result from the Non-Political Event and as are determined by the Independent Engineer and Independent Auditor in the Relief Order;

- a delay by the Agency in providing the Vacant Possession of the Project Site in accordance with the terms of this Agreement; provided, that the Concessionaire shall be entitled to an extension in Time for Completion for any delays and to Relief Costs that, in each case, directly result from such delay in providing Vacant Possession and as are determined by the Independent Engineer and Independent Auditor in the Relief Order;

- a delay caused as a result of Suspension, provided that such Suspension is caused due to a Permitted Event; the Concessionaire shall be entitled to an extension in Time for Completion for any delays that directly result from such delay due to Suspension, as determined by the Independent Engineer and the Independent Auditor in the Relief Order; and

- an act of delay, impediment or prevention by the Agency  or  any other governmental entity, agency, or authority or a material breach by the Agency of any of its obligations under this Agreement or any other Project Agreement to which it is a party; provided, that the Concessionaire shall be entitled to Relief Costs only for any delays that directly result from the [•] and as are determined by the Independent Engineer and the Independent Auditor in the Relief Order.

    - If due to the occurrence of a Relief Event the Concessionaire is entitled to initiate a Relief Order Request, the Concessionaire shall prepare and deliver to the Independent Engineer and the Independent Auditor (with a copy to the Agency) a Relief Order Request, together with the Relief Order Proposal that is prepared in accordance with and is subject to Section 15.3 (Relief Order Procedure) and, if applicable, Section 15.4 (Additional Requirements For Relief Orders Relating To Extension Of Time For Completion). Each Relief Order Request prepared in accordance with Section 15.3 (Relief Order Procedure) and, if applicable, Section 15.4 (Additional Requirements for Relief Orders Relating to Extension of Time for Completion) shall specifically set out in detail the events and circumstances constituting the Relief Event, together with all supporting satisfactory documentary evidence relating thereto.

    - Following submission to the Independent Engineer and the Independent Auditor of a Relief Order Request pursuant to Section 15.1.2, the Independent Engineer and the Independent Auditor shall proceed in accordance with Section 15.3 (Relief Order Procedure) and Section 15.4 (Additional Requirements for Relief Orders Relating to Extension of Time for Completion).

    - Notwithstanding anything to the contrary, the Parties agree that the Concessionaire shall not be entitled to any extensions of Time For Completion and/or Relief Costs, as applicable, due to occurrence of a Relief Event, until such time the same is determined by the Independent Engineer and the Independent Auditor and set out in the Relief Order issued by the same in accordance with this Agreement, provided further, that the Independent Engineer certifies that the Concessionaire has no space for parallel or alternate sequencing of works available for carrying out its obligations within the prescribed timelines and until the Concessionaire has proved to have made all its efforts to avoid such Relief Event according to Good Industry Practice.

## Distinction Between Relief Costs And Force Majeure Costs

## For the avoidance of doubt, while Force Majeure Events (including Political Events and Non-Political Events) are classified as Relief Events for the purposes of procedure, notices, and extensions of Time for Completion under this Article 15, any Force Majeure Costs arising from a Force Majeure Event shall be strictly governed by, and allocated between the Parties in accordance with, Section 21.4 (Allocation of Costs Arising out of Force Majeure).

## Relief Order Procedure

    - In the event the Concessionaire submits a Relief Order Request to the Independent Engineer and the Independent Auditor (with a copy to the Agency) pursuant to Section 15.1 (Relief Events) then prior to the Independent Auditor and the Independent Engineer issuing a Relief Order, the Concessionaire shall prepare and submit to the Independent Auditor and the Independent Engineer (with a copy to the Agency), as soon as practicable, a detailed proposal (the Relief Order Proposal) containing:

- a description of the proposed work to be performed and a detailed programme for its execution;

- the Concessionaire's proposal for any necessary modifications to the  Development Programme and/or the O&M Programme, as applicable;

- the Concessionaire’s proposal for any Relief Costs and any adjustments to Time for Completion and/or any Project Milestone Date, accompanied by detailed pricing and documentary evidence;

- a statement whether and the extent to which, in Concessionaire’s opinion, the proposals contained in the Relief Proposal would, notwithstanding the exercise of all due skill and care, result in defective Project Works or prevent the Concessionaire from performing its obligations under the Agreement, including defects liability,

provided, however, each Relief Order Request and Relief Order Proposal submitted by the Concessionaire that proposes an extension to Time for Completion or any Project Milestone Date for a Project Milestone shall be additionally subject to the provisions and requirements of Section 15.4 (Additional Requirements for Relief Orders Relating to Extension of Time For Completion);

provided, further, however, in the event of submission of any Relief Order Request and a Relief Order Proposal, the Concessionaire shall provide such additional information as the Agency, the Independent Engineer and/or the Independent Auditor may reasonably request; and

provided, further, however, the Concessionaire shall keep and maintain such contemporary records (as may be necessary to substantiate any proposals contained in the Relief Order Proposal and/or the Relief Order Request) as may reasonably be requested by the Independent Engineer, the Independent Auditor and/or the Agency and the Concessionaire shall permit the Independent Engineer, the Independent Auditor and/or the  Agency to inspect all such records and shall provide the same to the Agency Representative with copies as required.

    - The Parties agree that compliance by the Concessionaire with the provisions of this Article 15 (Relief Extensions & Relief Compensations) shall be a condition precedent to the issuance of a Relief Order by the Independent Engineer and the Independent Auditor, unless waived in writing by the Agency. Further, notwithstanding anything to the contrary contained herein:

- if the Project Works (or any part thereof) are not in accordance with this Agreement, any rectification in that respect undertaken by the Concessionaire shall not entitle the Concessionaire to issuance of a Relief Order;

- the Concessionaire is expressly precluded from any extension of the Time for Completion and any extension of a Project Milestone Date for Project Milestone or to payment of any Relief Costs due to delays resulting from any act or omission of the Concessionaire and/or the Concessionaire Engaged Persons;

- the Concessionaire shall not be entitled to any extensions of the Time for Completion for any delays or failure to perform and hence shall not be entitled to Relief Costs or to initiate Relief Order Request for issuance of a Relief Order to the extent the Concessionaire is, in any case, in delay of performance of its obligations under the Agreement.

    - Following receipt by the Independent Engineer and the Independent Auditor from the Concessionaire of the Relief Order Proposal and the Relief Order Request, the Independent Engineer and the Independent Auditor shall review the Concessionaire’s proposals contained in the Relief Order Proposal and the Relief Order Request, for the purpose of determining:

- the occurrence and subsistence of the Relief Event and the Concessionaire’s entitlement to issuance of the Relief Order Request;

- whether to proceed with the proposals submitted by the Concessionaire in its submitted Relief Order Proposal;

- (if applicable) any amendments or modifications to the estimates and proposals submitted by the Concessionaire in the Relief Order Proposal;

- other matters set forth in the Relief Order Proposal and the Relief Order Request including determination of extension of Time for Completion and Relief Costs; and

- any other matters considered necessary by the Independent Engineer and the Independent Auditor for the purposes of issuance of the Relief Order.

    - Following the Independent Engineer and the Independent Auditor’s determination of matters set out in Section 15.3.3 (together with any other matters relating to their evaluation for the issuance of a Relief Order), the Independent Engineer and the Independent Auditor shall either amend, approve or disapprove in writing the Concessionaire’s submitted proposals contained in the Relief Order Proposal and the Relief Order Request within twenty-one (21) days following receipt by the Independent Engineer and the Independent Auditor from the Concessionaire of the Relief Order Proposal and the Relief Order Request. If the Independent Engineer and the Independent Auditor amend, modify or reject the Relief Order Proposal and the Relief Order Request, in each case, submitted by the Concessionaire, the Concessionaire shall submit a revised Relief Order Proposal and Relief Order Request taking into account the amendments, modifications and comments on the same made by the Independent Engineer and the Independent Auditor, which shall be subject to approval by the Independent Engineer and the Independent Auditor within twenty-one (21) days of submission of the revised Relief Order Proposal and the Relief Order Request. In the event of the Independent Engineer and the Independent Auditor’s approval of the Relief Order Proposal and the Relief Order Request or, if applicable, a revision of the same approved by the Independent Engineer and the Independent Auditor, it is agreed that the Independent Engineer and the Independent Auditor shall jointly issue a written order of Relief Order to the Agency and the Concessionaire simultaneously. All extensions in Time For Completion and in any Project Milestone Date for achievement of a Project Milestone and all Relief Costs, as applicable, shall be expressly set out in the Relief Order and shall be (subject to Section 15.5) binding on the Parties; provided, however, that such extensions in Time For Completion and in any Project Milestone Date for achievement of a Project Milestone and the Relief Costs set in the Relief Order shall not be in excess of the Concessionaire’s request under the Relief Order Proposal and the Relief Order Request; provided, further, that any Relief Costs shall be paid by the Agency to the Concessionaire within forty-five (45) days of receipt of the Relief Order by the Agency.

    - Notwithstanding anything to the contrary, in the event of occurrence of a Relief Event (excluding a Non-Political Event and an Emergency Decommissioning directly resulting from a Non-Political Event, in each case, for which no Relief Costs shall be payable), the Concessionaire shall be only entitled to such Relief Costs that:

- are directly attributable to the Relief Event; and

- represent increase (as a result of a Relief Event) in only such costs that are expressly set out in the Financial Model.

    - Subject to the terms of this Agreement, the Project Works shall not be delayed pending the issuance of a Relief Order by the Independent Auditor and the Independent Engineer or by the granting of an extension of Time for Completion or payment of Relief Costs.

    - In the event the Agency fails to pay the Relief Costs in full within the forty-five (45) day period stipulated in Section 15.3.4 (or, where applicable, the timelines stipulated in Section 15.6), the Agency shall pay late payment interest on the unpaid amount of such Relief Costs at the Delayed Payment Rate. Such interest shall accrue daily from the due date until the date of actual payment of the Relief Costs by the Agency. The payment of such interest shall be without prejudice to the Concessionaire's right to Terminate this Agreement for an Agency Event of Default pursuant to Section 22.2.1 if such payment delay exceeds ninety (90) days.

## Additional Requirements for Relief Orders Relating to Extension of Time for Completion

    - The Parties agree that the provisions of this Section 15.4 (Additional Requirements for Relief Orders Relating to Extension of Time for Completion) shall apply to each Relief Order Proposal and the Relief Order Request that, in each case, proposes an extension to the Time for Completion or to any Project Milestone Date for a Project Milestone.

    - Any Relief Order Proposal and/or, if applicable, the Relief Order Request submitted by the Concessionaire shall be subject to the Concessionaire otherwise being ready to progress with the aspect of the Project Works for which an extension is being sought. In the event the Concessionaire is in any event delayed in the performance of its obligations due to reasons other than the Relief Event, the Concessionaire shall not be granted any extension of Time for Completion to the extent of its delay.

    - In all cases where the Concessionaire submits a Relief Order Proposal and the Relief Order Request, the Concessionaire shall consult with the Agency, the Agency Representative, the Independent Engineer and the Independent Auditor in order to determine steps (if any) which can be taken to overcome or minimize the actual or anticipated delay. The Concessionaire shall thereafter comply with all reasonable instructions that the Independent Engineer and the Independent Auditor shall give in order to overcome or minimize such delay.

    - If the Concessionaire intends to initiate a Relief Order Request for issuance of a Relief Order for an extension of Time For Completion, the Concessionaire shall give Notice to the Independent Engineer and the Independent Auditor (with a copy to the Agency) of such intention as soon as possible and in any event within seven (7) days of the day the Concessionaire should reasonably have become aware of the start of the Relief Event giving rise to the delay, together with any other notice required by the Agreement and relevant to such cause. The Concessionaire is further required to submit to the Independent Engineer and the Independent Auditor (with a copy to the Agency), as part of the Relief Order Proposal relating to the Relief Order Request that pertains to an extension of Time for Completion, an acceleration strategy and schedule to demonstrate how such delay can be eliminated and/or mitigated.

    - Within twenty-eight (28) days of the first day of a delay that has resulted from the Relief Event in initiation of the Relief Order Request by the Concessionaire for issuance of a Relief Order by the Independent Engineer and the Independent Auditor for an extension of Time for Completion, the Concessionaire shall submit full supporting details of its request, including, without limitation, a critical path analysis of the alleged delay reflecting the considerations set forth in this Section. If the Concessionaire cannot submit all relevant details within such period because the cause of delay has continued for a period exceeding seven (7) days, the Concessionaire shall submit interim details at intervals of not more than twenty-eight (28) days (from the first day of such delay) and full and final supporting details of its request within sixty (60) days of the last day of delay. In the appropriate circumstances, the Agency shall have the right to waive the time periods set out as above.

## Disputes and Burden of Proof

    - Any Dispute between the Parties in reference to the issuance of a Relief Order and/or any matters relating to the same shall be resolved pursuant to Article 30 (Dispute Resolution).

    - In case of a Dispute regarding the application of the provisions of this Article 15 (Relief Extensions & Relief Compensations), the Concessionaire shall have the burden of proof as to its entitlement to relief under this Article 15 (Relief Extensions & Relief Compensations).

## Relief Cost Payment Threshold

## To optimize administrative efficiency, the Parties agree that the Agency shall not be obligated to make a cash payment for Relief Costs unless and until the aggregate approved and unpaid Relief Costs determined pursuant to valid Relief Orders during a given Accounting Year exceed Relief Cost Threshold.

## Notwithstanding Section 15.6.1, the Concessionaire shall continue to submit Relief Order Requests, and the Independent Engineer and the Independent Auditor shall continue to evaluate and issue Relief Orders quantifying Relief Costs in real-time, regardless of whether the Relief Cost Threshold has been achieved.

## Once the aggregate unpaid Relief Costs approved via Relief Orders exceed the Relief Cost Threshold, the entire accumulated amount shall become due and payable by the Agency within forty-five (45) days of the Agency's receipt of the specific Relief Order that causes the Relief Cost Threshold to be exceeded.

## If, at the end of any Accounting Year, the accumulated unpaid Relief Costs are less than the Relief Cost Threshold, such accumulated amounts shall not be forfeited or waived. Instead, the total accumulated unpaid Relief Costs for that Accounting Year shall become due and payable by the Agency within forty-five (45) days following the last day of such Accounting Year.

## Full Compensation

    - Any:

- extensions of Time for Completion; and/or

- payment of Relief Costs,

in each case, granted pursuant to a Relief Order shall be deemed to be full and complete compensation to the Concessionaire by the Agency in respect of matters relating to the Relief Order.

# Change of Scope

## Change of Scope

    - Notwithstanding anything to the contrary contained in this Agreement, the Agency may require a change/amendment in the Scope of the Project (the Change of Scope); provided that the accrued and cumulative change at any given time does not result in a variation in the Pre-Estimated Project Cost by more than the Change of Scope Limit, as determined by the Independent Engineer and the Independent Auditor. All Additional Costs to be paid by the Agency in respect of the Change of Scope and any extensions in the timelines for the performance by the Concessionaire of its obligations resulting from a Change of Scope shall be in accordance with Section 16.2 and Section 16.3.

## Change of Scope Notice

    - The Agency may request the Change of Scope by issuing a Change of Scope Notice in accordance with the provisions of this Section 16.2 (Change of Scope Notice).

    - The Agency may request a Change of Scope by issuing a notice in writing to the Concessionaire through the Independent Engineer (the Change of Scope Notice):

- at least ninety (90) days prior to the Scheduled Substantial Completion Date in the event the Change of Scope is required during the  Development Period; and

- at any time in the event the Change of Scope is required during the Operations Period.

    - In the event at any time during the Development Period and/or the Operations Period, the Concessionaire determines that a Change of Scope is necessary for providing safer and improved services, the Concessionaire shall issue a request in writing to the Agency through the Independent Engineer to consider issuing a Change of Scope Notice in respect of the same. The Agency shall within forty-five (45) days from the date of receipt of such notice, either accept such request for Change of Scope, on an ‘as is’ basis or with modifications, and issue the requisite Change of Scope Notice in accordance with the provisions of this Section 16.2 (Change of Scope Notice) or communicate its reasons for not accepting the same to the Concessionaire.

## Change of Scope Order

    - The Concessionaire shall, within fifteen (15) days of receipt of the Change of Scope Notice, provide to the Independent Engineer such information as is necessary and reasonable together with the preliminary documentation and details, including the calculations, where necessary, in support of the following:

- the impact which the Change of Scope is likely to have on the  Development Requirements in the event the Change of Scope applicable during the Development Period and/or the O&M Requirements in the event the Change of Scope applicable during the Operations Period;

- the budgeted estimate of the Additional Cost to be incurred by the Concessionaire for implementing the Change of Scope;

- the estimated additional time (number of days) that the Concessionaire would require to achieve Substantial Completion and/or Project Development Completion consequent to the Change of Scope and any delay, if any, in the Final Expiry Date;

- any extensions in the Project Development Completion Schedule resulting from the Change of Scope; and

- any extensions in the timelines for performance by the Concessionaire of its obligations under this Agreement resulting from the Change of Scope.

    - The Independent Engineer shall, after reviewing the information, documentation and the budgeted estimate of the Additional Cost submitted by the Concessionaire pursuant to Section 16.3.1, settle the rates and approve the designs. Thereafter, the Independent Engineer and the Independent Auditor shall, in consultation with the Concessionaire, jointly issue a certified statement of the budgeted estimates of the Additional Cost to the Agency and the Concessionaire.

    - The Agency may, within a period of fifteen (15) days from the date of receipt of such statement, issue an order in writing to the Concessionaire through the Independent Engineer, instructing the Concessionaire to effect the Change of Scope (the Change of Scope Order). In the event the Agency fails to issue the Change of Scope Order within thirty (30) days of the receipt of such certified statement, the relevant Change of Scope Notice shall be deemed void and shall lapse immediately.

    - In the event the Agency for any reason whatsoever decides not to issue a Change of Scope Order in accordance with Section 16.3.3, then the Agency shall reimburse the Concessionaire for the cost/expenses actually incurred by the Concessionaire in the preparation and submission of the documents, estimates and other information in compliance with the Change of Scope Notice; provided, such costs and expenses are duly certified by the Independent Auditor and the Independent Engineer.

    - The mode for payment of the Additional Costs to the Concessionaire shall be as follows and shall be complied with by the Agency within forty-five (45) days of the issuance of a Change of Scope Order and until such time that the following conditions are complied with by the Agency, the Concessionaire shall not be obligated to commence and/or perform the works forming part of the Change of Scope Order:

- the Change of Scope Advance Percentage of the Additional Cost shall be paid in advance upon issuance of the Change of Scope O rder (or as agreed between the Parties in accordance with Applicable Laws);

- the remaining shall be transferred by the Agency to an Escrow Account pursuant to an escrow arrangement agreed with the Concessionaire wherefrom the same shall be utilized progressively upon certification by the Independent Engineer of the performance of works.

    - The Change of Scope Order shall be effective from the date that the Agency notifies the mode of reimbursement of the Additional Cost to the Concessionaire pursuant to Section 16.3.5.

    - Save for the advance payment under Section 16.3.5(a), the Agency shall progressively pay the Additional Cost in accordance with Section 16.3.5 or any other modality as mutually agreed between the Parties, only upon receiving a certificate from the Independent Engineer confirming that the Concessionaire has completed the relevant milestone(s) of the works in accordance with the Change of Scope Order.

    - Upon receipt of a Change of Scope Notice by the Concessionaire, all relevant Project Development Milestones and associated obligations of the Concessionaire under the Project Development Completion Schedule shall be suspended. Such suspension shall remain in effect from the date of receipt of the Change of Scope Notice until the date on which a Change of Scope Order is issued and the works forming part of the Change of Scope Order have actually commenced. The Time for Completion, Development Programme, Project Development Milestones and the Project Development Completion Schedule shall be equitably adjusted to reflect the duration of such suspension in accordance with the provisions of Article 15 (Relief Extensions & Relief Compensations).

    - In the event that a Change of Scope results in a net reduction in the capital or operating costs of the Project (the “Saving”), such Saving shall be shared between the Agency and the Concessionaire in a default ratio of or such other ratio as may be expressly agreed between the Parties in the relevant Change of Scope Order. The Independent Engineer and the Independent Auditor shall jointly quantify the amount of the Saving within twenty-one (21) days of the successful completion of the works and/or services as contemplated in the Change of Scope Order. The Agency’s share of the Saving shall be adjusted against any future payments due to the Concessionaire or as otherwise mutually agreed between the Parties.

# 17.    Revenue Matters

17.1.   The Parties acknowledge and agree that all matters pertaining to the collection, calculation, allocation, and distribution of Revenues generated by the Project shall be strictly governed by and subject to the provisions and parameters set forth in Schedule R (Revenue Matters).

# Defects & Deficiencies, Notice of Remedy, Suspension

## Remedying Defects & Deficiencies

    - The Concessionaire warrants that the:

- Project Works shall be performed in good workmen like manner in accordance with the Applicable Standards and shall be free from all Defects & Deficiencies; and

- the Concession Assets shall comply with the Applicable Standards.

    - In order that the Project Works and the Concession Assets comply with the foregoing warranties and that the same are in the condition required by this Agreement, the Concessionaire shall execute all works and services relating to amendment, redevelopment and remedying of Defects & Deficiencies (including the removal, replacement and reinstallation of materials and equipment, remedying of Defects & Deficiencies and retesting of repaired or replaced portions of the Project Works (if appropriate in accordance with Good Industry Practice)) at its own cost, risk and expense; provided, however, the amendment, redevelopment and remedying of such Defects & Deficiencies shall be at the cost, risk and expense of the Agency in the event the same is caused by a Permitted Events (except a Non-Political Event).

    - [In the event, the remedying of any Defect & Deficiency or damage is such that it may significantly affect the performance of the Project Works and/or the Concession Assets, the Independent Engineer and/or the Agency may require that certain  Development Tests, O&M Tests and/or the Completion Tests (as the case may be) to be repeated to the extent necessary. The requirement shall be made by written Notice after the Defect & Deficiency or damage is remedied. Such tests shall be carried out by the Concessionaire in accordance with the Applicable Standards and all costs and expenses of any nature associated with re-performance of such tests shall be allocated in accordance with Section 18.1.2.]

## Notice Remedy

    - In the event (the Remedy Events):

- the Project Works (or any part thereof) are not performed in accordance with the Applicable Standards; and/or

- the Project Works (or any part thereof) fail to comply with the Applicable Standards; and/or

- the Concession Assets (or any part thereof) fail to comply with the Applicable Standards, then the Independent Engineer and/or the Agency (through the Independent Engineer) shall be entitled to issue a Notice to the Concessionaire to rectify and remedy the same (the Notice of Remedy). The Notice of Remedy shall set out the reasonable time period (as determined by the Independent Engineer) (the Remedy Time Period) in which the Concessionaire shall remedy and rectify the Remedy Events in accordance with the Applicable Standards. The Parties agree and acknowledge that the Remedy Time Period does not amend or affect the Cure Period and the periods set out in the Cure Period (and Agency’s rights in respect of the Cure Period) shall continue to apply and shall not be affected by this Section 18.2 (Notice Remedy).

    - In the event of failure by the Concessionaire to remedy the Remedy Events within the Remedy Time Period, the Agency shall, without prejudice to any of its other rights and remedies under this Agreement, be entitled to, with the prior approval of the Independent Engineer and at the risk and cost of the Concessionaire, cause the remedying and rectification of the Remedy Events.

    - The Concessionaire shall reimburse all costs incurred by the Agency (as certified by the Independent Auditor and the Independent Engineer) on account of such remedying and rectification of the Remedy Events within thirty (30) days of receipt of the Agency’s claim thereof set out in an invoice approved by the Independent Engineer and the Independent Auditor (the Agency Remedy Invoice). In the event of failure by the Concessionaire to pay the amounts set out in the Agency Remedy Invoice (the Agency Remedy Amount) within the time period set out herein, the Agency shall be entitled to receive such Agency Remedy Amount through encashment of (as in effect at such time) the Development Performance Security or O&M Performance Security. In the event the funds received by the Agency through encashment of the Development Performance Security and/or the O&M Performance Security are less than the Agency Remedy Amount, the Concessionaire shall be obligated to pay the Agency the shortfall within three (3) days of the Agency’s written demand.

## Suspension

    - The:

- Agency may by Notice in writing to the Concessionaire (with a copy to the Independent Engineer and the Independent Auditor) require the Concessionaire to suspend forthwith the whole or any part of the Project Works if, in the reasonable opinion of the Agency: (i) such work threatens the safety of the Specific Persons; (ii) such Project Works impact national security;] or (iii) such Project Works are not in accordance with the Applicable Standards and/or Good Industry Practices; and/or

- Independent Engineer may, by Notice to the Concessionaire (with a copy to the Agency and the Independent Auditor), require the Concessionaire to suspend forthwith the whole or any part of the Project Works which in the reasonable opinion of the Independent Engineer is being carried on/conducted in a manner that is not in conformity with the Applicable Standards and/or is not in accordance with Good Industry Practice,

(the Suspension, Suspend and its grammatical variations).

    - The Concessionaire shall, pursuant to any notice issued under Section 18.3.1, Suspend the Project Works or any part thereof for such time and in such manner as may be specified by the Agency and/or the Independent Engineer and thereupon carry out remedial measures to secure the safety of Suspended works and for compliance of the Suspended Project Works with the Applicable Standards and Good Industry Practice.

    - The Concessionaire may by Notice (with a copy to the Agency) require the Independent Engineer to inspect such remedial measures forthwith. Following such inspection, the Independent Engineer shall either revoke such Suspension or instruct the Concessionaire to carry out such other and further remedial measures as may be necessary in the reasonable opinion of the Independent Engineer, and the procedure set forth in this Section 18.3 (Suspension) shall be repeated till such time as the Suspension hereunder is revoked.

    - All reasonable costs incurred for maintaining and protecting the Project Works (or part thereof) during the period of Suspension (the Preservation Costs) shall be borne by the Concessionaire; provided that if the Suspension has occurred as a result of a Permitted Event, the provisions of Article 21 (Force Majeure) and Article 15 (Relief Extensions & Relief Compensations), as the case may be, shall apply.

    - All delays caused as a result of the Suspension shall be on account of the Concessionaire; provided, however, in the event the Suspension is caused due to a Permitted Event, any extensions of the Time for Completion shall be subject to the provisions of Article 15 (Relief Extensions & Relief Compensations) and Article 21 (Force Majeure), as the case may be.

# Operation and Maintenance

## Operation and Maintenance

    - During the Operations Period, the Concessionaire shall operate and maintain the Concession Assets on a continuous twenty-four (24) hours per day, three hundred and sixty-five (365) days per year basis. The Concessionaire shall perform the Operation and Maintenance strictly in accordance with the Applicable Standards and the O&M Requirements, and shall complete such works within the O&M Time for Completion (including achieving each Project O&M Milestone on or prior to its respective Project O&M Milestone Date).

    - The Concessionaire shall perform the Operation and Maintenance either itself, or through the O&M Contractor appointed in accordance with the terms of this Agreement; provided, however, the Concessionaire shall remain solely responsible and liable for performance (within O&M Time For Completion) and compliance of the Operations and Maintenance with the Applicable Standards irrespective of whether the Operation and Maintenance is undertaken by the Concessionaire or the O&M Contractor.

## Operation and Maintenance Obligations of the Concessionaire

    - The Concessionaire undertakes to perform the Operation and Maintenance of the Concession Assets during the Operations Period in accordance with the provisions of Section 19.1 (Operation and Maintenance) and undertakes to modify, repair and to provide all such improvements and services as may be required for the Operation and Maintenance of the Concession Assets in accordance with the Applicable Standards.

    - The Concessionaire hereby agrees that the Operation and Maintenance obligations of the Concessionaire hereunder shall include, without limitation, the performance of the following obligations in accordance with the Applicable Standards and Good Industry Practice and within the O&M Time for Completion:

- ensuring that during the Operations Period, the Concession Assets are in a safe condition to permit safe, smooth and uninterrupted use during normal operating conditions;

- carrying out routine maintenance and the periodic preventive maintenance of the Concession Assets;

- preventing, with the assistance of concerned law enforcement agencies, any unauthorized use of the Concession Assets;

- preventing, with the assistance of the concerned law enforcement agencies, any encroachments on the Project Site;

- protecting the environment (to the extent of the Concessionaire’s activities) and providing equipment and materials therefor;

- operation and maintenance of all communication, control and administrative systems necessary for the efficient operation of the Concession Assets;

- maintaining a public relations unit to interface with and attend to suggestions from the  Agency, the Government Authorities, media and other agencies;

- complying with Safety Requirements;

- promptly removing from the Project Site, all surplus development machinery and materials, waste materials (including hazardous materials and waste water), rubbish and other debris (including, without limitation, accident debris) and keeping the Project Site in a clean, tidy and orderly condition, in each case, in conformity with the Applicable Standards; and

- performing all other activities and obligations relating to Operation and Maintenance so as to comply with the Applicable Standards and also so as to result in the Concession Assets complying with the Applicable Standards.

## Material Breach of O&M Requirements

    - The Concessionaire shall be deemed to be in material breach of the O&M Requirements (the Material Breach of O&M Requirements) if the Independent Engineer and/or the Agency (through the Independent Engineer), acting reasonably and in accordance with the provisions of this Agreement, has determined that due to breach of its obligations by the Concessionaire:

- there has been a failure/undue delay in carrying out scheduled/planned maintenance or the scheduled/planned maintenance has not been carried out in accordance with the O&M Requirements;

- there has been a material failure in performance by the Concessionaire of the Operation and Maintenance (or any part thereof) within the O&M Time for Completion which has resulted in a Material Adverse Effect;

- there has been a serious or persistent lapse in adhering to Safety Requirements and thereby the Concession Assets or any part thereof is not safe for operations;

- there has been Persistent Breach of O&M Requirements.

## Agency’s Rights with Regard to Material Breach of O&M Requirements

    - Upon the occurrence of a Material Breach of O&M Requirements, the Agency shall, without prejudice to and notwithstanding any other consequences provided thereof shall have the right and be entitled to Terminate this Agreement in accordance with Section 23 (Termination).

## O&M Manual

    - No later than twenty (20) days prior to the Scheduled Substantial Completion Date, the Concessionaire, the Concessionaire Project Expert and the Independent Engineer shall jointly prepare and submit to the Agency, an operations, repair, maintenance and safety manual (together with arrangements and procedures for conducting safety related measures) in respect of the Concession Assets that shall comply with the Applicable Standards and Good Industry Practice and shall set out, inter alia, the regular preventive maintenance and operating procedures for the Concession Assets, as to be performed pursuant to the Applicable Standards and Good Industry Practice. Such operations, repair, maintenance and safety manual shall include provisions for operation and maintenance of the Concession Assets and shall, inter alia, provide for life cycle maintenance, routine maintenance and reactive maintenance which may be reasonably necessary for maintenance and repair of the Concession Assets, including replacement thereof, such that their overall condition conforms to the Applicable Standards. The operations, repair, maintenance and safety manual shall also set out certain Project O&M Milestones and their respective Project O&M Milestone Dates.

    - The operations, repair, maintenance and safety manual jointly prepared by the Concessionaire, the Concessionaire Project Expertand the Independent Engineer shall be subject to approval of the Agency; provided, however, such approval shall be granted by the Agency within fifteen (15) days of the Concessionaire’s request for such approval if the operations, repair, maintenance and safety manual is recommended by the Independent Engineer for approval after addressing any comments and observations of the Agency on the same. The operations, repair, maintenance and safety manual, as approved by the  Agency, shall be binding on the Parties (the O&M Manual).

    - Four (4) copies of the O&M Manual shall be provided by the Concessionaire to each of Agency and the Independent Engineer.

    - The O&M Manual shall be revised and updated on third (3rd) anniversary of its initial preparation and subsequently every three (3) years thereafter, in each case, with mutual consent of the Parties and in consultation with the Independent Engineer; provided, however, the Parties may revise, update and/or amend the O&M Manual with mutual consent at any time.

## O&M Programme

    - Ninety (90) days prior to commencement of the Operations Period and thereafter thirty (30) days prior to the commencement of each Operational Year during the Operations Period, as the case may be, the Concessionaire, the Concessionaire Project Expert and the Independent Engineer shall jointly prepare and provide to the Agency, a proposed annual program, to be prepared in compliance with the Applicable Standards and Good Industry Practices, of Operation and Maintenance during the upcoming Operational Year (including preventive, urgent and other scheduled maintenance of Concession Assets) (the Proposed O&M Programme). The Proposed O&M Programme shall include, without restriction, the following:

- the Project O&M Milestones to be achieved during the upcoming Operational Year and the respective Project O&M Milestone Dates for each of the same;

- routine maintenance and preventive maintenance schedule;

- arrangements and procedures for carrying out urgent repairs in respect of the Concession Assets;

- the timelines, intervals and procedures for conducting the inspection of all elements of the Concession Assets;

- the timelines and intervals at which the Concessionaire shall conduct periodic maintenance in respect of the Concession Assets;

- arrangements and procedures for conducting safety related measures in relation to the Concession Assets;

- timelines and intervals for maintenance works and the scope thereof; and

- all major events and activities in the preparation of  O&M Documents and submission of the same to the Agency, the Independent Engineer and/or the Independent Auditor (as applicable) for the review and approval (as applicable);

    - The Proposed O&M Programme jointly prepared by the Concessionaire, the Concessionaire Project Expertand the Independent Engineer shall be subject to approval of the Agency; provided, however, such approval shall be granted by the Agency within twenty one (21) days of the Concessionaire’s request for such approval if the Proposed O&M Programme is recommended by the Independent Engineer for approval after addressing any comments and observations of the Agency on the same. The Proposed O&M Programme prepared in respect of an Operational Year, as approved by the Agency on the Independent Engineer’s recommendation, shall be binding on the Parties for such Operational Year (the O&M Programme).

    - The Concessionaire shall, whenever required by the Agency, the Independent Engineer and/or the Independent Auditor, provide in writing, a general description of the arrangements and methods which the Concessionaire proposes to adopt for the execution of the Operation and Maintenance. Any alteration to the O&M Programme or to such arrangements and methods shall be made by the Concessionaire with prior written consent of the Independent Engineer.

    - Any reports (including the O&M Status Reports) submitted by the Concessionaire and covering the execution of the Operation and Maintenance shall emphasize any delays in the O&M Time for Completion.

## O&M Documents

    - The Concessionaire shall prepare the O&M Documents in accordance with the Applicable Standards and shall complete and deliver the same to the Agency, the Independent Engineer and the Independent Auditor (as applicable) from time to time within the O&M Time for Completion. Further, the Concessionaire hereby undertakes that the O&M Documents shall comply with the Applicable Standards.

    - The Agency, the Independent Engineer and the Independent Auditor (as applicable) shall have the right to review and inspect all O&M Documents. The Concessionaire shall provide all such O&M Documents that the Agency, the Independent Engineer and the Independent Auditor may reasonably require to inspect in respect of the Operation and Maintenance. It is made clear that nothing in the above shall diminish the Concessionaire’s responsibility to provide the Agency, the Independent Engineer and the Independent Auditor with sufficient information to enable the same to satisfy themselves regarding the Operation and Maintenance.

    - For each part of the Operation and Maintenance, if the Agency, the Independent Engineer and the Independent Auditor (as applicable) wish to modify any O&M Documents, the Agency, the Independent Engineer and the Independent Auditor (as applicable) shall immediately submit their proposal for modification to the Concessionaire. Performance of such modification shall be subject to mutual agreement between the Parties.

    - Defects & Deficiencies, errors, omissions, ambiguities, inconsistencies, inadequacies and other defects in the O&M Documents or arising there from shall be rectified by the Concessionaire at its sole cost and risk.

    - The Agency, the Independent Engineer and the Independent Auditor (as applicable) may use the O&M Documents for such purposes as it may require for the purposes of the Project.

## Modifications to the Project

    - The Concessionaire shall not carry out any material modifications to the Concession Assets, save and except where such modifications are necessary for: (a) the Operation and Maintenance of the Concession Assets in conformity with the Applicable Standards; and (b) compliance by the Concession Assets with the Applicable Standards; provided, however, the Concessionaire shall Notify the Independent Engineer and the Agency of the proposed modifications along with particulars thereof at least thirty (30) Business Days before commencing work on such modifications and shall only implement such modifications upon receipt of the Independent Engineer’s and/or Agency’s approval of the same, which approval shall be provided or declined by the Independent Engineer and/or the Agency within fifteen (15) days of its receiving the Concessionaire’s proposal. For the avoidance of doubt, all modifications made hereunder shall comply with the Applicable Standards.

## Barriers and Diversions

    - The Agency shall procure that during the Operations Period, no barriers are erected or placed by any Government Agency and/or the Agency on the Concession Assets, except for reasons of Emergency, national security, law and order; provided, that all such barriers shall be in accordance with the Applicable Standards (including the Safety Requirements).

## O&M Status Report

    - During the Operations Period, the Concessionaire shall furnish to the Agency and the Independent Engineer a report in accordance with each O&M Status Reporting Timeline (the O&M Status Report) stating in reasonable detail the condition of the Concession Assets including its compliance or otherwise with the Applicable Standards and shall promptly give such other relevant information as may be required by the Independent Engineer, the Independent Auditor and/or and the Agency. In particular, the O&M Status Report shall separately identify and state in reasonable detail the Defects & Deficiencies in the Concessionaire Assets and/or the Operation and Maintenance that require rectification and any delays in the performance of its obligations by the Concessionaire set out in the O&M Programme. The O&M Status Report shall also expressly highlight all Defects & Deficiencies in the Operation and Maintenance and/or the Concession Assets identified by the Independent Engineer in its O&M Inspection Report and shall set out all actions taken, and arrangements made by the Concessionaire for remedying the same.

    - Each O&M Status Report shall be updated by the Concessionaire based on any observations and comments made by the Independent Engineer and shall be provided again to each of the Agency and the Independent Engineer until such time that it is approved by the Independent Engineer; provided, that the Independent Engineer shall not accord its approval of the O&M Status Report until it is satisfied that all reasonable comments and observations of the Agency on the O&M Status Report are addressed.

    - The O&M Status Report shall be in the form approved by the Independent Engineer from time to time.

## O&M Inspection Report

    - During the Operations Period, the Concessionaire shall enable the Independent Engineer to inspect the Operation and Maintenance and the Concession Assets in accordance with each O&M Inspection Timeline and the Concessionaire shall make all arrangements for the same.

    - The Independent Engineer shall make a report of such inspection (the O&M Inspection Report) stating in reasonable detail the Defects & Deficiencies, if any, in the Operation and Maintenance and /or the Concession Assets with particular reference to the Applicable Standards.

    - The Independent Engineer shall, within seven (7) days after every O&M Inspection Timeline, provide a copy of the O&M Inspection Report to the Concessionaire and the Agency.

    - The Concessionaire hereby undertakes that, within fifteen (15) days from receipt of the O&M Inspection Report, it shall rectify and remedy the Defects & Deficiencies, if any, stated in the O&M Inspection Report, on its own cost and expense.

    - The inspection or submission of the O&M Inspection Report by the Independent Engineer shall not relieve or absolve the Concessionaire of its obligations and liabilities hereunder in any manner whatsoever.

## O&M Tests

    - The Concessionaire shall conduct or procure to be conducted such tests, as specified in Schedule G (Completion Tests Matters) in order to determine whether the Operation and Maintenance and/or the Concession Assets conform to the Applicable Standards (the O&M Tests). The O&M Tests shall be conducted at such time and frequency and in such manner as may be specified by the Independent Engineer and the  Agency. In the event the timing and frequency of any O&M Tests is specified by the Agency and it is determined that the Operation and Maintenance is not in accordance with the O&M Requirements (as determined by the Independent Engineer), the cost of such O&M Tests shall be borne by the Concessionaire; provided, however, in the event it is determined that the Operation and Maintenance are in accordance with the O&M Requirements (as determined by the Independent Engineer), the cost of such O&M Tests shall be borne by the Agency.

    - Subject to Section 19.23.1, the Concessionaire hereby undertakes to conduct the O&M Tests under the supervision of the Independent Engineer  and in accordance with the Applicable Standards at its own and expense.

    - The Concessionaire hereby undertakes to carry out, at its sole cost, the necessary remedial measures required to rectify the Defects & Deficiencies in the Operation and Maintenance and/or the Concession Assets that are identified in the O&M Tests and to ensure that as a consequence of such remedial measures the Operation and Maintenance and the Concession Assets conform to the Applicable Standards. The Concessionaire further undertakes that the remedial measures required to be undertaken by the Concessionaire pursuant to this Section 19.23.3 shall be repeated by the Concessionaire at its sole cost till such time as the Operation and Maintenance and the Concession Assets conform to the Applicable Standards to the satisfaction of the Independent Engineer. In the afore stated circumstances, the Independent Engineer may require the Concessionaire to conduct additional tests to determine whether the Defects & Deficiencies are rectified and in such case the costs of such additional tests shall be borne by the Concessionaire.

    - The Concessionaire shall maintain proper record of the O&M Tests and the remedial measures taken to cure the Defects & Deficiencies, if any, indicated by the O&M Test results.

    - Results of all O&M Tests shall be jointly recorded by the Independent Engineer and the Concessionaire.

## Remedial Measures

    - The Concessionaire shall repair or rectify the Defects & Deficiencies, if any, set forth in the O&M Inspection Report or in the O&M Tests results referred to in Section 19.23 (O&M Tests) and furnish a report in respect thereof to the Independent Engineer and the Agency within seven (7) days of receiving the O&M Inspection Report or the O&M Tests results, as the case may be; provided, that where the remedying of such Defects & Deficiencies is likely to take more than seven (7) days, the Concessionaire shall submit progress reports of the repair works once every week until such works are completed in conformity with this Agreement.

    - The Independent Engineer shall require the Concessionaire to carry out or cause to be carried out the O&M Tests, at its own cost, to determine that such remedial measures have brought the relevant Concession Assets into compliance with the Applicable Standards and the procedure set forth in this Section 19.24 (Remedial Measures) shall be repeated until the Concession Assets conform to the Applicable Standards.

    - The provisions of this Section 19.24 (Remedial Measures) shall not in any manner limit the obligations of the Concessionaire relating to remedying of Defects & Deficiencies set out elsewhere in this Agreement.

# Insurances

## Development Period Insurances

    - The Concessionaire shall, at its sole cost and expense, procure and maintain during the Development Period all such Insurances, as described in Part I (Development Period Insurances) of Schedule I (Insurances), that are necessary and required to be procured by the Concessionaire in accordance with the Applicable Laws.

## Operations Period Insurances

    - The Concessionaire shall, at its sole cost and expense, procure and maintain during the Operations Period all such Insurances, as described in Part II (Operations Period Insurances) of Schedule I (Insurances), that are necessary and required to be procured by the Concessionaire in accordance with the Applicable Laws.

## Insurance Companies

    - The Concessionaire agrees that it shall procure the Insurances (which for the purposes of this Article 20 shall include Takaful arrangements) from Takaful companies of appropriate rating or insurance companies holding a rating of at least [single A/AA] as per PACRA/JCR-VIS or an equivalent international rating agency (the Minimum Insurance Rating) that are acceptable to the Agency and further agrees that the Concessionaire shall only procure Insurances through foreign insurance companies or Takaful companies if the relevant Insurances are not being offered by local companies at comparable rates, subject always to the prior consent of the Agency. The Minimum Insurance Rating shall serve as the default floor standard for the Project; provided that the specific rating floor and requirements for the Project may be further detailed or increased.

    - Further, the Insurances to be maintained in terms of this Agreement and in accordance with the terms set out herein shall be maintained throughout until the Trigger Date.

## Evidence of Insurances

    - The Concessionaire shall, from time to time, provide to the Agency copies (duly attested as certified to be a true and correct copy by the relevant insurance company or Takaful company) of all insurance policies (or appropriate endorsements, certifications or other satisfactory evidence of insurance) obtained by the Concessionaire in accordance with this Agreement.

    - Failure by the Concessionaire to obtain the Insurance coverage or certificates of Insurance required by this Article 20 (Insurances) shall not in any way relieve or limit the Concessionaire’s obligations and liabilities under any provision of this Agreement.

    - In the event the Concessionaire fails to procure or maintain any Insurance required pursuant to this Article 20 (Insurances), then the Agency shall have the right to procure such Insurance in accordance with the requirements of Schedule I (Insurances) and shall be entitled to offset the premiums paid for such insurance against any amounts owed to the Concessionaire pursuant to the terms of this Agreement and the Agency Agreements. The Concessionaire shall be named as the loss payee on any such Insurance procured by the Agency pursuant to this Section 20.4.3.

    - The Concessionaire shall provide the Agency with copies of any underwriters’ reports or other reports received by the Concessionaire from any insurance company or Takaful company; provided, that the Agency shall not disclose such reports to any other person except as necessary in connection with administration and enforcement of this Agreement or any other Agency Agreement or as may be required by any Government Authority and shall use and internally distribute such reports only as necessary in connection with the administration and enforcement of this Agreement.

## Application of Insurance Proceeds

    - All moneys received under the Insurance shall be promptly applied by the Concessionaire towards repair, renovation, restoration and/or substitution of the Concession Assets or any part thereof which may have been damaged or destroyed; provided, that all costs relating to such repair, renovation, restoration and/or substitution shall be duly certified by the Independent Engineer and the Independent Auditor.

    - The Concessionaire shall carry out the repair, renovation, restoration and/or substitution to the extent possible in such manner that the Concession Assets or any part thereof, shall, after such repair, renovation, restoration and/or substitution be as far as possible in the same condition as they were before such damage or destruction, normal wear and tear excepted.

## Validity of Insurances

    - The Concessionaire hereby undertakes to promptly pay the insurance premium or Takaful contribution in respect of the Insurances and to keep the policies in force and valid during the entire Concession Period. The Concessionaire shall provide to the Agency, copies of the renewed policies and other documentary evidence of the payment of the insurance premium and Takaful contribution in respect of the Insurances.

    - The Concessionaire shall ensure, subject to market availability, that each instrument, contract and/or policy issued in respect of the Insurances shall provide that the Insurance may not be cancelled and/or terminated without at least ten (10) days prior written notice to the Agency of such cancellation and/or termination.

    - Notwithstanding anything contained herein, in the event the Concessionaire fails to comply with its obligations to procure the Insurances in accordance with Section 20.1 (Development Period Insurances) and/or Section 20.2 (Operations Period Insurances), the Agency may, without prejudice to its other rights and remedies for breach, at its option, obtain and maintain such Insurance and all sums incurred by the Agency therefore shall be reimbursed by the Concessionaire to the Agency within seven (7) days from the receipt of a claim by the Concessionaire in respect thereof from the Agency.

    - The Concessionaire shall notify the Agency in advance, prior to any material variation of the Insurances.

## Maintenance Of ‘Occurrence’ Form Policies

    - A coverage required under this Article 20 (Insurances) and Schedule I (Insurances) and any ‘umbrella’ or excess coverage shall be ‘occurrence’ form policies. In the event the Concessionaire has ‘claims-made’ form coverage, the Concessionaire must obtain prior approval of all ‘claims-made’ policies or contracts from the Agency.

## Policy Endorsements

    - The Concessionaire shall cause the insurance companies or Takaful companies to provide the following endorsement items in the commercial general liability and, if applicable, umbrella or excess liability policies relating to the development, Operation and Maintenance of the Concession Assets provided pursuant to this Article 20 (Insurances) and Schedule I (Insurances):

- the Agency, its officers, servants and agents shall be additionally insured under such policies with respect to claims arising out of or in connection with this Agreement;

- the insurance shall be primary with respect to the interest of the Agency, its officers, servants and agents and any other insurance maintained by them is excess and not contributory with such policies;

- the following separation of interests clause shall be made a part of the policy:

“In the event of claims being made by reason of (i) personal and/or bodily injuries suffered by any employee or employees of one insured hereunder for which another insured hereunder is or may be liable, or (ii) damage to property belonging to any insured hereunder for which another insured is or may be liable, then this policy shall cover such insured against whom a claim is made or may be made in the same manner as if separate policies have been issued to each insured hereunder, except with respect to the limits of insurance.”;

- the insurer shall waive all rights of subrogation against the Agency, its officers, servants and agents; and

- notwithstanding any provision of the policy, the policy may not be canceled or not renewed without the insurer endeavouring to give thirty (30) days written notice to the Agency except in the case of non-payment, in which case it shall be ten (10) days with prior written notice to the Agency. All other terms and conditions of the policy shall remain unchanged.

## [Uninsurable Risks

## If a risk previously covered by the Insurances becomes Uninsurable, the Concessionaire shall, within ten (10) Business Days of becoming aware of the same, notify the Agency in writing.

## Within fifteen (15) Business Days of the notice under Section 20.9.1, the Parties shall refer the matter to a ‘Fast-Track Panel’ comprising of the Independent Engineer, the Independent Auditor, and one (1) insurance expert mutually appointed by the Parties. The Fast-Track Panel shall, within fifteen (15) Business Days of the referral, verify and confirm whether the risk has become Uninsurable.

## Upon confirmation by the Fast-Track Panel that a risk is Uninsurable: (a) the Agency shall, in the event of a loss occurring which relates to such Uninsurable risk, pay to the Concessionaire an amount equivalent to the insurance proceeds that would have been payable had the risk remained insurable; or (b) where the Uninsurable risk results in a total loss of the Concession Assets or renders the Project permanently unviable, the Concessionaire may, at its sole election, terminate this Agreement and receive the Force Majeure Termination Payment as set out in Section 22.4.]

## Change in Insurance Market

## In the event that any insurance or Takaful coverage required under this Article 20 is no longer available in the international or local insurance markets on reasonable commercial terms (the Change in Insurance Market), the Concessionaire shall promptly notify the Agency. For the purposes of this Section, ‘reasonable commercial terms’ shall mean terms and conditions, including premium or contribution levels, that are generally available to and accepted by prudent concessionaires of infrastructure projects of a similar scale and risk profile.

## Upon the occurrence of a Change in Insurance Market, the Parties shall mutually agree and in consultation with the Independent Engineer and an insurance expert, implement one of the following options:

- the Concessionaire shall procure the best available coverage in the market, and the Agency shall bear the uninsured exposure and indemnify the Concessionaire against any Losses that would have been covered by the original required insurance; or

- the Parties shall agree upon alternative risk management or self-insurance arrangements to mitigate the specific risks affected by the Change in Insurance Market; or

- the Change in Insurance Market shall be treated as a Force Majeure Event under Article 21, and the Concessionaire shall be entitled to the relevant relief and compensation mechanisms provided therein, including Termination for Force Majeure if the risk is deemed material to the Project’s viability.

# Force Majeure

## Force Majeure Event

    - A Force Majeure Event means any event or circumstance or combination of events or circumstances (including the effects thereof) that is beyond the reasonable control of a Party and that on or after the Commencement Date materially and adversely affects the performance by such affected Party (the Affected Party) of its obligations under or pursuant to this Agreement; provided, however, that, such material and adverse effect could not have been prevented, overcome or remedied in whole or in part by the Affected Party through the exercise of diligence and reasonable care, it being understood and agreed that reasonable care includes acts and activities to protect the Concession Assets from a casualty or other event that are reasonable in light of the probability of the occurrence of such event, the probable effect of such event if it should occur, and the likely efficacy of the protection measures. Without limiting the generality of the foregoing, Force Majeure Events hereunder shall include each of the following events and circumstances (including the effects thereof), but only to the extent that each satisfies the requirements above:

(a)	the following political events that occur inside or directly involve Pakistan (each a Political Event):

(i)	any act of war (whether declared or undeclared), invasion, armed conflict or act of foreign enemy, blockade, embargo, revolution, riot, insurrection, civil commotion, or act or campaign of terrorism or political sabotage; or

(ii)	any Lapse of Consent of which report to the Agency, the Independent Engineer and the Independent Auditor shall have been given under Section 7.6.2 and that shall have existed for thirty (30) consecutive days or more; or

- any strike, work-to-rule, go-slow, or analogous labour action that is politically motivated or is widespread or nationwide and that (or its effects) shall have existed for thirty (30) consecutive days or more; or

- Change in Law.

(b)	the following events beyond the reasonable control of the Affected Party (each a Non-Political Event), including, but not limited to:

(i)	lightning, fire, earthquake, tsunami, flood, storm, cyclone, typhoon, or tornado, which has, in each case, affected the work or operations; or

(ii)	any Lapse of Consent of which report to Agency, the Independent Engineer and the Independent Auditor shall have been given under Section 7.6.2 and that shall have existed for less than thirty (30) consecutive days; or

(iii)	any strike, work-to-rule, go-slow, or analogous labour action that is not politically motivated or is not widespread or nationwide and that shall have existed for thirty (30) consecutive days or more; or

(iv)	explosion, chemical contamination, radioactive contamination or ionizing radiation; or

(v)	epidemic or plague.

(c)	Force Majeure Events shall expressly not include the following conditions, events or circumstances:

(i)	late delivery or interruption in the delivery of machinery, equipment materials, spare parts or consumables;

(ii)	a delay in the performance of any Contractor;

(iii)	a breakdown in machinery and/or equipment;

- normal wear and tear or random flaws in materials and equipment,

- a delay caused by rains and monsoons; and

provided, that each of the events described in clauses (c)(i), (ii), (iii), (iv) or (v) shall constitute a Force Majeure Event to the extent that such events or circumstances are caused by an event or circumstance that is in itself a Force Majeure Event whether experienced directly by the Concessionaire or by one of its Contractors.

## Obligation to Notify

    - The Parties acknowledge and agree that because Political Events and Non-Political Events constitute Relief Events pursuant to Section 15.1.1, the obligation of the Affected Party to notify the other Party, the Independent Engineer, and the Independent Auditor regarding the occurrence, mitigation, and ongoing effects of any Force Majeure Event shall be strictly and exclusively governed by the notice, reporting, and Relief Order Request procedures set forth in Article 15 (Relief Extensions & Relief Compensations) (the Force Majeure Notice).

    - The Affected Party shall provide all relevant details in respect of the Force Majeure Event in the Force Majeure Notice, including but not restricted to the following:

- the nature and extent of the Force Majeure Event;

- the estimated Force Majeure Period;

- the nature of and the extent to which, performance of any of the Affected Party’s obligations under this Agreement are affected by the Force Majeure Event;

- the measures which the Affected Party has taken or proposes to undertake to alleviate/mitigate the impact of the Force Majeure Event and to resume performance of such of its obligations that are affected by the Force Majeure Event; and

- any other relevant information concerning the Force Majeure Event, and/or the rights and obligations of the Parties under this Agreement.

    - The Parties shall, as soon as practicable upon the receipt of the Force Majeure Notice and in any case within five (5) days from the date of receipt of the same, convene a meeting, along with the Independent Engineer for the purpose of conducting discussions in good faith, and where necessary the Parties shall agree to conduct inspections and/or surveys of the Project in order to:

- assess the impact of the underlying Force Majeure Event;

- determine the likely duration of the Force Majeure Period; and

- formulate damage mitigation measures and the steps to be undertaken by the Parties for resumption of the obligations, the performance of which has been affected by the Force Majeure Event.

    - The Affected Party shall during the Force Majeure Period provide the other Party with regular (not less than weekly) reports in respect of the matters set out in Section 21.2.3 and such other information, details and / or documents that the other Party may reasonably require.

## Consequence of Force Majeure Event

    - Upon occurrence of a Force Majeure Event, the following shall apply:

- there shall be no Termination of this Agreement except in accordance with the provisions of Section 21.5 (Termination Notice for Force Majeure Event), Section 21.6 (Termination Payment for Force Majeure Event) and Article 23 (Termination);

- in the event of occurrence of a Force Majeure Event:

- subject to Section 21.8, the Concessionaire shall have the right to apply; for a Relief Order Request with respect to the extension of the Project

- Milestone Dates for the Project Milestones (affected by the Force Majeure Event), in accordance with the provisions of Article 15 (Relief Orders);

- all costs, fees, expenses and charges arising from and relating to the Force Majeure Event shall be allocated in accordance with Section 21.4 (Allocation of Costs Arising out of Force Majeure).

provided, however, that no relief, including extension of Time for Completion, shall be granted to the Affected Party to the extent that such failure or delay would nevertheless have been experienced by the Affected Party had the Force Majeure Event not occurred.

## Allocation of Costs Arising out of Force Majeure

    - Upon occurrence of a Force Majeure Event, the Force Majeure Costs shall be allocated as follows:

- upon occurrence of a Non-Political Event, all Force Majeure Costs shall be on the account of the Concessionaire and the Agency shall not be liable or responsible for the same in any manner;

- upon occurrence of a Political Event, the Agency shall fund and bear the Force Majeure Costs (as set out in a Relief Order) and in such case, the provisions of Article 15 (Relief Extensions & Relief Compensations) shall apply.

    - Save and except as expressly provided in this Section 21.4 (Allocation of Costs Arising out of Force Majeure) and, if applicable, Section 21.5 (Termination Notice For Force Majeure Event) and Section 21.6 (Termination Payment For Force Majeure Event), neither Party shall be liable in any manner whatsoever to the other Party in respect of any loss, damage, cost, expense, claims, demands and proceedings relating to or arising out of occurrence or existence of any Force Majeure Event or exercise of any right pursuant hereto.

## Termination Notice for Force Majeure Event

    - If:

(a)	a Force Majeure Event subsists for a continuous period of one hundred and twenty (120) days, either Party may in its discretion Terminate this Agreement by issuing a Termination Notice to the other Party; or

(b)	in case of a Political Event, the Agency determines that the Force Majeure Costs relating to the same are unacceptable then the  Agency may in its discretion Terminate this Agreement by issuing a Termination Notice to the Concessionaire,

in each case above, without being liable in any manner whatsoever, save as provided in this Section 21.5 (Termination Notice for Force Majeure Event) and Section 21.6 (Termination Payment for Force Majeure Event), and upon issue of such Termination Notice, this Agreement shall, notwithstanding anything to the contrary contained herein, stand Terminated forthwith; provided, that before issuing such Termination Notice, the Party intending to issue the Termination Notice shall inform the other Party of such intention and grant fifteen (15) days’ time to make a representation, and may after the expiry of such fifteen (15) days period, whether or not it is in receipt of such representation, in its sole discretion issue the Termination Notice.

## Termination Payment for Force Majeure Event

    - If Termination is on account of a Non-Political Event, the Agency shall make a Termination Payment to the Concessionaire on or prior to the Termination Payment Date in an amount equal to the Non-Political Event Termination Amount.

    - If Termination is on account of a Political Event, the Agency shall make a Termination Payment to the Concessionaire on or prior to the Termination Payment Date in an amount equal to the Political Event Termination Amount.

## Force Majeure Dispute Resolution

    - In the event that the Parties are unable to agree in good faith about the occurrence or existence of a Force Majeure Event, such Dispute shall be finally settled in accordance with the Dispute Resolution Procedure; provided, that the burden of proof as to the occurrence or existence of such Force Majeure Event shall be upon the Party claiming relief and/or excuse on account of such Force Majeure Event.

## Excuse From Performance of Obligations

    - If the Affected Party is rendered wholly or partially unable to perform its obligations under this Agreement because of a Force Majeure Event, it shall be excused from performance of such of its obligations (except payment obligations) to the extent it is unable to perform on account of such Force Majeure Event; provided, that:

- the suspension of performance shall be of no greater scope and of no longer duration than is reasonably required by the Force Majeure Event and/or of the effects of the same;

- the Affected Party shall make all reasonable efforts to mitigate or limit damage to the other Party arising out of or as a result of the existence or occurrence of such Force Majeure Event and to cure the same with due diligence; and

- when the Affected Party is able to resume performance of its obligations under this Agreement, it shall give to the other Party (with a copy to the Independent Engineer and the Independent Auditor) notice to that effect and shall promptly resume performance of its obligations hereunder.

# Events of Default

## Concessionaire Event of Default

    - Any of the following events shall constitute an event of default by the Concessionaire (the Concessionaire Event of Default) unless such event has occurred as a consequence of Permitted Events:

- any Material Breach by the Concessionaire or the Sponsor of any  Agency Agreement which Material Breach has not been cured within sixty (60) days from the date of written notice thereof by the  Agency, or within such time period as provided in the relevant  Agency Agreement, respectively;

- the Concessionaire fails to commence the Development Works within thirty (30) days from the Commencement Date;

- the Concessionaire fails to achieve Substantial Completion by the date falling one hundred and twenty (120) days following the Scheduled Substantial Completion Date;

- any statement, representation or warranty made by the Concessionaire in this Agreement proving to have been incorrect, in any material respect, when made or when reaffirmed and such incorrect statement, representation or warranty having a Material Adverse Effect on the Concessionaire’s ability to perform its obligations under this Agreement and/or on the Project or having a Material Adverse Effect on the rights and/or obligations of the Agency hereunder or under the Agency Agreements;

- the Concessionaire creates any Encumbrance on the Concession Assets in favor of any Person save and except as otherwise expressly permitted in terms of this Agreement;

- the transfer of the rights and/or obligations of the Concessionaire under this Agreement, save and except as permitted in terms of this Agreement; and/or

- except for the purpose of amalgamation or reconstruction (provided, that such amalgamation or reconstruction does not affect the ability of the amalgamated or reconstructed entity, as the case may be, to perform its obligations under this Agreement and further provided, that such amalgamation has been agreed to by the  Agency), the occurrence of any of the following events:

(i) 	the passing of a resolution for the dissolution or winding up of the Concessionaire;

(ii) 	the voluntary filing by the Concessionaire of a petition of bankruptcy, moratorium, winding up, or other similar relief;

(iii) 	the appointment of a provisional liquidator in a proceeding for the winding up of the Concessionaire after notice to the Concessionaire and due hearing, which appointment has not been set aside or stayed within ninety (90) days of such appointment;

(iv) 	the making by a court with jurisdiction over the Concessionaire of an order winding up the Concessionaire that is not stayed or reversed by a court of competent authority within ninety (90) days; and/or

(v)	any proceeding being validly instituted under the Applicable Laws for the dissolution of the Concessionaire or attachment of the Concession Assets in accordance with Applicable Laws that has a Material Adverse Effect and that is not stayed or suspended within ninety (90) days; provided, that, if, within seven (7) business days of the Concessionaire becoming aware of such proceedings being filed, the Concessionaire:

(A)	confirms to the  Agency that such proceedings relate to the recovery of a claim against the Concessionaire that is disputed bona fide by the Concessionaire as payable, and

(B)	furnishes a certificate by the Independent Auditor to the effect that the Concessionaire is and shall remain solvent despite the payment of the claim subject to the said insolvency proceedings,

then, in such case, the Concessionaire Event of Default set forth in Section 22.1.1(g)(v) shall not constitute a Concessionaire Event of Default until such time that the said certificate by the Independent Auditor is revoked or otherwise ceases to remain accurate;

- an Abandonment by the Concessionaire, without the prior written consent of the Agency, for a period of thirty (30) consecutive days or for an aggregate period of sixty (60) days during any Accounting Year; provided, however, that the Concessionaire shall not be deemed to have Abandoned the Concession Assets so long as it is using all reasonable efforts (as determined by the Independent Engineer) to regain control of the Concession Assets and reinstate its development and/or Operation and Maintenance, as applicable;

- the Concessionaire is in Material Breach of O&M Requirements;

- any other events or circumstances expressly set out in this Agreement as a Concessionaire Event of Default;

- the  Development Performance Security or the O&M Performance Security, in each case, is not issued, renewed, replaced or provided (as the case may be) in accordance with this Agreement or becomes inoperative or ceases to remain valid or in force in breach of the relevant provisions of this Agreement;

- a breach by the Concessionaire of its obligation to take out and maintain the required Insurances in accordance with Article 20 (Insurances);

- the Concessionaire or the Sponsor repudiate/terminate any of the Agency Agreements or otherwise evidence an intention not to be bound by the same;

- termination of the  Project Site Land Instrument as a result of a material breach by the Concessionaire that is not remedied in accordance with the terms of the Project Site Land Instrument;

- the Concessionaire has delayed any payment that has fallen due and payable under this Agreement and any of the Agency Agreements and if such delay exceeds sixty (60) days, save where such payment is duly Disputed by the Concessionaire in accordance with this Agreement;

- any assets or shares of the Concessionaire are expropriated, confiscated, compulsorily acquired or nationalised by any Government Authority or entity due to an act or omission of the Concessionaire or its shareholders, causing a Material Adverse Effect;

- a material breach by the Development Contractors, the O&M Contractors or any other subcontractor or any of the parties to the Agency Agreements or any of their respective contracts with the Concessionaire having a Material Adverse Effect;

- the Concessionaire fails to achieve Project Development Completion in accordance with the Applicable Standards and/or the timelines set-out in the Applicable Standards (in each case, as certified by the Independent Engineer), which failure continues for a period of thirty (30) days;

- the right of the  Agency to Terminate this Agreement in accordance with Section 3.4.1.

## Agency Event of Default

    - The following events shall constitute events of default by the Agency (the  Agency Event of Default), unless such event has occurred and/or has resulted from a Concessionaire Event of Default or a Force Majeure Event:

- any Material Breach by the Agency of any Agency Agreement and the same has not been cured within sixty (60) days from the date of written notice thereof by the Concessionaire, or within such time period as provided in the relevant  Agency Agreement, respectively;

- any statement, representation or warranty made by the Agency in any Agency Agreement proving to have been incorrect, in any material respect, when made or when reaffirmed and such incorrect statement, representation or warranty having a Material Adverse Effect on the Concessionaire’s ability to perform its obligations under this Agreement and/or on the Project;

- any termination, cancellation, resumption or revocation of the Concessionaire’s interest established under the Project Site Land Instrument in respect of the Project Site (otherwise than for a breach of the conditions of the  Project Site Land Instrument by the Concessionaire entitling such termination, cancellation, resumption or revocation);

- any change in any Applicable Laws:

(i)	making unenforceable, invalid, or void any material undertaking of the Agency under the Agency Agreements; and/or

(ii)	making:

(A)	it unlawful for the Concessionaire, the Financiers or the Sponsors to make or receive any payment, to perform any material obligation or to enjoy or enforce any material right under any  Agency Agreement (other than a Change in Law for which compensation is provided in accordance with this Agreement); or

(B)	any payment, the performance of any material obligation or the enjoyment or enforcement of any material right unenforceable under any  Agency Agreement, invalid or void as a result of any such change in Applicable Laws (other than a Change in Law for which compensation is provided in accordance with this Agreement);

- the expropriation, compulsory acquisition, or nationalization by the Agency or any Government Authority of: (i) any Sponsor Shares in the Concessionaire; or (ii) any Concession Assets or rights of the Concessionaire;

- any change in, or any change in the interpretation of, any of the Applicable Laws (including the Constitution of Pakistan and any other Applicable Laws that gives effect to the injunctions of Islam, being in the case of a decision of a court, a decision which is no longer in suspense as a result of an appeal) from and after the date of this Agreement having the effect of making:

(i)	unlawful, unenforceable, invalid, or void any material undertaking of the  Agency under any  Agency Agreement; or

(ii)	unlawful for the Concessionaire to make or receive or the Financiers or the Sponsors to receive any payment (including interest or return), for the Concessionaire to perform any material obligation or to enjoy or enforce any material right under this Agreement or any other Project Agreement in relation to the Project; or

(iii)	any such payment, the performance of any such material obligation or the enjoyment or enforcement of any such material right becoming unenforceable, invalid or void as a result of any such change in the Applicable Laws,

which in the case of (i), (ii) or (iii) above, has a continuing effect for more than one hundred and eighty (180) days without an arrangement being provided to exempt the affected party from the effect of such Change in Law (other than a Change in Law for which compensation is provided in accordance with this Agreement);

- the Agency has delayed any payment certified by the Independent Engineer and the Independent Auditor that has fallen due and payable under this Agreement and/or any of the Agency Agreements and if such delay exceeds ninety (90) days, save where such payment is duly Disputed by the Agency in accordance with this Agreement and/or Agency Agreements; and

- the right of the Concessionaire to terminate the Agreement in accordance with Section 3.4.2.

22.3.2 If the defaulting Party fails to remedy the default within the applicable Cure Period, the non-defaulting Party shall be entitled to Terminate this Agreement in accordance with Article 23 (Termination).

# Termination

## Termination for Concessionaire Event of Default

    - Without prejudice to any other right or remedy which the  Agency may have in respect thereof under this Agreement, upon the occurrence and continuation of a Concessionaire Event of Default, the Agency shall be entitled to Terminate this Agreement by issuing a Termination Notice to the Concessionaire; provided, that before issuing the Termination Notice, the  Agency shall by a notice in writing inform the Concessionaire of its intention to issue the Termination Notice (the  Agency Preliminary Notice).

    - In the event the underlying Concessionaire Event of Default is not cured within the Cure Period and the same is subsisting at the expiry of the Cure Period, the  Agency shall be entitled to:

- Terminate this Agreement by issuing the Termination Notice upon expiry of the Cure Period; and

- encash the Development Performance Security or the O&M Performance Security, as applicable and in effect at such time, on or following the issuance of the Termination Notice.

    - The following shall apply in respect of Cure Period relating to a Concessionaire Event of Default:

- the Cure Period provided in this Agreement shall not relieve the Concessionaire from liability for damages (as expressly set out in this Agreement), if any, caused by its underlying breach or default giving rise to the Agency Preliminary Notice; and

- the Cure Period shall not in any way be extended by any period of Suspension under this Agreement.

    - Upon issuance of a Termination Notice by the  Agency (following expiry of the Cure Period) on account of occurrence and continuation of a Concessionaire Event of Default during the Operations Period, the right of the Concessionaire to collect Revenues shall stand terminated, with immediate effect and no Revenues shall accrue and/or be payable to the Concessionaire from the date of the Concessionaire’s receipt of the Termination Notice .From the date of receipt of an Agency Preliminary Notice until the default is cured or the Termination Date occurs, the Concessionaire is strictly prohibited from making any distributions to its Shareholders.

    - The Parties agree that from the date of the Agency Preliminary Notice and until the expiry of the applicable Cure Period, the Revenue shall be managed in the following manner:

- all Revenue collected shall be deposited into a dedicated Escrow Account managed by an Escrow Agent mutually appointed by the Parties;

- no funds shall be withdrawn or disbursed from the Escrow Account, save and except for mandatory O&M Costs and payments to Financiers, in each case, as verified and approved by the Independent Auditor; and

- if Termination occurs, the remaining credit balance in the Escrow Account shall be applied in accordance with the Order of Priority following the Termination Date.

    - In the event of Termination due to a Concessionaire Event of Default, the  Agency shall pay to the Concessionaire on or prior to the Termination Payment Date, by way of Termination Payment, an amount equal to the Concessionaire Default Termination Amount.

## Termination For Agency Event Of Default

    - Without prejudice to any other right or remedy which the Concessionaire may have in respect thereof under this Agreement, upon the occurrence and continuation of any of any Agency Event of Default, the Concessionaire shall by a notice in writing inform the  Agency of its intention to issue the Termination Notice (the Concessionaire Preliminary Notice).

    - In the event the underlying  Agency Event of Default is not cured by the  Agency within the Cure Period and the same is subsisting at the expiry of the Cure Period, the Concessionaire shall be entitled to Terminate this Agreement by issuing the Termination Notice upon expiry of the Cure Period.

    - In the event of Termination due to an Agency Event of Default, the  Agency shall have the obligation to pay to the Concessionaire on or prior to the Termination Payment Date, by way of Termination Payment, an amount equal to the  Agency Default Termination Amount.

## Termination for Corrupt Acts

    - The Concessionaire warrants that in entering into this Agreement it has not committed any Corrupt Act.

    - If any Corrupt Act is committed, then the Agency shall be entitled to act in accordance with the following provisions of this Section 23.3; provided, that at all times the  Agency shall bear the burden of proof for establishing that a Corrupt Act has been committed:

- if the Corrupt Act is committed by the Concessionaire or any Associate of the Concessionaire, as the case may be, then in any such case, the Agency may issue a notice to the Concessionaire of its intent to issue a Termination Notice;

- if the Corrupt Act is committed by an employee of the Concessionaire, then in such case, the Agency may give written notice to the Concessionaire of its intention to issue a Termination Notice; provided, however, the  Agency shall not be entitled to issue a Termination Notice in the event the Concessionaire, within forty-five (45) days of its receipt of the Agency’s notice stating its intention to issue a Termination Notice, terminates such employee’s involvement in the Project and (if necessary) provides evidence to the Agency of the performance of any part of the Project deliverables previously performed by such employee by another person;

- if the Corrupt Act is committed by any other person not specified in sub-section (b) above but involved in the Project as a subcontractor or supplier to any Contractor or to the Concessionaire, then the  Agency may give notice to the Concessionaire of its intention to issue a Termination Notice; provided, however, that the Agency shall not be entitled to issue a Termination Notice in the event the Concessionaire, within thirty (30) days of its receipt of the Agency’s notice stating its intention to issue a Termination Notice, procures the termination of such person’s involvement in the Project and (if necessary) procures the performance of the relevant contract and procures the performance of the relevant part of the Project Works by another person.

    - Any notice of intention to issue a Termination Notice by the  Agency under this Section 23.3 shall specify:

- the nature of the Corrupt Act;

- the identity of the party or parties who the Agency believes has committed the Corrupt Act; and

- the date on which the Termination Notice shall be issued, which date shall be subject to the timelines provided in Section 23.3.2(b) and (c), as applicable.

    - Without prejudice to its other rights or remedies under this Section, the  Agency shall be entitled to recover from the Concessionaire, the greater of:

- the amount or value of the gift, consideration or commission which is the subject of the Corrupt Act; and

- any direct losses (including Losses) sustained by the Agency in consequence of any breach of this Section by the Concessionaire.

    - Nothing contained in this Section shall prevent the Concessionaire from paying any proper commission or bonus to its employees within the agreed terms of their employment.

    - In the event of Termination due to a Corrupt Act in accordance with this Section 23.3, the Agency shall have the obligation to pay to the Concessionaire on or prior to the Termination Payment Date, by way of Termination Payment, an amount equal to the Corrupt Act Termination Amount.

## Rights of the  Agency on Termination and/or Final Expiry Date

    - In case of Termination of this Agreement for any reason whatsoever and subject to receipt by the Concessionaire of the Termination Payment on or prior to the Transfer Date or in case of expiry of this Agreement on the Final Expiry Date, the  Agency shall, on the Transfer Date, have the power and authority to:

- take possession and control of the Concession Assets;

- prohibit the Concessionaire and any person claiming through or under the Concessionaire from entering upon the Concession Assets or dealing with the Concession Assets or any part thereof .

23.4.2 Notwithstanding the issuance of a Termination Notice, if the Termination Payment is not received in full by the Concessionaire by the Termination Payment Date, the Concessionaire shall have the right (but not the obligation) to remain in possession of the Concession Assets and continue to operate the Project and collect all Revenue until such time as the Termination Payment is received in full.

## Termination Payments

    - The Termination Payment shall be payable to the Concessionaire by the Agency on or prior to the Termination Payment Date in accordance with a demand being made by the Concessionaire in writing, subject to the same being duly certified by the Independent Engineer and Independent Auditor. Within thirty (30) Business Days of receipt of a written demand from the Concessionaire, the Independent Engineer and the Independent Auditor shall jointly issue such certificate.If the Termination Payment becomes subject to any tax (corporate tax, minimum tax or alternate corporate tax), the Agency shall pay to the Concessionaire such additional compensation (as determined by the Independent Auditor) such that the net amount received by the Concessionaire after deduction of any tax shall be equal to the total Termination Payment that would have been received had no such tax been paid or incurred.

    - The recipients of the Termination Payment shall be shareholders of the Sponsor Shares, provided however, for the purposes of calculating the Termination Payment, the term Equity shall exclude all amounts comprising injections to the Equity effected after the Project Development Completion Date; provided, that such amounts shall constitute Equity to the extent the same are part of the Pre-Estimated Project Cost and determined by the Independent Auditor to be part of the Total Project Cost.

    - To the extent:

- the Termination Equity and/or Termination Dividend Amount is payable by the Agency to the Concessionaire upon Termination of this Agreement; and

- the Agency fails to make payment of such due and payable Termination Equity and/or Termination Dividend Amount (the Unpaid Termination Equity Amount) by the date falling fifty (50) days following the Termination Payment Date,

then, the  Agency shall (in addition to the payment of the due and payable Unpaid Termination Equity Amount) make payment to the Concessionaire of late payment interest on the Unpaid Termination Equity Amount at the Delayed Payment Rate, such interest commencing to accrue on the date falling fifty (50) days following the Termination Payment Date and ending on the actual date on which the Agency makes payment of the Unpaid Termination Equity Amount. The stipulation regarding additional amounts payable in respect of delayed Unpaid Termination Equity Amount contained in this Section 23.5.2 shall not be construed nor be deemed to authorize any delay in payment of any amount due to the Concessionaire nor be construed or deemed to be a waiver of the underlying breach of payment obligations, in each case, in the afore-stated circumstances.

## Mode of Payment

    - Notwithstanding anything to the contrary contained in this Agreement, any Termination pursuant to the provisions of this Agreement shall be without prejudice to accrued rights of either Party including its right to claim and recover money damages and other rights and remedies which it may have in law or contract. All rights and obligations of either Party under this Agreement, including without limitation Termination Payment, shall survive the Termination of this Agreement to the extent such survival is necessary for giving effect to such rights and obligations.

# Divestment of Rights and Interest

## Requirements for Divestment

    - In case of (as applicable):

- Termination of this Agreement prior to Final Expiry Date and subject to the  Agency fully complying with all its obligations in respect of making Termination Payments on or prior to the Termination Payment Date; or

- one (1) year prior to expiry of this Agreement on the Final Expiry Date, the Concessionaire shall comply with and conform complete compliance with the following requirements by the Transfer Date (the Divestment Requirements);

- Notify to the Agency forthwith the location and particulars of all Concession Assets;

- deliver forthwith the actual or constructive possession of the Concession Assets, free and clear of all Encumbrances;

- unless this Agreement is Terminated due to a Permitted Event (excluding Non-Political Event), cure all Concession Assets of all Defects & Deficiencies in accordance with the Handover List; provided, that in the event of Termination during the  Development Period, all Concession Assets shall be handed over on ‘as is where is’ basis after bringing them to a safe condition;

- deliver and transfer all relevant records, reports, intellectual property and other Licenses pertaining to the Concession Assets and its design, engineering, development, Operation and Maintenance, including all programs and manuals pertaining thereto and the O&M Documents as on the Transfer Date;

- transfer and/or deliver to the  Agency, all Concessionaire Permits to the extent permissible under Applicable Laws;

- execute such deeds of conveyance, documents and other writings as the  Agency may reasonably require for conveying, divesting and assigning all the rights, title and interest of the Concessionaire in the Concession Assets, including manufacturers’ warranties in respect of any plant or equipment and the right to receive outstanding insurance claims, absolutely unto the Agency or its nominee; and

- train all staff notified by the  Agency for Operations and Maintenance in accordance with the O&M Manual; and

- comply with all other requirements as may be prescribed or required under Applicable Laws for completing the divestment and assignment of all rights, title and interest of the Concessionaire in the Concession Assets, free from all Encumbrances, absolutely unto the Agency or to its nominee.

    - The Agency may, in its sole discretion, waive any of the Divestment Requirements set forth in Section 24.1.1.

## Inspection and Cure

    - In case of:

- Termination during the Operations Period, not earlier than thirty (30) days prior to Termination but not later than fifteen (15) days prior to the Transfer Date; or

- expiry of this Agreement on the Final Expiry Date, not earlier than twelve (12) months prior to Transfer Date but not later than six (6) months prior to the Transfer Date,

the Independent Engineer shall verify, after giving due notice to the Concessionaire of the time, date and venue of such verification, compliance by the Concessionaire with the Applicable Standards, and if required, cause appropriate tests to be carried out. In the event of Termination (excluding Termination due to Political Event or a  Agency Event of Default) or expiry of this Agreement on the Final Expiry Date, the Concessionaire shall bear the cost for this purpose. In the event of Termination due to  Agency Event of Default or Political Event, the  Agency shall bear the cost for this purpose. All Defects & Deficiencies shall be cured by the Concessionaire at its cost unless the same is due to a Political Event or a  Agency Event of Default in which case, the  Agency shall bear such costs.

    - Until the Transfer Date, all risks shall vest with the Concessionaire for loss of or damage to the whole or any part of the Concession Assets and following the Transfer Date, all risks in relation to the same shall be deemed to have been transferred to and vest with the  Agency.

## Cooperation and Assistance for Transfer of the Concession Assets

    - The Parties shall cooperate on a best effort basis and take all necessary measures, in good faith, to achieve a smooth transfer of the Concession Assets in accordance with the provisions of this Agreement so as to protect the safety of and avoid undue delay or inconvenience to the users, other members of the public or the lawful occupiers of any part of the Project Site and the Concession Assets.

    - The Parties shall provide to each other (as applicable):

- in case of Termination of this Agreement, two (2) months prior to the Termination Payment Date in the event of Termination and immediately in the event of either Party conveying to the other Party its intent to issue a Termination Notice, as the case may be; or

- in case of expiry of this Agreement on the Final Expiry Date, six (6) months prior to the Final Expiry Date,

as much information and advice as is reasonably practicable regarding the proposed arrangements for operation of the Project following the Transfer Date. The Concessionaire shall further provide such reasonable advice and assistance as the Agency, its appointed concessionaire or agent may reasonably require for operation of the Project until the Transfer Date.

## Vesting Certificate

    - Subject to:

- in case of Termination of this Agreement, the Agency fully complying with all its obligations in respect of making Termination Payments on or prior to the Termination Payment Date; or

- expiry of this Agreement on the Final Expiry Date,

the divestment of all rights, title and interest in the Project shall be deemed to be complete on the Transfer Date, and the Independent Auditor and the Independent Engineer shall jointly, without unreasonable delay, thereupon issue a certificate (the Vesting Certificate) substantially in the form set forth in Schedule O (Form of Vesting Certificate), which shall have the effect of constituting evidence of divestment by the Concessionaire of all of its rights, title and interest in the Concession Assets, and their vesting in the  Agency pursuant hereto.

## Transfer Consideration

    - The Parties agree that the Concession Assets shall be transferred to the Agency on the Transfer Date for a sum of (as consideration) PKR 1/- (Pakistani Rupees One only).

## Divestment Costs

    - Subject to Section 24.6.2, the Concessionaire shall bear and pay, in case of Termination due to a Concessionaire Event of Default and/or due to Corrupt Act and/or due to a Non Political Event or in case of expiry of this Agreement on the Final Expiry Date, all costs incidental to divestment of all of the rights, title and interest of the Concessionaire in the Concession Assets in favor of the Agency, save and except that all stamp duties payable on any deeds or documents executed by the Concessionaire in connection with such divestment shall be borne by the Agency. In the event of Termination due to a Force Majeure Event and/or a Agency Event of Default, the Agency shall bear and pay all the above-mentioned costs.

    - The Agency shall be responsible for the costs and expenses, including stamp duties, taxes, legal fees and expenses incurred in connection with the transfer of the Concession Assets to the Agency or its nominated agency on the Transfer Date. The Agency shall at its own cost obtain or effect all clearances, permits, authorizations, consents and approvals under or pursuant to Applicable Laws and take such other actions as may be necessary for such transfer.

    - In the event of any Dispute relating to matters covered by and under this Article 24 (Divestment of Rights and Interest), the Dispute Resolution Procedure shall apply.

## Transfer Bond

    - The Concessionaire shall provide Transfer Bond:

- no later than eight (8) months prior to the Final Expiry Date, the Concessionaire shall provide to the Agency a performance security to ensure the seamless handback of the Concession Assets (the Transfer Bond);

- for an amount equal to two percent (2%) of the Total Project Cost, and shall be provided in the form of cash, a bank draft, an irrevocable letter of credit from an Acceptable Pakistani Bank, or an AA-rated insurance bond;

- which shall entitle the Agency to draw upon the certification by the Independent Engineer of the Concessionaire’s failure to complete any handback requirements.

# Defects Liability During Exit Implementation Period

## Liability for Defects During Exit Implementation Period

    - Without prejudice to any obligation of the Concessionaire in this Agreement and subject to Section 24.1.1(c), the Concessionaire shall be responsible for all Defects & Deficiencies in the Concession Assets during the Exit Implementation Period in accordance with this Section 25.1.1 and it shall have the obligation to repair or rectify all Defects & Deficiencies observed by the Independent Engineer in the Concession Assets during the aforesaid period, as set out in a list jointly prepared by the Independent Engineer and the Concessionaire (the Handover List) within:

- in case of Termination of this Agreement, one (1) year of the issuance of a Termination Notice; or

- in case of expiry of this Agreement on the Final Expiry Date, one (1) year after the Final Expiry Date;

the aforesaid period in each case of part (a) and (b) above shall be referred to as the defects liability period (the Defects Liability Period).

    - Notwithstanding anything to the contrary set out herein, the provisions of this Article 25 (Defects Liability During Exit Implementation Period) shall not apply to any Defects & Deficiencies caused by an Agency Event of Default or a Political Event that has resulted in Termination.

# Disclaimer

## Disclaimer

    - Subject to the terms of this Agreement, the Concessionaire acknowledges that prior to the execution of this Agreement, the Concessionaire has, after a complete and careful examination and due diligence, made an independent evaluation of the Concession, the RFP, the Scope of the Project, the Project Requirements, the Project Site, existing structures, local conditions, physical qualities of ground, subsoil and geology and all information provided by the Agency or obtained, procured or gathered otherwise, and has determined to its satisfaction the accuracy or otherwise thereof and the nature and extent of difficulties, risks and hazards as are likely to arise or may be faced by it in the course of performance of its obligations hereunder and on the basis of such examination and determinations is entering into this Agreement for the purpose of accepting the Concession for the implementation of the Project in accordance with the terms and conditions of this Agreement. Except as expressly provided in this Agreement, the Agency makes no representation whatsoever, express, implicit or otherwise, regarding the accuracy, adequacy, correctness, reliability and/or completeness of any assessment, assumptions, statement or information provided by it and the Concessionaire confirms that it shall have no claim whatsoever against the Agency in this regard.

    - Subject to the terms of this Agreement, the Concessionaire acknowledges and hereby accepts the risk of inadequacy, mistake or error in or relating to any of the matters set forth in Section 26.1.1 and hereby acknowledges and agrees that the Agency shall not be liable for the same in any manner whatsoever to the Concessionaire, the Sponsors and their Associates or any person claiming through or under any of them.

    - Any mistake or error in or relating to any of the matters set forth in Section 26.1.1 shall not vitiate this Agreement or render it voidable.

    - In the event that either Party becomes aware of any mistake or error relating to any of the matters set forth in sub-section 26.1.1 of this Section 26.1 (Disclaimer) above, such Party shall immediately notify the other Party, specifying the mistake or error; provided, however, it is expressly agreed between the Parties that any such failure on part of the Agency to give any notice pursuant to this sub-section 26.1.4 of Section 26.1 (Disclaimer) shall not prejudice the disclaimer of the Agency contained in sub-section 26.1.1 of this Section 26.1 (Disclaimer) and shall not in any manner shift to the Agency any risks assumed by the Concessionaire pursuant to this Agreement.

    - Except as otherwise provided in this Agreement, all risks relating to the Concession Assets shall be borne by the Concessionaire and the Agency shall not be liable in any manner for such risks or the consequences thereof.

# Assignment and Charges

## Restriction on Assignment and Charges

    - Neither Party may sell, assign, or transfer its rights or obligations under or pursuant to this Agreement without prior written consent of the other Party. The Concessionaire shall not:

- create nor permit to subsist any Encumbrance, or otherwise transfer or dispose of all or any of its rights and benefits under this Agreement; or

- create or permit to subsist any Encumbrance on the Concession Assets or otherwise transfer or dispose of the Concession Assets;

in each case above, except with prior consent in writing of the Agency, which consent the Agency shall be entitled to decline without assigning any reason.

## Permitted Assignment and Charges

    - The restriction set forth in sub-section 27.1.1 of Section 27.1 (Restriction on Assignment and Charges) shall not apply to liens and Encumbrances arising by operation of law (or by an agreement evidencing the same) in the ordinary course of business of the Project.

## Late Payment

    - [In the event, any sum payable by one Party to the other under this Agreement is not paid within the time allowed, the defaulting Party shall pay an additional amount on such sum at a rate of two percent (2%) per annum above the six (6) month KIBOR as at the due date, calculated from the due date until payment. This additional amount shall be the agreed compensation for delayed receipt and without prejudice to any other right or remedy available.

    - If a Party fails to make any payment due under this Agreement within sixty (60) days of the due date, the other Party shall have the right to set-off any such overdue amount (including interest accrued under Section 27.6.1) against any payment it is obliged to make to the defaulting Party under this Agreement.]

# Dispute Resolution

## Dispute Resolution

    - Any dispute, difference or controversy of whatever nature howsoever arising under or out of or in relation to this Agreement (including its interpretation) between the Parties, and so notified in writing by either Party to the other Party (the Dispute) shall, in the first instance, be attempted to be resolved amicably in accordance with the conciliation procedure set forth in Section 28.2 (Conciliation).

    - The Parties agree to use their best efforts for resolving all Disputes promptly, equitably and in good faith, and further agree to provide each other with reasonable access during normal business hours to all non-privileged records, information and data pertaining to any Dispute.

## Conciliation

    - In the event of any Dispute between the Parties, either Party may call upon the Independent Engineer and/or the Independent Auditor, as the case may be, to mediate and assist the Parties in arriving at an amicable settlement thereof. Failing mediation by the Independent Engineer and/or the Independent Auditor as the case may be, either Party may request for their departmental heads to meet to resolve such Dispute. In the event the Parties are unable to resolve the matters through conciliation, within thirty (30) days of commencement of the conciliation process in terms of this Section 28.2.1, either Party may refer the Dispute to arbitration in accordance with the provisions of Section 28.3 (Arbitration).

## Arbitration

    - Any Dispute which is not resolved amicably by conciliation, as provided in Section 28.2 (Conciliation), shall be finally decided by reference to arbitration by a board of arbitrators (the Board of Arbitrators) appointed in accordance with Section 28.3.3. Such arbitration shall be held in accordance with the provisions of the Arbitration Act.

    - The venue and seat of such arbitration shall be Karachi.

    - There shall be a Board of Arbitrators consisting of three (3) arbitrators, of whom each Party shall select one, and the third arbitrator shall be appointed by the two (2) arbitrators so selected, and in the event the two (2) arbitrators are unable to agree on the third arbitrator, then the same shall be appointed in accordance with the Arbitration Act.

    - The arbitrators shall make a reasoned award (the Award). Any Award made in any arbitration held pursuant to this Article 30 (Dispute Resolution) shall be final and binding on the Parties as from the date it is made, and the Concessionaire and the Agency agree and undertake to carry out such Award without delay.

    - The Concessionaire and the Agency agree that an Award may be enforced against the Concessionaire and/or the Agency, as the case may be, and their respective assets wherever situated.

    - [This Agreement and the rights and obligations of the Parties shall remain in full force and effect, pending the Award in any arbitration proceedings hereunder. Specifically, the Agency shall not withhold, set-off, or delay the payment of any amounts due and payable to the Concessionaire (including but not limited to Relief Compensations, or any additional costs) on the grounds that a Dispute has been referred to concilationor arbitration. All such payment obligations shall be performed in a timely manner as per the terms of this Agreement, and the Agency expressly waives any right to use the existence of a Dispute as leverage to suspend its financial obligations.]

# Miscellaneous

## Governing Law and Jurisdiction

    - This Agreement shall be construed and interpreted in accordance with and governed by the laws of Pakistan and the courts of appropriate jurisdiction in the Project Jurisdiction shall have the exclusive jurisdiction over all Disputes or matters arising out of or relating to this Agreement.

## Waiver

    - Waiver by either Party of any default by the other Party in the observance and performance of any provision of or obligations under this Agreement:

- shall not operate or be construed as a waiver of any other or subsequent default hereof or of other provisions or obligations under this Agreement;

- shall not be effective unless it is in writing and executed by a duly authorized representative of such Party; and

- shall not affect the validity or enforceability of this Agreement in any manner.

    - Neither the failure by either Party to insist on any occasion upon the performance of the terms, conditions and provisions of this Agreement or any obligation thereunder nor time or other indulgence granted by a Party to the other Party shall be treated or deemed as waiver of such breach or acceptance of any variation or the relinquishment of any such right hereunder.

## Amendments

    - This Agreement and the Schedules together constitute a complete and an exclusive statement of the terms of this Agreement between the Parties on the subject hereof and no amendment or modification hereto shall be valid and effective unless agreed to by all the Parties hereto and evidenced in writing. This Agreement may only be amended or supplemented by a written agreement signed by the duly authorized representatives of both Parties.

## Notices

    - Unless otherwise stated, notices to be given under this Agreement including but not limited to a notice of waiver of any term, breach of any term of this Agreement and Termination of this Agreement, shall be in writing and shall be given by hand delivery, recognized international courier, mail, telex or facsimile transmission and delivered or transmitted to the Parties at their respective addresses set forth below in Schedule S (Notices) or such address, telex number, or facsimile number as may be duly notified by the respective Parties from time to time, and shall be deemed to have been made or delivered (a) in the case of any communication made by letter, when delivered by hand, by recognized international courier or by mail (registered, return receipt requested) at that address and (b) in the case of any communication made by telex or facsimile, when transmitted properly addressed to such telex number or facsimile number.

## Survival

    - Termination of this Agreement (a) shall not relieve the Concessionaire or the Agency of any obligations hereunder which expressly or by implication survives Termination hereof, and (b) except as otherwise provided in any provision of this Agreement expressly limiting the liability of either Party, shall not relieve either Party of any obligations or liabilities for loss or damage to the other Party arising out of or caused by acts or omissions of such Party prior to the effectiveness of such Termination or arising out of such Termination.

## Confidentiality

    - Each of the Parties and their Contractors (including the Concessionaire Engaged Persons), subcontractors, consultants, employees and agents and each of their respective successors and permitted assigns shall hold in confidence all documents and other information, whether technical or commercial, supplied to it by or on behalf of the other Party, relating to the design, development, insurance, Operation and Maintenance, transfer and management of the Concession Assets, and all information and documents obtained in accordance with the terms of the Agency Agreements, and shall not, without the consent of the other Party, save as required by Applicable Laws or appropriate regulatory authorities, prospective lenders to, or investors in the Concessionaire and their professional advisers, publish or otherwise disclose or use the same for its own purposes otherwise than as may be required to perform its obligations under this Agreement.  Notwithstanding the above, nothing herein contained shall preclude the use of provisions similar to those contained in the Agency Agreements and the other agreements referred to herein and in agreements prepared and issued or to be prepared and issued in connection with other projects by the Agency.

## The provisions of Paragraph (a) hereabove shall not apply to:

## any information in the public domain otherwise than by breach of this Agreement or any other Agency Agreement;

## (b)	information in the possession of the receiving Party thereof before divulgence as aforesaid, and which was not obtained under any obligation of confidentiality.

## Severability

    - If for any reason whatever any provision of this Agreement is or becomes invalid, illegal or unenforceable or is declared by any court of competent jurisdiction or any other instrumentality to be invalid, illegal or unenforceable, the validity, legality or enforceability of the remaining provisions shall not be affected in any manner, and the Parties shall negotiate in good faith with a view to agreeing upon one or more provisions which may be substituted for such invalid, unenforceable or illegal provisions, as nearly as is practicable.

## No Partnership

    - Nothing contained in this Agreement shall be construed or interpreted as constituting a partnership between the Parties. Neither Party shall have any authority to bind the other in any manner whatsoever.

    - Notwithstanding anything to the contrary set out in this Agreement or elsewhere, nothing contained in this Agreement shall be construed or interpreted as the Concessionaire providing design and/or engineering consulting services to the Agency.

## Language

    - All notices required to be given under this Agreement and all communications, documentation and proceedings which are in any way relevant to this Agreement shall be in writing and in the English language.

## Exclusion of Implied Warranties

    - This Agreement expressly excludes any warranty, condition or other undertaking implied at law or by custom or otherwise arising out of any other agreement (except the Agency Agreements) between the Parties or any representation by any Party not contained in a binding legal agreement executed by the Parties.

## Counterparts

    - This Agreement shall be executed in two counterparts, each of which when executed and delivered shall constitute an original of this Agreement.

## Set-Off

    - The Agency shall have the right to withhold and set-off against any amount it is liable to pay to the Concessionaire hereunder, in the event:

- the deduction is expressly contemplated under this Agreement and has been duly certified in writing by the Independent Engineer; or

- the deduction is required to give effect to a final, non-appealable arbitral award rendered under Section 28 or a final judgment from a court of competent jurisdiction.

## Independence

    - In respect of all matters dealing with the Agreement, the Independent Engineer and the Independent Auditor shall be independent and shall ensure that they performs all their obligations in accordance with their respective terms of reference and this Agreement.

## Entire Agreement

    - The Parties hereto acknowledge, confirm and undertake that this Agreement (and the Agency Agreements, as applicable), as at the date hereof, constitutes the entire understanding between the Parties regarding the Project and supersedes all previous written and/or oral representations and/or arrangements regarding the Project.

# List of Schedules

# Signature Page

In witness whereof, the Parties hereto have caused this Agreement to be executed on the day, month and year first above mentioned.

As the Agency

| For and on behalf of [•] through its authorised signatory Name: Designation: Name: Designation: in the presence of Witnesses: 1- Name: Address: CNIC / Passport No: 2- Name: Address CNIC / Passport No: |  | Signature ……………………………….. ……………………………….. Signature ……………………………….. ………………………………… |
| --- | --- | --- |

As the Concessionaire

| For and on behalf of [•] through its authorised signatory Name: Designation: in the presence of Witnesses: 1- Name: Address: CNIC / Passport No: 2- Name: Address CNIC / Passport No: |  | Signature ……………………………….. Signature ……………………………….. ………………………………… |
| --- | --- | --- |

List Of Schedules

[List To Be Added]

# Schedule A – Scope Of The Project

[To Be Attached Hereto]

# Schedule B – Specific Definitions

This Schedule contains the project-specific definitions that supplement the definitions in the main body of the Agreement. All [●] placeholders are mandatory fill-ins before issuance of the RFP. The definitions set out herein are to be read alongside, and form part of, the definitions in Article 1 of the Agreement.

Acceptable Pakistani Bank means a scheduled bank or a financial institution incorporated or organised in Pakistan having a credit rating of at least [A or higher by PACRA, or A or higher by VIS];

Accounting Year means the financial year of the Concessionaire, being the period of twelve (12) months commencing on [1 July] and ending on [30 June] of each year, or such other accounting year as may be notified to the Agency in writing;

Agency means the Government of [•], its respective departments or any other authorities, agencies and instrumentalities functioning under the direction or control of the Government of [•], and its administrators, successors and permitted assigns;

Agency Specific Permits  means all such approvals, consents, authorizations, notifications, concessions, acknowledgements, licenses, permits, decisions or similar items that relate to the Project and its implementation which the Agency is solely responsible for procuring, issuing or maintaining under the Applicable Laws, as specifically set out in Schedule Y (Agency Specific Permits);

Approved Pre-Commencement Costs means:

- any cost for undertaking Pre-Commencement Activities;

- fees due and payable to the Independent Engineer and Independent Auditor; and

- works approved by the Independent Engineer;

Change Of Scope Advance Percentage  means [●] percent ([●]%) of the Additional Cost, representing the advance portion of the Change of Scope payment payable by the Agency to the Concessionaire upon issuance of a Change of Scope Order, as may be agreed between the Parties in accordance with this Agreement;

Change Of Scope Limit means [●]% of the Total Project Cost, being the maximum aggregate value of all Change of Scope orders permissible without requiring renegotiation of the financial model;

Daily Development Period Damages  means [●]% of the Development Performance Security amount per day of delay, subject to the Development Period Damages Cap;

Delayed Payment Rate  means the six (6) months KIBOR plus two percent (2%), compounded semi-annually, calculated for the actual number of days which the relevant amount remains unpaid on the basis of a 365-day year;

Development Performance Security  means:

(a)	for the period commencing from the Effective Date till the Commencement Date, in the form of a bank guarantee or standby letter of credit issued by a scheduled bank in Pakistan (with a credit rating equal to or higher than the Minimum Credit Rating) acceptable to the Agency, of an amount, in Pakistani Rupee, equal to the bid security or PKR [●] (Pakistani Rupees [●]), whichever is higher;

(b)	for the period commencing from the Commencement Date till the Development Performance Security Expiry Date, in the form of a bank guarantee or standby letter of credit, issued by a scheduled bank in Pakistan (with a credit rating equal to or higher than the Minimum Credit Rating) acceptable to the Agency, of an amount in Pakistani Rupee equal to [●] per cent ([●]%) of Pre-estimated Project Cost;

Development Performance Security Expiry Date means the date falling [●] months following the Substantial Completion Date;

Development Period Damages Cap means [●]% of the Total Project Cost, being the maximum aggregate amount of Development Period Damages payable by the Concessionaire;

Development Progress Reporting Timeline  means the periodic reporting interval applicable during the Development Period, being a frequency of [●] ([●]) [days/weeks/months], or such other frequency as may be agreed in writing between the Parties and the Independent Engineer from time to time, commencing on the Commencement Date and ending on the Project Development Completion Date;

Equity  means the aggregate funds subscribed and paid-up (or committed to be subscribed and paid-up) by the Sponsor(s) and/or the Agency (as the case may be) as share capital in the Concessionaire in the form of ordinary or preference shares, in accordance with the Equity Funding & Utilization Agreement and the Financial Model, excluding any Financing and any shareholder loans;

Excluded Change In Law means:

- coming into effect, on or after the Bid Submission Date, of any provision of a statute which is already gazetted in accordance with the Applicable Laws prior to the Bid Submission Date;

- any new Applicable Law or any change in the existing Applicable Law under the active consideration of or in the contemplation of the Project Jurisdiction as of the Bid Submission Date, which is already gazetted prior to the Bid Submission Date; or

- [income tax applicable to the Concessionaire in accordance with the Income Tax Ordinance, 2001, as in force on the Bid Submission Date;]

Extension Request Deadline means the date falling exactly one (1) year prior to the Final Expiry Date;

Final Expiry Date means the date on which the Concession Period expires, being the date falling [●] ([●]) years from the Commencement Date, or such extended date as may arise pursuant to and in accordance with the terms of this Agreement;

Force Majeure Costs means all such costs that are directly attributable to, arise from and are a direct result of, in each case, a Force Majeure Event and shall include; any additional capital expenditures; any additional development costs; and any additional operating costs; provided, however, all such additional costs shall be subject to confirmation by the Independent Auditor and the Independent Engineer and provided further, for the purposes of determining such costs, information contained in the Financial Model shall be relied upon;

Indemnity Survival Period means the period of [●] ([●]) years commencing from and after the Termination Date or, as the case may be, the Final Expiry Date, during which the indemnification obligations of the Parties under Article 9 (Indemnities & Limitation of Liability) shall remain in full force and effect;

LOA Date means the date of which the letter of award for the Project was issued to the Sponsor;

Maximum Extension Period  means an aggregate period not exceeding [●] ([●]) years from the Final Expiry Date;

Minimum Credit Rating means a long-term credit rating of at least [AA-] as rated by [JCR-VIS] or an equivalent rating by [PACRA];

Minimum Indemnification Amount  means PKR [●] (Pakistani Rupees [●]), being the aggregate threshold of Losses that must be incurred by a Party in any Accounting Year before such Party shall be entitled to assert a claim for indemnification under this Agreement, as set out in Section 9.2 (Assertion of Claims to Exceed Minimum Indemnification Amount);

O&M Costs  means all costs, expenses and outgoings incurred or to be incurred by the Concessionaire in connection with the operation and maintenance of the Concession Assets during the Operations Period in accordance with the O&M Requirements, including:

- routine and periodic maintenance costs;

- staffing and management costs;

- insurance premiums applicable to the Operations Period;

- costs of utilities consumed at the Project Site; and

- costs of compliance with Applicable Laws and Applicable Standards during the Operations Period,

provided that O&M Costs shall exclude Financing Due and Equity returns;

O&M Performance Security means the performance security, in the form of a bank guarantee or a standby letter of credit, issued by a scheduled bank in Pakistan (with a credit rating equal to or higher than the Minimum Credit Rating) acceptable to the GoS Agency, being in an amount equal to [•] ([•]%) of the O&M Costs for the Operational Year or an amount equal to PKR [•] (Pakistani Rupees [•] only) escalated at [•]% per annum whichever is higher, to which it pertains, furnished from time to time by the Concessionaire to the GoS Agency in accordance with Section 11.3 (O&M Performance Security), in case of a bank guarantee, the same shall be in form and substance as attached hereto as Schedule M (Form of O&M Performance Security);

O&M Status Reporting Timeline  means the periodic reporting interval applicable during the Operations Period, being a frequency of [●] ([●]) [days/weeks/months], or such other frequency as may be agreed in writing between the Parties and the Independent Engineer from time to time, commencing on the Commercial Operations Date and ending on the Trigger Date;

Order Of Priority  means the order of priority in accordance with which the funds standing to the credit of the Escrow Account shall be applied and disbursed by the Escrow Agent, as follows:

- first, payment of all amounts due and payable in respect of O&M Costs;

- second, payment of all Financing Due to the Financiers in accordance with the Financing Documents;

- third, payment of any amounts due and payable to the Agency under this Agreement (including any Agency Remedy Amount and Development Period Damages);

- fourth, replenishment of any reserve accounts required under the Financing Documents; and

- fifth, distribution of the remaining balance to the Sponsors as Equity returns, subject to compliance with all other provisions of this Agreement;

Pre-Commencement Activities means the preparatory activities undertaken by the Concessionaire prior to the Commencement Date for the purposes of enabling the timely commencement of Development Works, including:

- procurement and mobilization of the Development Contractor(s);

- preparation and submission of the Preliminary Engineering Design;

- identification and survey of existing utilities, roads and right-of-way encumbrances on the Project Site;

- procurement of all Concessionaire Permits required for commencement of Development Works; and

- such other activities as may be agreed between the Parties and approved by the Independent Engineer prior to the Commencement Date;

Project Jurisdiction means [Karachi / [Relevant District], Province of Sindh, Islamic Republic of Pakistan];

Project Modality means the specific project delivery framework, being a [●] basis, under which the Concessionaire is obligated to [investigate, study, procure, finance, develop, operate, maintain and transfer] the Project;

Project Requirements means the technical, operational, environmental and legal requirements applicable to the Project and the Project Works as set out in:

- the Scope of the Project;

- the Applicable Standards;

- the Development Requirements;

- the O&M Requirements;

- the Specific Requirements; and

- any additional requirements specified or agreed upon in writing by the Agency and the Concessionaire from time to time in accordance with this Agreement;

Project Site Land Instrument means [Lease Deed / Sub-Lease Agreement / License to Occupy / Right-of-Way Grant], being the instrument pursuant to which the Agency grants the Concessionaire the right to occupy the Project Site;

Project Site Land Instrument Right means the right of the Concessionaire to occupy, use and enjoy the Project Site granted pursuant to the Project Site Land Instrument, for the duration of the Project Site Land Instrument Right Period;

Project Site Land Instrument Right Expiry Date means:

- [Option A:] the Transfer Date, being the date co-terminus with the expiry or Termination of the Concession Period; or

- [Option B:] the date falling on the last day of the Project Site Land Instrument Right Period, as may be extended from time to time in accordance with this Agreement;

Project Site Land Instrument Right Period  means a period of [●] ([●]) [years/months] commencing from the date of the physical handing over of the Vacant Possession of the Project Site to the Concessionaire by the Agency, as may be extended from time to time in accordance with this Agreement;

Relevant Environmental Protection Agency  means the provincial or local environmental protection authority having jurisdiction over the Project Site and the Project in the Project Jurisdiction, being the [●], and any successor authority thereto;

Repetition Dates  means, collectively, each of the following dates upon which the representations and warranties set out in Section 7.1 and Section 8.1 shall be deemed to be repeated by the respective Parties:

- the Financial Close Date;

- the Commencement Date;

- the Substantial Completion Date; and

- the Transfer Date;

Revenue means all revenues, income, receipts and other monies received or receivable by the Concessionaire from or in connection with the operation of the Concession Assets during the Operations Period, including:

- toll revenue, user charges and access fees;

- ancillary commercial revenues derived from the Project Site;

- any relief compensation or Change of Scope payments received from the Agency; and

- insurance proceeds in respect of loss of revenue;

provided, however, that Revenue shall exclude: (i) Financing proceeds; (ii) Equity injections; and (iii) any amounts received by way of Termination Payment;

RFP Publication Date means the date on which the RFP was issued by the Agency to prospective bidders for the grant of the Concession;

Scheduled Commencement Date  means the date falling [●] days after the Effective Date, as may be extended from time to time in accordance with this Agreement;

Scheduled Substantial Completion Date  means the date falling [●] months after the Commencement Date, as may be extended from time to time in accordance with this Agreement;

Specific Agency Agreements means:

- the Escrow Agreement; and

- the Price Escalation Agreement;

Specific Agency Conditions Precedent means:

- the Agency has provided the First Agency Financial Instrument in accordance with Section 17.8;

- the Agency has entered into the Equity Funding & Utilization Agreement with the Concessionaire; [INCLUDE ONLY IF EQUITY FUNDING & UTILIZATION AGREEMENT APPLIES — see Schedule Y]

- the Agency has entered into the Price Escalation Agreement with the Concessionaire; [INCLUDE ONLY IF PRICE ESCALATION MECHANISM APPLIES — see Schedule Z] and

- the Agency has procured, issued, and delivered to the Concessionaire, in full force and effect, all Agency Specific Permits required for the commencement of the Development Works;

Specific Agency Undertaking means procure, issue, and maintain in full force and effect all Agency Specific Permits in a timely manner to prevent any delay in the performance of the Project Works by the Concessionaire;

Specific Concessionaire Conditions Precedent means:

- the Concessionaire and the Sponsor have entered into the Equity Funding & Utilization Agreement with the Agency;

- the Concessionaire's Approved Preliminary Engineering Design stands approved by the Independent Engineer and the Agency;

- the Corporate Documents of the Concessionaire reflect, to the satisfaction of the Agency, the different classes of shares;

- each of the Concessionaire Permits have been procured and are effective, valid, and have not been cancelled and/or rescinded;

- the Concessionaire has provided a certified true copy of the duly executed Financing Term Sheet that is not objected to by the Agency and the Independent Auditor in accordance with Section 27.3;

- certified true copies of the executed Financing Documents have been delivered to the Agency;

- the Financial Close Achievement Notice has been issued by the Financiers (or an agent of the same);

- the Concessionaire and the Sponsor have entered into the Price Escalation Agreement with the Agency;

- the Concessionaire has obtained the EIA Approval;

- the Concessionaire has obtained the Specified Concessionaire Permits [including CCP approval where applicable]; and

- [the Concessionaire has obtained the SBP Approval;]

Specific Concessionaire Undertaking  means [●];

Specific Persons  means the persons, categories of individuals or designated groups whose safety is to be specifically protected in connection with the Project Works and the Project Site, as identified and listed in Schedule Y, including (without limitation) any persons occupying or using the Project Site and any neighbouring areas during the Development Period or the Operations Period;

Specific Requirements  means:

- in respect of Development Works, the Development Requirements; and

- in respect of Operations and Maintenance, the O&M Requirements;

Sponsor Base Equity Amount  means the amount set out in the Financial Model, being PKR [●] (Pakistani Rupees [●]), representing the minimum aggregate Equity contribution required to be subscribed and paid-up by the Sponsor(s) in the Concessionaire by way of Class A Shares in accordance with the Equity Funding & Utilization Agreement;

Substantial Completion Criteria  means [insert detailed list of completion requirements specific to the Project, including: (a) all Completion Tests have been passed; (b) all as-built drawings have been submitted and approved by the Independent Engineer; (c) all regulatory approvals required for the commencement of operations have been obtained; and (d) the O&M Performance Security for the first Operational Year has been provided to the Agency];

Termination Dividend Amount means the aggregate return on Sponsor Invested Equity for each of the [three (3) Accounting Years  falling immediately after the Termination Date], the same being an amount equal to the aggregate of Termination Equity IRR applied to the Sponsor Invested Equity for each of the three (3) Accounting Years falling after the Termination Date, as illustrated in Schedule V (Illustrations);

Termination Equity means, as of the Transfer Date occurring due to Termination, the aggregate of the Sponsor Invested Equity reduced on a [straight-line basis from the Substantial Completion Date] through the term of this Agreement, as illustrated in Schedule V (Illustrations);

Termination Equity IRR means the post-tax internal rate of return, the same being [17%], on the Sponsor Invested Equity;

Schedule C – Development Works: Engineering, Design & Construction Drawings

(Conditional — Applicable to Engineering and Construction Projects Only)

This Schedule C is a conditional schedule. It applies exclusively to projects that require the engineering, design, procurement and physical construction of Concession Assets – such as roads, highways, bridges, water infrastructure, energy generation facilities, ports and other built infrastructure. This Schedule does not apply to projects that do not involve engineering design or physical construction works (such as carbon credit forestry concessions, conservation concessions, management service concessions or similar non-construction arrangements). For such projects, this Schedule C shall be deleted in its entirety and all cross-references thereto in the main body of the Agreement shall be removed or replaced with project-specific provisions.

This Schedule is divided into two Parts. Part A sets out the key definitions applicable to the engineering, design and construction phase of the Project. Part B sets out the standardised Construction Drawings provisions corresponding to the Agreement. All definitions in this Schedule C are to be read alongside, and form part of, the definitions in Article 1 of the Agreement and Schedule B (Specific Definitions).

Part A — Key Definitions

Approved Detailed Engineering Design means the Detailed Engineering Design approved by the Independent Engineer (in consultation with the Agency) in accordance with the Applicable Standards;

Approved Preliminary Engineering Design means the Preliminary Engineering Design approved by the Independent Engineer (in consultation with the Agency) in accordance with the Applicable Standards;

Construction Drawings  means the drawings, designs, calculations and documents prepared and/or to be prepared by the Concessionaire pursuant to the Applicable Standards and the Design Requirements that pertain to the Project and the Concession Assets, as amended from time to time by the Concessionaire in accordance with the terms of this Agreement with the approval of the Independent Engineer (in consultation with the Agency);

Design Requirements means the design requirements of the Concession Assets, as set out in Schedule B (Design Requirements);

Detailed Engineering Design means the detailed engineering design for the Project prepared by the Concessionaire in accordance with the Applicable Standards and the Design Requirements, submitted in batches to the Independent Engineer for approval within four (4) months of the Commencement Date in accordance with Clause 5 of Schedule C;

Preliminary Engineering Design means the preliminary engineering design for the Project prepared by the Concessionaire in accordance with the Applicable Standards, submitted to the Independent Engineer (with a copy to the Agency) within one hundred and twenty (120) days of the Effective Date as part of the Concessionaire Conditions Precedent process in accordance with Clause 5 of Schedule C;

Proposed Detailed Design has the meaning ascribed thereto in Clause 5.4 of Schedule C, being the Detailed Engineering Design (submitted in batches) delivered to the Independent Engineer by the Concessionaire within four (4) months of the Commencement Date for review and approval;

Proposed Preliminary Design has the meaning ascribed thereto in Clause 5.1 of Schedule C, being the Preliminary Engineering Design submitted by the Concessionaire to the Independent Engineer (with a copy to the Agency) within one hundred and twenty (120) days of the Effective Date for approval as part of the Concessionaire Conditions Precedent process;

Part B — Construction Drawings Provisions

The Construction Drawings provisions in this Part B are fully standardised and correspond to Clause 1 through Clause 5 of Schedule C. No project-specific amendments are required to the operative text of this Part B, subject only to the conditional amendments identified in the footnotes below.

    - Preparation Of Construction Drawings

  - The Concessionaire shall prepare the Construction Drawings in accordance with the Applicable Standards and shall complete and deliver the same to the Agency and the Independent Engineer from time to time within the Development Time for Completion. The Concessionaire hereby undertakes that the Construction Drawings shall comply with the Applicable Standards.

  - Defects & Deficiencies, errors, omissions, ambiguities, inconsistencies, inadequacies and other defects in the Construction Drawings or arising therefrom shall be rectified by the Concessionaire at its sole cost and risk.

  - The Agency, the Independent Engineer and the Independent Auditor (as applicable) may use the Construction Drawings for such purposes as the same may require for the purposes of the Project.

  - The Concessionaire may at its discretion and subject to the Applicable Standards and the Design Requirements, propose with or without modifications the drawings made available by the Agency or adopt its own Construction Drawings after prior approval of the Independent Engineer; provided, however, that the Concessionaire shall always remain solely responsible and liable for the adequacy and accuracy of the Construction Drawings.

  - Notwithstanding the Concessionaire's decision to adopt the drawings provided by the Agency, all Construction Drawings shall remain subject to the review, approval and acceptance by the Independent Engineer prior to the adoption of the same by the Concessionaire.

  - The Agency and the Independent Engineer shall have the right to review and inspect all Construction Drawings. The Concessionaire shall provide all such Construction Drawings as may be reasonably required by the Agency and/or the Independent Engineer in respect of the Development Works.

- Details of Construction Drawings

  - The Construction Drawings to be submitted by the Concessionaire to the Independent Engineer shall include but not be limited to the following details:

- [insert project-specific list of required drawing types and categories, in accordance with the Design Requirements and Schedule B;]

- such further information and details as may be requested by the Independent Engineer and the Agency acting reasonably.

  - All Construction Drawings submitted by the Concessionaire shall comply with and shall be in accordance with the Design Requirements and the Applicable Standards.

- Review & Approval of Construction Drawings

  - The Concessionaire shall promptly and in such sequence as is consistent with the Development Requirements, submit four (4) copies of the Construction Drawings to the Independent Engineer and the Agency.

  - The submission of the Construction Drawings pursuant to Clause 3.1 of the Schedule C shall constitute the representation of the Concessionaire that the Construction Drawings submitted are in conformity with the Design Requirements.

  - Within fifteen (15) days of receipt of the Construction Drawings, the Independent Engineer shall review and comment on the same taking into account, inter alia, the comments of the Agency, if any, thereon, and convey its comments/observations to the Concessionaire on the conformity of the Construction Drawings with the Design Requirements.

  - The Concessionaire hereby undertakes to revise the Construction Drawings to the extent necessary and to resubmit the same for the review of the Independent Engineer and the Agency in the event the comments and observations indicate non-conformity with the Design Requirements. The Independent Engineer shall provide its observations and comments on such re-submitted Construction Drawings within fifteen (15) days of receipt.

  - The Concessionaire shall simultaneously with the submission of Construction Drawings prepare and submit to the Independent Engineer the construction plan providing, inter alia, the “critical path method” in respect of the Project.

  - Notwithstanding anything contained herein:

- in the event the response of the Agency is not provided within the period stipulated in Clause 3.3 of the Schedule C, the same shall stand deemed approved, and the Independent Engineer may at its discretion proceed with the approval of Construction Drawings on the basis of the Construction Drawings submitted by the Concessionaire;

- the Concessionaire shall be solely liable for the Construction Drawings and their compliance and conformity with the Design Requirements, and shall not be relieved and/or absolved in any manner whatsoever of its obligations hereunder, irrespective of whether or not the Independent Engineer has provided its observations and comments;

- neither the review of the Construction Drawings by the Independent Engineer, the failure of the Independent Engineer to provide observations and comments, nor the provision of comments by the Independent Engineer and/or the Agency shall relieve the Concessionaire of its obligations hereunder, nor shall the same be construed as a waiver; nor shall the Agency be held liable for the observations and comments provided by the Independent Engineer; and

- the Concessionaire shall be obligated to provide a copy of the approved Construction Drawings to the Agency and the Independent Engineer prior to commencement of Development Works.

  - The Concessionaire hereby undertakes that it shall be solely responsible and liable for:

- achieving completion of each Project Development Milestone on or prior to its respective Project Development Milestone Date;

- achieving Substantial Completion on or prior to the Scheduled Substantial Completion Date; and

- achieving Project Development Completion on or prior to the Scheduled Project Development Completion Date,

and, in each case, the said obligation and liability of the Concessionaire shall not be reduced, negated, rescinded and/or waived by any delay and/or failure of the Independent Engineer to fulfil its obligations under this Clause.

- Submission Of Final Construction Drawings Prior To Project Development Completion Date

  - Within forty-five (45) days of the Substantial Completion Date and in any event as a condition precedent to the issuance of the Final Project Development Completion Certificate, the Concessionaire shall submit to the Agency the “as built” Construction Drawings, duly verified and approved by the Independent Engineer, illustrating the layout of the Project and the Project Facilities and reflecting the same as actually designed, engineered and constructed.

  - The Construction Drawings to be submitted pursuant to this Clause 4 of the Schedule C shall be in such form as may be requested by the Agency, including but not restricted to paper format (hard copies), digital format, micro films or such other format as may be acceptable to the Agency.

  - The Concessionaire shall be responsible for amending, modifying and updating the Construction Drawings from time to time during the Operations Period, subject to the approval of the Independent Engineer. All updated, amended and/or modified Construction Drawings shall be submitted to the Agency and the Independent Engineer. Preparation, completion and delivery of the updated Construction Documents shall form part of the Concessionaire's obligations relating to the O&M Documents.

- Approval of the Preliminary Engineering Design and the Detailed Engineering Design

  - Notwithstanding anything to the contrary, the Concessionaire shall, as part of the process of the Concessionaire Conditions Precedent, within one hundred and twenty (120) days of the Effective Date submit the Preliminary Engineering Design (the Proposed Preliminary Design) to the Independent Engineer (with a copy to the Agency) for approval and procure issuance of the Approved Preliminary Engineering Design. The Approved Preliminary Engineering Design shall set out the exact location and extent of the Project Site for land acquisition and for the relocation of existing utilities, and all other matters relating to any relocations and impediments in connection with the Project Site.

  - Upon receipt of the Proposed Preliminary Design, the Agency shall communicate its objections or reservations (if any) to the Independent Engineer, and the Independent Engineer shall ensure that the same are adequately addressed and where necessary form an approval requirement for such Proposed Preliminary Design.

  - The Parties hereby acknowledge and agree that the delivery of Vacant Possession of the Project Site, the exact area, location, relocation of existing utilities and other relevant matters relating to the same are a function of the Approved Preliminary Engineering Design.

  - Thereafter, the Concessionaire shall submit its Detailed Engineering Design (in batches) to the Independent Engineer (with a copy to the Agency) within four (4) months of the Commencement Date for approval (the Proposed Detailed Design). Within thirty (30) days of receipt of each batch, the Independent Engineer shall review the same and convey its observations to the Concessionaire with reference to conformity with the Applicable Standards. In the event no comments are provided within twenty (20) days of receipt, the Concessionaire shall notify the Independent Engineer. In the event no comments are received within ten (10) days following such notification, each batch shall be deemed to be approved by the Independent Engineer.

  - Upon receipt of the Proposed Detailed Design, the Agency shall communicate its objections or reservations (if any) to the Independent Engineer, and the Independent Engineer shall ensure that the same are adequately addressed and where necessary form an approval requirement for the Proposed Detailed Design.

  - In the event the observations of the Independent Engineer indicate that the Proposed Preliminary Design or the Proposed Detailed Design is not in conformity with the Applicable Standards, the relevant design shall be revised by the Concessionaire at its cost and expense and resubmitted to the Independent Engineer within fifteen (15) days of receiving such observations. The Independent Engineer shall provide further observations within seven (7) days of receipt of the revised design. The Concessionaire shall revise and resubmit within fifteen (15) days of receiving such further observations.

# Schedule D – Project Facilities

[To Be Attached Hereto]

# Schedule E – Project Development Completion Schedule

[To Be Attached Hereto]

# Schedule F – Project Site

[To Be Attached Hereto]

# Schedule G – Completion Tests Matters

[To Be Attached Hereto]

Schedule H – O&M Requirements

[To Be Attached Hereto]

Schedule I – Insurance

[To Be Attached Hereto]

Schedule J – Specific Matters Relating To Relief Events

This Schedule J quantifies the Specific Relief Matters upon a qualifying Relief Event. It is divided into three Parts: Definitions, Basis of Calculation, and Determination Mechanism.

    - Definition

Relief Costs means the increase in such capital expenditures and costs and/or the operating costs, in each case, that are set out in the Financial Model and which directly result from a Relief Event (excluding such Relief Events that are set out in Section 15.1.1 (f) and (g)), as determined by the Independent Engineer and the Independent Auditor pursuant to Article 15 (Relief Extensions & Relief Compensations) and which are set out in the Relief Order; provided, however, for the purposes of determining such costs, information contained in the Financial Model shall be relied upon by the Independent Engineer and the Independent Auditor;

Specific Relief Costs means, in respect of a qualifying Relief Event, the aggregate of the following demonstrably incurred or accrued costs and losses: (a) Loss of Revenue; and (b) Financing Markup.

    - Basis Of Calculation

  - Loss Of Revenue

    - The Loss of Revenue shall be calculated by the Independent Auditor in accordance with the following methodology:

- during the Operations Phase: the average daily revenue generated by the Concessionaire from the Concession Assets over the ninety (90) day period immediately preceding the occurrence of the Relief Event, multiplied by the number of days the Concessionaire was prevented from generating revenue as a direct result of the Relief Event; and

- prior to the Operations Phase: the projected daily revenue set out in the Base Case Financial Model for the corresponding period of the delay, multiplied by the number of days of delay to the Scheduled Commencement Date or the Scheduled Construction Completion Date directly caused by the Relief Event.

  - Financing Markup

    - Financing Markup shall be calculated as the aggregate of any additional interest, markup, commitment fees, or other financing charges accruing under the Financing Documents as a direct and unavoidable consequence of the delay, suspension, or extension of the Time for Completion caused by the Relief Event, as verified by the Independent Auditor.

    - Determination Mechanism and Timeline

  - Notwithstanding any general timeframes set out in Article 15, upon submission of a Relief Order Request by the Concessionaire claiming Specific Relief Costs, the Independent Engineer and the Independent Auditor shall, within twenty-one (21) days of receipt of such request, jointly determine, quantify, and certify the exact amount of the Specific Relief Costs to be paid by the Agency. Upon such determination, the quantum of the Specific Relief Costs shall be incorporated into the binding Relief Order.

Schedule K – Corporate Documents

[To Be Attached Hereto]

Schedule L – Financing Matters

This Schedule L is the master financing schedule. It contains all definitions, operative sections, and consequential amendments that apply only if the project involves third-party debt financing. If the project is entirely equity-funded, this Schedule L shall be deleted in its entirety from the Agreement.

      - Definitions Added by Schedule L

The following definitions are to be added to Schedule B (Specific Definitions) and cross-referenced to Schedule L when financing is present:

Concession Direct Agreement means the direct agreement that may be entered into between the Concessionaire, the Agency and the Financiers, if required by the Financiers;

Financial Close means the execution and delivery of the Financing Documents that (together with Equity commitments) evidence sufficient financing for the construction, testing, and commissioning of the Project and achievement of Project Development Completion, following the resolution of any objections raised by the Agency and/or the Independent Auditor to the Financing Term Sheet, and evidence of commitments for such equity as is required by the Concessionaire to satisfy the requirements of the Financiers, and the satisfaction of all conditions precedent for the initial availability of funds under the Financing Documents and the Concessionaire having immediate access to the Financing;

Financial Close Achievement Notice means shall have the meaning ascribed in Section 1.2.1 of Schedule L;

Financiers means the financial institutions, banks, Islamic financiers, funds, trusts or trustees of the holders of debentures or other securities, their successors and assigns, that extend Financing to the Concessionaire pursuant to the Financing Documents;

Financing means the finance facilities, loans, advances, financial accommodation and/or arrangement, subscription and/or issuance of debentures/bonds/redeemable capital, risk participation, take-out financing and/or any other financial obligation availed by the Concessionaire from the Financiers in respect of the Project, pursuant to the Financing Documents;

Financing Amendment Term Sheets means shall have the meaning ascribed thereto in Section 1.1.3 of Schedule L;

Financing Component means the component that relates to the repayment and servicing of Financing Due (i.e. both Principal repayment and interest/mark-up payments), as set out in the Financial Model;

Financing Due means the aggregate of the following sums expressed in Pakistani Rupees outstanding and payable to the Financier up to the date immediately preceding the Termination Payment Date pursuant to the Financing Documents:

- the principal amount of the Financing provided and disbursed by the Financiers under the Financing Documents (the Principal), in accordance with the Financial Model and the Financing Term Sheet;

- the interest or mark-up accruing on the Principal in accordance with the Financial Model and the Financing Term Sheet;

- only in the event of Termination due to Agency Event of Default: penal interest or charges payable under the Financing Documents;

Financing Documents means the loan/financing agreements or instruments relating to or contemplated by the Financing Term Sheets that have not been objected to by the Agency and/or the Independent Auditor pursuant to Section 1.1 of Schedule L, as may be amended from time to time in accordance with the provisions of Section 1.1 of Schedule L;

Financing Term Sheet means shall have the meaning ascribed thereto in Section 1.1.1 of Schedule L;

Financing Termination Date means the date on which no part of the Financing Due is outstanding and all amounts due and payable by the Concessionaire to the Financiers are paid in accordance with the Financing Documents, as confirmed in writing by the Independent Auditor;

Principal means has the meaning ascribed thereto in the definition of 'Financing Due';

      - Section 1.1 — Financing Term Sheet and Financing Amendment Term Sheets

Section 1.1.1 (Financing Term Sheet)

Prior to Financial Close, the Concessionaire shall deliver to the Agency and the Independent Auditor a copy of the term sheet reflecting the proposed material terms of the Financing Documents, including: (i) principal repayment schedule; (ii) maximum principal amounts; (iii) interest or markup rate; (iv) fees and charges upon early termination; and (v) equity commitments (the Specific Term Sheet Parameters). The Agency and the Independent Auditor shall evaluate the Specific Term Sheet Parameters to ensure principal financial terms are not greater than the Financing Component in the Financial Model. If the Agency and/or Independent Auditor has objections, they shall inform the Concessionaire within thirty (30) days; otherwise deemed not to have objected (the Financing Term Sheet).

Section 1.1.2 (Post-Financial Close Amendments)

Following Financial Close, all amendments to Financing Documents shall be delivered to the Agency and Independent Auditor within ten (10) Business Days of execution. No amendment affecting principal repayment or new secured debt shall be executed without thirty (30) Business Days prior notice and a revised term sheet, subject to the same objection mechanism.

Section 1.1.3 (Financing Amendment Term Sheets)

The Agency and the Independent Auditor shall raise objections to proposed amendments within thirty (30) days of receipt. If no objection within thirty (30) days, deemed no objection (Financing Amendment Term Sheets).

Section 1.1.4 (Restriction on Amendments Increasing Agency Liability)

The Concessionaire shall not amend Financing Documents in a way that imposes or increases financial liability on the Agency without prior written Agency consent. Unauthorised amendments are unenforceable against the Agency.

- Section 1.2 — Financial Closing

Section 1.2.1

Upon achievement of Financial Close, the Concessionaire shall procure issuance by Financiers (or an agent of the same) of a Financial Close Achievement Notice to the Agency (with copies to the Independent Auditor and Independent Engineer) certifying the achievement of Financial Close.

D.   Section 1.3 — Assignment by the Agency

Notwithstanding anything to the contrary, the Agency shall not assign and/or transfer any of its rights and obligations under this Agreement or any Agency Agreement without the prior written consent of the Concessionaire; provided that the Agency may, without the Concessionaire's consent, assign its rights and obligations to any successor Government Authority that expressly assumes all of the Agency's obligations hereunder.

E.   Consequential Amendments to Other Sections — Financing Scenario

The following amendments to the main body of the Agreement and other Schedules are triggered when financing is present:

Section 3.1.2 — Concessionaire Conditions Precedent

Add the following as new Concessionaire CPs (as set out in Schedule B above):

- Financing Term Sheet delivered and not objected to by the Agency and Independent Auditor.

- Financing Documents executed and copies delivered to Agency.

- Financial Close Achievement Notice issued by Financiers.

Section 7.1.1 — Representations

Add the following representation: ‘the Concessionaire has the ability to achieve Financial Close by the Scheduled Commencement Date.’

Section 7.14.5 — Lists of Creditors

Replace ‘each of its creditors’ with ‘(i) the Financiers; and (ii) each of its creditors’. Add ‘such Financiers and’ before ‘creditors’ throughout.

Section 7.14.6 — Statutory Notice / Winding Up

Insert "the Financiers or" before "its creditors" in both sub-sections.

Sections 20.1.1 & 20.1.2 — Development Period Insurances

Insert "Financing Documents (as contemplated in the Financing Term Sheet) and the" before "Applicable Laws" in Section 20.1.1.

Add new Section 20.1.2: "The Concessionaire shall, at its sole cost and expense, procure any other insurance or Takaful coverages as may be required from time to time under the Financing Documents or pursuant to any Applicable Laws."

Section 20.3.2 — Duration of Insurances

Add at end: "notwithstanding the expiry of the Financing Documents (as contemplated in the Financing Term Sheet)."

Section 20.3.3 — Acceptability of Insurers

Add new Section 20.3.3: "Notwithstanding any other provision of this Article 20, for so long as any Financing remains outstanding, the insurance and/or Takaful companies from which the Insurances are procured must be acceptable to the Financiers in accordance with the terms of the Financing Documents."

Section 20.5.1 — Application of Insurance Proceeds

Add at opening: "Subject to the terms of the Financing Term Sheet," before "all moneys received under the Insurance shall be promptly applied…"

Section 20.5.3 — Loss Payee Designation

Add new Section 20.5.2: "The Concessionaire may, with the prior approval of the Agency, designate the Financiers as the loss payees under the Insurance and/or assign the Insurance in their favor as security for the Financing availed by the Concessionaire from the Financiers pursuant to the Financing Documents."

Section 20.5.2 — Three-Stage Loss Payee Structure

Add new Section 20.5.2 specifying the following three-stage loss payee structure:

- Development Period (until Completion Certificate): Concessionaire, Financiers' Agent, and Agency as their interests appear.

- Operations Period — Financing Outstanding: Concessionaire and Financiers' Agent.

- Post-Financing Repayment: Concessionaire as sole loss payee.

Add: ‘The Agency acknowledges that its right in any insurance proceeds shall be subordinate to the rights and interests of the Financiers as set out in the Financing Documents.’

Section 22.1 / Schedule P — Events of Default

Add to the definition of Agency EoD (Section 22.2(d)(ii)(A)): ‘it unlawful for the Concessionaire, the Financiers, or the Sponsors to make or receive any payment, to perform any material obligation or to enjoy or enforce any material right under any Agency Agreement’ [Financiers' rights must be protected alongside Concessionaire's in EoD triggers].

Section 23.1.3 — Cure Period (Concessionaire EoD)

Add new sub-section: ‘During any period when any Financing Due is outstanding, the Agency shall not be entitled to terminate this Agreement for a Concessionaire Event of Default unless it has provided the Financiers (or the Financiers' Agent) with a separate written notice of the Concessionaire's failure to cure. Upon receipt of a Notice of Failure to Cure, the Financiers shall have an additional period of thirty (30) Business Days (the Financiers' Cure Period) to remedy, or cause the remedy of, the relevant Concessionaire Event of Default. During the Financiers' Cure Period, the Agency's right to terminate this Agreement shall be suspended.’

Section 23.5.2 — Termination Payment as Liquidated Debt

Add: ‘Any Termination Payment certified by the Independent Engineer, Independent Auditor, or Financiers' Agent shall be treated as a liquidated debt. The Concessionaire may pursue summary recovery of such debt in any court of competent jurisdiction without prior recourse to arbitration.’

Section 23.6.2 — Payment Direction

Add: ‘Notwithstanding any instructions to the contrary, the Termination Payment and all other payments payable by the Agency under this Agreement shall, so long as the Financing Due is outstanding, be made only by way of credit directly to a bank account designated by the Financiers and advised to the Agency and the Concessionaire in writing.’

Section 27.1.2 — Permitted Assignment and Charges

Carve-out from restriction on assignment — the following shall NOT require Agency consent:

- assignment of rights, interest and obligations of the Concessionaire under this Agreement, the Agency Agreements, and/or the Project Agreements, Encumbrances, pledges/hypothecation of goods/assets, and any and all other bank accounts of the Concessionaire, a mortgage/charge in relation to the Development Works and the Concession Assets (excluding the Project Site), a charge on the present and future movable, immovable and intellectual property of the Concessionaire, in each case, arising or created as security only for indebtedness to the Financiers under the Financing Documents in accordance with the Financing Term Sheet;

- pledge of Sponsor Shares as security only for indebtedness to the Financiers under the Financing Documents; provided that any enforcement of such share pledge shall be subject to the share transfer restrictions under Section 10.3 and require prior Agency approval for share transfer thereunder, which shall not be unreasonably withheld or delayed.

Section 27.2 — Collateral Assignment Consent

‘The Agency consents to the collateral assignment of the Concessionaire's rights under this Agreement to the Financiers pursuant to the Financing Documents and agrees: (a) to afford the Financiers a reasonable opportunity to remedy any default by the Concessionaire before exercising termination rights; and (b) in the event of a foreclosure sale of the Concessionaire's interest in the Concession Assets, to accept the purchaser of the Concessionaire's interest as the successor Concessionaire, provided that such purchaser: (i) has reasonable access to funding to complete the Project; (ii) meets technical and financial qualification requirements; (iii) assumes all Concessionaire obligations; and (iv) cures all outstanding payment defaults.’

Section 27.3 — Concession Direct Agreement

‘The Agency shall enter into a Concession Direct Agreement with the Financiers in respect of this Agreement as the Concessionaire or the Financiers may reasonably request, provided that the Agency shall not thereby assume any obligations under the Financing Documents other than as expressly set out in the Concession Direct Agreement.’

Escrow Agreement — Financing Amendment

Amend definition of Escrow Agent to add: ‘provided, that till the Financing Termination Date, such bank shall be one of the Financiers (or a financial institution designated by the same).’

Amend definition of Escrow Agreement to include ‘the Financiers’ as a party to the Escrow Agreement.

Force Majeure Costs in Schedule B — Financing Amendment

Amend Force Majeure Costs definition to include: ‘and shall include interest and principal payments under the Financing Documents that are in accordance with the Financing Term Sheets and the Financing Amendment Term Sheets"; and add "and payment of interest and principal" after "all such additional costs’.

Agency Agreements — Financing Amendment

Amend definition of Agency Agreements to include ‘and/or the Financiers’ in the ‘any other agreement’ basket (last bullet).

In the section dealing with document copies, add ‘the Financiers’ as a recipient alongside the Agency, Independent Engineer, and Independent Auditor.

Arbitration — International Lenders Election

‘Where the Project involves international lenders or investors (as specified in the Financing Documents), the Parties may, by express election in Schedule B, substitute the Arbitration Act 1940 with the ICC Rules of Arbitration or the UNCITRAL Arbitration Rules. In the event such an election is made in Schedule B, the seat of arbitration, the language of proceedings, and the appointing authority shall be as designated in Schedule B, and the award shall be final, binding, and enforceable in accordance with the New York Convention.’

Consent to Amendment — Financiers' Protection

‘Notwithstanding the foregoing, in the event that any proposed amendment, supplement, or modification would materially and adversely affect the rights, interests, or security of the Financiers under the Financing Documents, such amendment shall not take effect unless and until the prior written consent of the Financiers (or the Financiers' Agent) has been obtained by the Concessionaire and delivered to the Agency.’

F.   Step In Rights

[•]

Schedule M – Form Of O&M Performance Security

[To Be Attached Hereto]

Schedule N – Part I (Indicative Independent Auditor Terms of Reference)

[To Be Attached Hereto]

Schedule N – Part II (Indicative Independent Engineer Terms Of Reference)

[To Be Attached Hereto]

Schedule O – Form Of Vesting Certificate

[To Be Attached Hereto]

Schedule P – Equity Matters

Schedule P governs the equity structure of the Concessionaire SPV. This Schedule shall be customised based on the chosen equity architecture, as set out in the table below.

Part A — Equity Architecture Options

| Architecture | Description | Schedule Y Treatment |
| --- | --- | --- |
| Option A: Class A only (Sponsor 100%) | No Agency equity. Sponsor holds 100% Class A Shares. No Class B Shares issued. | Delete all Class B Share references. Delete Equity Funding & Utilization Agreement (Agency component). Delete Agency Funding Amount definition. Delete Class B Dividends mechanism. |
| Option B: Class A + Class B (Baseline) | Sponsor holds Class A (voting, participating). Agency holds Class B (non-voting, non-participating). Agency injects Viability Gap Funding as Class B equity. | Use Schedule Y as drafted (baseline). Fill in Agency Funding Amount and Sponsor Base Equity Amount from Financial Model. |
| Option C: Class A + Class E (no Agency equity, but Agency gets nominal share) | Sponsor holds Class A (economic rights). Agency holds one Class E (golden) share with step-in/veto rights but no economic participation. | Replace "Class B Shares" with "Class E Shares" throughout. Remove non-voting/non-participating characterisation. Remove dividend mechanism. Add step-in/information rights for Class E holder. |

Part B — Definitions (Baseline — Option B)

Class A Share(s) means share capital held by the shareholders of the Concessionaire (excluding the Agency), from time to time, in accordance with the Equity Funding & Utilization Agreement and this Agreement;

Class A Shares Invested Equity means the aggregate of funds invested (as Equity) by the Sponsors and shareholders of Class A Shares for funding of the Sponsor Base Equity Amount in accordance with the Equity Funding & Utilization Agreement;

Class B Dividends means shall have the meaning ascribed thereto in Clause 3 of the Schedule P;

Class B Share(s) means the non-voting and non-participating share capital held by the Agency (in case the Agency Funding Amount (or any part thereof) is funded, from time to time, as equity pursuant to the Equity Funding & Utilization Agreement) and this Agreement;

Equity means the share capital of the Concessionaire, represented in PKR for meeting the equity component of the Total Project Cost, consisting of [two classes of shares i.e. Class A Shares and Class B Shares], as set out in the Equity Funding & Utilization Agreement;

Equity Funding & Utilization Agreement means the agreement (in the form agreed between the Parties and the Sponsors) to be entered into by and between, inter alia, the Agency, the Sponsor and the Concessionaire, at any time prior to the Scheduled Commencement Date, for the purposes of, inter alia, the Agency's and the Sponsor(s)' contribution towards the Equity (with respect to Class B Shares) and Equity (with respect to Class A Shares), respectively, and the utilization of the same, in each case, in accordance with the terms thereof;

Agency Funding Amount means an amount not exceeding PKR [●]/- (Pakistani Rupees [●] only), as requested by the Concessionaire from the Agency, in its Bid, as set out in the Financial Model and to be funded through the Equity Funding & Utilization Agreement;

Sponsor Base Equity Amount means the amount set out in the Financial Model;

Part C — Operative Provisions

Clause 1 of the Schedule P — Agency Undertaking to Fund (Class B)

The Agency hereby undertakes to fund from time to time the Agency Funding Amount in accordance with the terms of the Equity Funding & Utilization Agreement.

Clause 2 of the Schedule P — Sponsor Undertaking to Fund (Class A)

The Concessionaire hereby undertakes to procure funding by the Sponsor from time to time of the Sponsor Base Equity Amount through subscription in cash in Pakistani Rupees for Class A Shares in accordance with the Equity Funding & Utilization Agreement.

Clause 3 of the Schedule P — Class B Share Issuance

Upon funding of the Agency Funding Amount (or any part thereof) by the Agency from time to time in accordance with the Equity Funding & Utilization Agreement (if applicable), the Agency shall be issued Class B Shares by the Concessionaire in accordance with the Applicable Laws in the name of ‘Viability Gap Fund, Government Of Sindh’.

Clause 4 of the Schedule P — Class B Dividends

Following the end of each Accounting Year, the Agency shall be entitled to dividends in respect of Class B Shares comprising: (a) the Advertising Proceeds; and (b) the Utility Proceeds that become payable to the Concessionaire during the Concession Period.

Clause 5 of the Schedule P — No Additional Share Classes

The Concessionaire shall not create any classes of its shares other than Class A Shares and Class B Shares without the prior approval of the Agency.

Schedule Q – Price Escalations

Schedule Q governs price escalation for key construction inputs (Escalable Items). It operates through the Price Escalation Agreement, a separate ancillary document to be entered into by the Parties prior to the Scheduled Commencement Date.

Part A — Definitions

Actual Cost means the actual cost of any Escalable Item(s), at the time of procurement of the same;

Base Price means the price of the Escalable Items at the rate prevailing twenty-eight (28) days prior to the Bid Submission Date, as confirmed and notified by the Independent Engineer in accordance with the Price Escalation Agreement;

De-escalation Amount means has the meaning given to that term in Section 10.5.2;

Escalable Items means:

- cement;

- bitumen;

- steel; and

- Petroleum, Oil and Lubricant (POL) for construction machinery and equipment;

Price Escalation Agreement means the agreement (in the form and substance agreed between the Parties in accordance with Applicable Laws) to be entered into by and between the Agency, the Sponsors and the Concessionaire, prior to the Scheduled Commencement Date;

Part B — Operative Provisions

Clause 1 of the Schedule Q — Escalation Cost

In the event the Actual Cost of Escalable Items (in aggregate) exceeds the Base Price (Escalation Cost), the Agency shall bear and fund such portion of the Escalation Cost (provided that such Escalation Cost is duly verified by the Independent Engineer and the Independent Auditor with reference to the price set out in the monthly statistical bulletin issued by the Pakistan Bureau of Statistics) as further detailed in the Price Escalation Agreement. To the extent any Escalable Item is not mentioned in the PBS bulletin, the same shall be determined by the Independent Engineer and the Independent Auditor.

Clause 2 of the Schedule Q — De-escalation

If the Actual Cost of Escalable Items is lower than the Base Price, the resulting De-escalation Amount shall be credited to the Agency by the Concessionaire in accordance with the Price Escalation Agreement.

Schedule R – Revenue Matters

Schedule R governs revenue sharing, specifically the Excess Revenues mechanism. It is project-specific and must be completed based on the agreed revenue model.

Part A — Key Definition

Excess Revenues means shall bear the meaning ascribed thereto in Section 17.4.2; being the revenues received by the Concessionaire from the Project in excess of the [Projected Revenue Threshold / Base Toll Revenue as set out in the Financial Model] in any Accounting Year, the sharing of which with the Agency is governed by the Revenue Sharing Mechanism in Part B of this Schedule AA;

Part B — Revenue Sharing Mechanism

The Revenue Sharing Mechanism is set out in the table below. Percentage shares for Band 1, Band 2, and Band 3 are to be populated from the Base Case Financial Model before issuance of the RFP.

| Revenue Band | Concessionaire Share | Agency Share |
| --- | --- | --- |
| Up to Base Revenue Threshold | 100% | Nil |
| Band 1: 100–120% of Base Revenue | [●]% — insert from Financial Model | [●]% — insert from Financial Model |
| Band 2: 120–150% of Base Revenue | [●]% — insert from Financial Model | [●]% — insert from Financial Model |
| Band 3: >150% of Base Revenue | [●]% — insert from Financial Model | [●]% — insert from Financial Model |

Schedule S – Notices

[To Be Attached Hereto]

Schedule T – Termination Payments

| Sr. No. | Termination Payment Amount | Compensation Payable by GoS |
| --- | --- | --- |
|  | Concessionaire CP Failure Termination Amount | [Fifty percent (50%)] of the Approved Pre-Commencement Costs. |
|  | Agency CP Failure Termination Amount | [One hundred percent (100%)] of the Approved Pre-Commencement Costs |
|  | Non-Political Event Termination Amount | (a) the Termination Equity; plus (b) the Financing Due |
|  | Political Event Termination Amount | (a) the Termination Equity; plus (b) the Termination Dividend Amount, plus (c) the Financing Due |
|  | Concessionaire Default Termination Amount | (a) the Financing Due |
|  | GoS Default Termination Amount | (a) the Termination Equity; plus (b) the Termination Dividend Amount, plus (c) the Financing Due |
|  | Corrupt Act Termination Amount | (a) the Financing Due |
|  | Change in Law Termination Amount | (a) the Termination Equity; plus (b) the Termination Dividend Amount, plus (c) the Financing Due |

Schedule U – Financial Model

[To Be Attached Hereto]

Schedule V – Illustrations

[To Be Attached Hereto]

Schedule W – Agency Financial Instrument And Related Matters

Schedule W governs the Agency Financial Instrument (e.g., Agency guarantee or debit authority from the State Bank of Pakistan) that backstops the Agency’s payment obligations. This Schedule is only applicable where the Agency provides a Financial Instrument.

Part A — Definitions

First Agency Financial Instrument means an irrevocable and unconditional guarantee from the Agency in a form and substance acceptable to [the Financiers (where financing is present) / the Concessionaire (where no financing)] as a stand-by letter of credit or a debit authority from the Agency authorizing the State Bank of Pakistan to debit the relevant account of the Agency with the State Bank of Pakistan on demand;

First Agency Financial Instrument Amount means shall have the meaning ascribed thereto in Section 17.8.3(a)(i); being the aggregate amount of the [Projected Termination Payment / Maximum Financing Due] as set out in the Financial Model;

Agency Financial Instrument Issuing Bank means a scheduled bank in Pakistan with a minimum credit rating of at least [AA- as rated by JCR-VIS or an equivalent rating by PACRA];

Debt Repayment Date means the earlier of (a) the date falling on the tenth anniversary of the Substantial Completion Date; and (b) the date on which the financing availed pursuant to the Financing Term Sheet is scheduled to be fully repaid which shall in any event not be earlier than eight (08) years commencing from Scheduled Substantial Completion Date;

Part B — Extension Mechanism

[•]

Schedule X – Change In Control, Change In Complete Control And Change In Shareholding

Schedule X governs share transfer restrictions at the SPV level. These restrictions are fundamental to the long-term governance of the PPP project. They apply for the entire Concession Period.

Part A — Definitions

Change in Complete Control means any issuance, sale, transfer, conveyance, disposal or any event, transaction, arrangement, Encumbrance or agreement of any nature that results in or may result in:

- the issuance of any Class A Share to any Person other than the Sponsor; or

- the transfer of direct and/or indirect, legal and/or beneficial ownership of any shares, or securities convertible into shares, that causes or may cause the sale, transfer, conveyance or disposal of the Sponsor's legal and/or beneficial ownership in the total (or any part thereof) paid up and outstanding Class A Shares; and

- the Sponsor, as a result of (a) or (b) above, holding less than one hundred percent (100%) of the Class A Shares and/or losing the power to direct the management, policies, control and/or decisions of the Concessionaire;

Change in Control means any such transaction that results in or may result in:

- issuance of any Class A Share to any Person other than the Sponsor(s); or

- transfer of direct and/or indirect ownership in the total (or any part thereof) paid up and outstanding Class A Shares of the Concessionaire; and

- the Sponsor(s) divesting more than or equal to forty-nine percent (49%) of the Class A Shares and/or losing the power to direct the management, policies and decisions of the Concessionaire;

Change in Shareholding means any such transaction where:

- issuance of any Class A Share to any Person other than the Sponsor; or

- transfer of direct and/or indirect ownership in the Class A Shares; and

- the Sponsor as a result divests up to forty-nine percent (49%) of Class A Shares provided that the Sponsor does not lose the power to direct the management, policies and decisions of the Concessionaire;

Part B — Operative Restrictions

Section 10.3.1 — Lock-Up Period (No Change in Complete Control)

The Concessionaire shall not permit any Change in Complete Control until the second anniversary of the Substantial Completion Date, unless: (a) required by Applicable Laws; or (b) approved in writing by the Agency.

Section 10.3.2 — Post Lock-Up (Change in Control requires Agency Approval)

Following the second anniversary of the Substantial Completion Date, any Change in Control requires: (a) Applicable Laws compliance; (b) prior written approval of the Agency; (c) in a consortium, replacement of the lead member with an entity of equivalent or better qualifications; and (d) the incoming member holding at least 51% of the Shares.

Section 10.3.3 — Change in Shareholding (Notification Only)

Following the second anniversary of the Substantial Completion Date, the Concessionaire may permit a Change in Shareholding without Agency consent but with prior Notification, provided the acquiring Person is: (a) not from a proscribed nationality; (b) not blacklisted by any Government Authority; and (c) not a defaulter of any bank or financial institution.

Schedule Y – Agency Specific Permits

[To Be Attached Hereto]

Input required from ADB on the timeline.

Input required from ADB on the timeline.

Input required from ADB whether the reasonable legal fees to be part of Losses or not.

Concept of Persistent Breach of O&M Requirements to be discussed with ADB.

Drafting Note: Mandating strict adherence to the original financial terms and structural framework during any extension period is a novel addition to this template. This mechanism is specifically engineered to lock in the baseline risk allocation and commercial equilibrium established at Financial Close, thereby precluding backdoor renegotiations. The Implementing Agency must ensure this continuity constraint aligns with the overarching regulatory framework while maintaining the integrity of the original procurement parameters. To be discussed with ADB.

To be discussed with ADB.

To be discussed with ADB.

Drafting Note: This Conditions Precedent is adapted from the TP1 precedent; however, it has been structurally amended to resolve a temporal paradox found in the legacy draft. The original TP1 text required the Concessionaire to submit a certificate dated "as of the Commencement Date" in order to achieve the Commencement Date—creating a circular impossibility, as the Commencement Date cannot be formally declared until the certificate is received and verified. This standardized version corrects the legal mechanic by accurately anchoring the certification of warranties to the actual date the certificate is executed and submitted to the Agency.

To be discussed with ADB.

To be discussed with ADB.

To be discussed with ADB.

TBD with ADB.

TBD with ADB.

This point is taken from Hubcanal Concession Areement & Islamabad Airport Concession Agreement.

This provision is taken from TP 1 Concession Agreement.

This point is taken from Hubcanal Concession Agreement.

This provision is taken from TP 1 Concession Agreement.

This Big four selection criteria is not dicussed in Hubcanal, Tp 1 and Islamabad Airport Concession Agreements.

To be discussed with ADB.

Islamabad Airport 16.1.4

Islamabad Airport 16.5

NED 20.1.1 (f)(i)(A)

The concept of “Project Development Milestones” and “Development Programme” to be discussed with ADB.

TBD with ADB.

TBD with ADB.

TBD with ADB.

While this has been proposed based on a precednt transaction undertaken by the Firm with ADB (TP1), it is not standrard practice in Pakistan to provide coverage fpr this risk. To be discussed with ADB.

For further discussion with ADB.

TBD with ADB.

TBD with ADB.

[Drafting Note] The minimum credit rating threshold must be calibrated against the quantum of any performance security or instrument to be issued. "A" is a common baseline but should be elevated to "AA-" for large-value instruments. Both PACRA and VIS equivalents must be specified.

[Drafting Note] Insert the start and end dates of the Accounting Year. If the Concessionaire's accounting year differs from the standard financial year (1 July – 30 June), the amended dates must be consistent with the Concessionaire's constitutional documents and tax filings.

[Drafting Note] Consider whether any other pre-commencement expenditure categories are project-specific (e.g., land survey costs, environmental consultant fees). If so, add as additional items under (d) et seq.

[Drafting Note]  Insert the applicable advance percentage. This percentage must be calibrated against the Additional Cost payment mechanism in Article 16 and should be consistent with the Base Case Financial Model.

[Drafting Note]  Insert the percentage cap. Standard market practice is 10–15% of Total Project Cost.

[Drafting Note]  Insert the daily liquidated damages rate. Typical market rate: 0.05–0.1% per day of the Development Performance Security amount.

[Conditional Amendment — If Financing Involved]  Lenders may require the Delayed Payment Rate to equal the weighted average cost of debt under the Financing Documents plus a margin, rather than KIBOR-based. Align with the Financing Term Sheet.

[Drafting Note]  Pre-Commencement period: amount should equal the bid security submitted at RFP stage. Post-Commencement period: typical range is 5–10% of Pre-estimated Project Cost, sized to cover likely delay damages.

[Conditional Amendment — If Islamic Financing]  Replace "bank guarantee" with "Shariah-compliant bank guarantee or kafalah instrument" and add a Takaful-based performance bond as an alternative.

[Drafting Note] Insert the number of months. Recommended minimum: twelve (12) months after Substantial Completion.

[Drafting Note] Insert the cap percentage. Must be calibrated against the financial model to ensure debt serviceability is not impacted. Recommended: 10–15%.

[Drafting Note] Insert the applicable reporting frequency (e.g., monthly or quarterly). The frequency must be consistent with the monitoring obligations of the Independent Engineer under Article 5 and the reporting obligations of the Concessionaire under Section 13.4.

[Drafting Note] Equity in this Agreement excludes shareholder loans. Where the project structure includes subordinated shareholder debt, a separate definition of "Shareholder Loans" should be added and the Equity definition updated to reference the exclusion explicitly.

[Conditional Amendment — If Tax Regime Is Fixed In Bid] Replace the tax exclusion bracket with the specific taxes (corporate income tax, WHT) fixed in the bid financial model, so that only changes to those specific tax heads qualify as Change in Law. A generic exclusion of "Tax" may be too broad.

[Drafting Note] Insert the agreed Concession Period duration in years (numeric and in words). The Final Expiry Date drives the Concession Period, the Project Site Land Instrument Right Period, and all long-stop termination mechanics. Confirm with ADB/MDB before RFP issuance where applicable.

[Drafting Note] Insert the agreed survival period in years. A minimum period of two (2) years is standard; consider extending to three (3) or five (5) years for higher-risk projects. Must be consistent with the limitation of liability provisions in Article 9.

[Drafting Note — ADB Concurrence Required] Insert the number of years (numeric and in words). Minimum: two (2) years; Maximum: five (5) years, subject to ADB/MDB concurrence. Confirm with the Agency's transaction advisors before RFP issuance.

[Drafting Note] Insert the minimum rating (e.g., AA-) and both rating agencies (JCR-VIS and PACRA). Do not leave blank for RFP issuance.

[Drafting Note] Insert the minimum indemnification threshold in PKR (numeric and in words). This amount should be calibrated against the scale of the Project to avoid trivial claims while ensuring genuine losses are compensable.

[Drafting Note] The definition of O&M Costs is intended to capture all operational expenditures. Drafting Counsel should confirm with the Agency's technical advisors whether any specific cost categories are to be explicitly included or excluded based on the project's O&M structure.

[Drafting Note] Insert the applicable percentage of projected annual O&M Costs. A typical range is 5–10%, sized to cover the estimated cost of remedying foreseeable O&M defaults in any Operational Year.

[Drafting Note] Insert the applicable reporting frequency (e.g., quarterly). The O&M Status Reporting Timeline must be consistent with the Independent Engineer's obligations under Article 5 and the O&M monitoring provisions of Article 19.

[Drafting Note]  The Order of Priority reflects a standard PPP Escrow waterfall. Where Islamic Financing is involved, the reference to "interest" in item (b) should be replaced with "profit/markup/return". Drafting Counsel must ensure consistency with the executed Escrow Agreement.

[Drafting Note] The list of Pre-Commencement Activities must be reviewed and supplemented by the Agency's technical advisors prior to RFP issuance. The agreed list should be annexed to Schedule D (Project Facilities) or Schedule F (Project Site), as appropriate.

[Drafting Note] Insert the specific administrative jurisdiction (district, province) of the Project Site. This determines which courts have territorial jurisdiction and which local bye-laws apply.

[Drafting Note] Select the applicable delivery mechanism and insert both (i) the acronym/name and (ii) the corresponding scope of activities. The selection of Project Modality has downstream implications for Section 7 (Representations), Article 10 (Funding), and Schedule L (Financing Matters). Ensure all cross-references are updated consistently.

[Drafting Note] Select the applicable delivery mechanism and insert both (i) the acronym/name and (ii) the corresponding scope of activities. The selection of Project Modality has downstream implications for Section 7 (Representations), Article 10 (Funding), and Schedule L (Financing Matters). Ensure all cross-references are updated consistently.

[Drafting Note] Project Requirements is intended to function as an umbrella term capturing all applicable obligations of the Concessionaire. Drafting Counsel should review all cross-references to this term in the main body to ensure consistency.

[Drafting Note] Specify the correct legal instrument (lease, sub-lease, license, or right-of-way) depending on the land title structure. The Right Period should be co-terminus with or slightly exceed the Concession Period.

[Drafting Note] Select Option A (Transfer Date — expiry co-terminus with Concession Period) or Option B (end of the Project Site Land Instrument Right Period — fixed period). Delete the inapplicable option. Option A is preferred for certainty.

[Drafting Note] Insert the agreed duration in years or months. The Project Site Land Instrument Right Period must be co-terminus with or slightly exceed the Final Expiry Date to ensure continuity of the Concessionaire's right to occupy the Project Site.

[Drafting Note] Insert the name of the applicable provincial environmental protection authority (e.g., Sindh Environmental Protection Agency). Confirm the correct authority with the Agency before RFP issuance.

[Conditional Amendment — If No Financing] Delete "(a) the Financial Close Date" from the list of Repetition Dates, as Financial Close will not occur. The remaining dates (b) through (d) continue to apply.

[Drafting Note]  The definition of Revenue must be read alongside the Revenue Sharing Mechanism in Schedule R. Drafting Counsel must confirm that the categories of Revenue are consistent with the revenue projections in the Base Case Financial Model.

[Drafting Note] Insert the number of days. Standard: 120–180 days. This is the Conditions Precedent long-stop date; if the Conditions Precedent are not satisfied by this date, either Party may terminate.

[Drafting Note] Insert the construction period in months (typically 24–60 months depending on project scale). This period drives Development Period Damages accrual and the long-stop termination date.

[Conditional Amendment — If No Agency Financial Instrument]  If the Agency is not providing a financial guarantee or Financial Instrument, delete item (a) entirely and cross-reference Section 17 to confirm the provision is removed. If the Equity Funding & Utilization Agreement does not apply, delete item (b).

[To Be Discussed With ADB]  The scope of the Specific Agency Undertaking should be finalised in consultation with the Agency's transaction advisors and ADB. The undertaking as drafted should be populated with concrete obligations beyond permit procurement where appropriate.

[Conditional Amendment — If No Financing]  If the project is entirely equity-funded, delete items (e), (f) and (g) relating to the Financing Term Sheet, Financing Documents, and Financial Close Achievement Notice. Amend Section 3 of the main Agreement accordingly.

[Drafting Note] The Specific Concessionaire Undertaking is intentionally left as a project-specific placeholder. Drafting Counsel must populate this definition with the concrete technical or commercial undertaking(s) specific to the Project. Do not leave blank for RFP issuance.

[Drafting Note] The list of Specific Persons must be reviewed and finalised by the Agency in conjunction with its health and safety advisors prior to RFP issuance, identifying all categories of persons whose safety is to be specifically protected.

[Drafting Note] Sponsor Base Equity Amount is cross-referenced to the Financial Model and should be stated in absolute PKR terms to avoid ambiguity if the Financial Model is later revised. Confirm the amount with the Agency's financial advisors before RFP issuance.

[Drafting Note] This definition is deliberately left project-specific. Drafting Counsel must populate this in conjunction with Schedule G (Completion Tests Matters) and the technical annexures. The criteria must be objective, measurable, and agreed with the Independent Engineer before RFP issuance, as they drive the issuance of the Completion Certificate, the commencement of the Operations Period, and the release of the Development Performance Security.

[Drafting Note]  Detailed Engineering Design and Preliminary Engineering Design are retained as standardised definitions. The approval timelines in Clause 5 of the Schedule C (120 days for PED, 4 months post-Commencement for DED) are standardised. Adjust only where there is strong technical justification, as these periods are reflected in the Scheduled Commencement Date.

[Drafting Note]  Construction Drawings is defined here in Schedule C as it is only relevant where the Project involves physical engineering and construction. Where this Schedule is deleted for non-construction projects, the definition of Construction Drawings must also be removed from Article 1 of the main body.

[Drafting Note] Schedule B (Design Requirements) must be completed by the Agency's technical team and attached before RFP issuance. It should set out all technical design standards, performance specifications, material standards and quality benchmarks applicable to the Project. It is intentionally left blank in the standardised template.

[Drafting Note] Insert the specific submission timeline (120 days from the Effective Date is standardised). The Approved Preliminary Engineering Design is critical as it determines the exact Project Site area for land acquisition and utility relocation. Drafting Counsel must ensure that the Agency's land delivery obligations under Section 4 are aligned with this timeline.

[Conditional Amendment — If Project Is Phased]  Where the Project is phased or segmented, add segment-specific references throughout Part B. Insert "in respect of each Phase/Segment" after each reference to "Construction Drawings" in Clause 1 through Clause 5 of the Schedule C.

[Conditional Amendment — If Non-Infrastructure Project]  The list of drawing types in Section 12.2A is drafted for a generic infrastructure project. For sector-specific projects (e.g., water treatment, energy, port infrastructure), replace the enumerated drawing types with the relevant technical drawing categories. The Agency's technical advisors must confirm the appropriate drawing list before RFP issuance.

[Drafting Note] The four (4) copy submission requirement is standardised. Where the Agency requires digital-only submission, replace with "electronic copies in [BIM/CAD/PDF] format as specified by the Agency" and update Section 12.4.2 accordingly.

[Drafting Note]  The as-built Construction Drawings submission obligation (forty-five (45) days from Substantial Completion Date) is a condition precedent to issuance of the Final Project Development Completion Certificate. Drafting Counsel must ensure this is reflected in Schedule G (Completion Tests Matters) as a completion condition.

[Drafting Note] The Proposed Preliminary Design submission (120 days from Effective Date) triggers the Agency's land acquisition and utility relocation obligations. The Project Site Land Instrument Right Period in Schedule B must be consistent with this timeline.

[Drafting Note]  The deemed-approval mechanic for the Detailed Engineering Design (twenty (20) day inactivity notice, followed by ten (10) day cure) is standardised. The Independent Engineer Contract must include corresponding obligations to meet these review timelines.

[Conditional Amendment — If No Financing] Delete "(b) Financing Markup" from this definition. "Financing Markup" is only applicable where the Concessionaire has financing in place and incurs additional financing costs as a result of a delay caused by a Relief Event.

This is to be discussed with ADB.

[Drafting Note] The 90-day lookback for Operations Phase revenue is standardised. For seasonal projects (e.g., tourism infrastructure), consider using a 12-month average to smooth seasonal variation.

This is to be discussed with ADB.

[Conditional Amendment — If No Financing] Delete Part 2, Section 2 (Financing Markup) in its entirety.

[Conditional Amendment — If Islamic Financing] Replace "interest" with "profit/markup/return" throughout, and include Takaful-related charges where applicable.

[Drafting Note] The 21-day determination period is standardised and tight. Ensure the Independent Engineer and Independent Auditor appointment agreements include this obligation. Consider adding a deemed-approval mechanic if no determination is made within 21 days.

[Conditional Amendment — If Adb/Mdb Financing] ADB lenders may require the Relief Order process to include a Financiers' Agent review step prior to the 21-day determination. Add a sub-clause permitting the Financiers' Agent to observe (but not veto) the determination process.

[Master Trigger] ENTIRE SCHEDULE L APPLIES ONLY IF PROJECT HAS THIRD-PARTY FINANCING. IF NO FINANCING — DELETE SCHEDULE L AND ALL CROSS-REFERENCES THERETO.

[Conditional Amendment — If International Lenders] Add the following definition: "Financiers' Agent means the lead arranger or facility agent appointed under the Financing Documents to act on behalf of the syndicate of Financiers." Confirm agent appointment with the lead arranger.

[Drafting Note] The 30-day objection period for both the initial Financing Term Sheet and subsequent amendments is standardised. The Agency's review should focus on: (i) does the debt repayment exceed the Financing Component in the Base Case Financial Model; (ii) does the Agency's Termination Payment exposure increase materially; (iii) are new security interests being created over Agency assets or revenue.

[Drafting Note] The Financial Close Achievement Notice triggers: (i) the start of the 30-day window for the Agency to issue/confirm the Commencement Certificate; and (ii) the activation of financing-related provisions throughout the Agreement. Drafting Counsel must verify all financing activation triggers are cross-referenced.

[Conditional Amendment — If Financing] The Financiers may require a step-in right consent mechanism such that the Agency cannot assign this Agreement to a successor entity without Financier consent if doing so would impair the security structure. Add: "provided further that, during any period when any Financing Due is outstanding, any assignment to a successor Government Authority shall require the prior written consent of the Financiers' Agent (which shall not be unreasonably withheld or delayed)."

[Drafting Note] The Financiers' Cure Period is a key lender protection and essential for bankability. 30 Business Days is standard; some lenders request 60 calendar days for complex defaults. Confirm with the lead arranger.

[Drafting Note] The Concession Direct Agreement (CDA) is a separate document to be negotiated with lenders. The CDA typically includes: (i) step-in rights; (ii) curing rights; (iii) Agency's obligations on Termination; (iv) substitution rights. CDA negotiation should begin in parallel with the Financing Term Sheet review.

[Conditional Amendment — If International Lenders (Adb, Ifc, Deg, Fmo, Etc.)] This election is mandatory. Specify in Schedule B: (i) ICC or UNCITRAL; (ii) seat of arbitration (London, Singapore, or Dubai recommended); (iii) language (English). The Agency may need Ministry of Law and Sindh Cabinet approval before agreeing to international arbitration.

Concept to be incorporated after discussion with ADB.

[ Drafting Note] Fill in the equity class description based on the chosen Option (A, B, or C).

[ Drafting Note] Insert the Agency Funding Amount in absolute PKR figures, as set out in the Base Case Financial Model.

[Drafting Note] Sponsor Base Equity Amount is cross-referenced to the Financial Model. It should be stated in absolute PKR terms to avoid ambiguity if the model is later revised.

[Conditional Amendment — If Option A (No Agency Equity)] Delete Section 10.2.1 in its entirety.

[Conditional Amendment — If Different Province/Entity] Replace "VIABILITY GAP FUND, GOVERNMENT OF SINDH" with the correct registered name of the Government entity that will hold the Class B Shares. For Punjab: "VIABILITY GAP FUND, GOVERNMENT OF PUNJAB" etc.

[Conditional Amendment — If No Advertising Or Utility Revenues] Delete the inapplicable revenue stream from Class B Dividends. If both are absent, consider whether Class B Shares serve any purpose at all and whether Option A or C should be selected instead.

[Conditional Amendment — If Option C (Class E Shares)] Amend to "…other than Class A Shares, Class B Shares, and Class E Shares…" and add a definition of Class E Shares with the applicable special rights.

[Conditional Amendment — If Additional Escalable Items] Some projects include additional items such as explosives (for tunnelling), aggregates (for remote projects), or copper wiring (for electrical infrastructure). Add project-specific items as additional bullets here and in the Price Escalation Agreement.

[Drafting Note] The four baseline Escalable Items (cement, bitumen, steel, POL) are indexed to the Pakistan Bureau of Statistics (PBS) monthly statistical bulletin. If any item is not covered by the PBS bulletin, the Agreement provides that the Independent Engineer and Independent Auditor shall determine the price. Confirm PBS coverage before RFP issuance.

[Conditional Amendment — If No Price Escalation Mechanism] If the Parties agree that cost escalation risk is fully on the Concessionaire (fixed-price contract), delete Schedule Z in its entirety and remove all references to the Price Escalation Agreement throughout the Agreement (including from the Agency Agreements definition and Specific Agency CPs in Schedule B).

[Drafting Note] The de-escalation mechanism is symmetric — if input prices fall, the Agency receives a benefit. Drafting Counsel must ensure the Price Escalation Agreement specifies the precise mechanism for calculating and crediting the De-escalation Amount (e.g., against toll payments, as a direct payment, or as a set-off).

Please note that a very preliminary revenue matters schedule has been developed for now.

[ Drafting Note] Fill in the Excess Revenues threshold. This is project-specific and must be derived from the Base Case Financial Model. The threshold is typically set at a level that provides the Concessionaire with its projected IRR before sharing begins.

[Drafting Note] The revenue sharing bands and percentages must be calibrated by the transaction financial advisor based on the risk/return profile of the project. Higher sharing with the Agency in upper bands incentivises both parties to maximise traffic without giving the Concessionaire a windfall.

The percentage of the Approved Pre-Commencement Costs needs to be discussed with ADB.

The percentage of the Approved Pre-Commencement Costs needs to be discussed with ADB.

[Conditional Trigger] entire Schedule W applies only if the Agency is providing a financial instrument (guarantee / debit authority / standby lc). If the Agency is not providing a financial instrument, delete Schedule W and all cross-references thereto, including section 17.8 and the related Specific Agency CP.

[Conditional Amendment — If Financing] The First Agency Financial Instrument must be acceptable to the Financiers (not just the Concessionaire). Confirm form and substance requirements with the lead arranger's counsel.

[Conditional Amendment — If No Financing] Replace "acceptable to the Financiers" with "acceptable to the Concessionaire".

[Drafting Note] The Financial Instrument Amount is a key risk allocation point. It should cover the maximum Termination Payment the Agency could owe in a worst-case scenario. Fill from the Financial Model.

[Drafting Note] The issuing bank must be a high-rated Pakistani bank. Align minimum rating with the Minimum Credit Rating in Schedule B.

[Drafting Note] The Agency Financial Instrument Issuing Bank is the bank that issues the instrument on behalf of the Agency (i.e., the bank that gives the guarantee or LC). This is different from the Acceptable Pakistani Bank, which is the bank issuing the Concessionaire's performance security.

The clauses need to be developed for the financial instruments after discussion with ADB.

[Drafting Note] The 2-year post-Substantial Completion lock-up is standardised. For very large or critical infrastructure, the Agency may seek a 3-year lock-up. This should be determined at RFP stage.

[Conditional Amendment — If Financing] The Financiers may require a carve-out from the lock-up for enforcement of their share pledge under the Financing Documents. Add: "provided that the foregoing shall not restrict the Financiers from enforcing a share pledge over the Class A Shares in accordance with Section 27.2 (Permitted Assignment and Charges)."

[Conditional Amendment — If Financing] Any Change in Shareholding that would affect the share pledge security must be notified to the Financiers' Agent simultaneously with the Agency notification. Add: "and simultaneously notifying the Financiers' Agent in writing."

[Drafting Note] The three-tier control structure (Change in Complete Control → Change in Control → Change in Shareholding) with progressively relaxing restrictions is a well-tested market mechanism. Drafting Counsel should ensure the definitions are mutually exclusive and collectively exhaustive to avoid classification disputes.